## TRUE Data (hidden)
Job Name | Title
88 Falls of The Cape | Rails Complete
120 Annandale | Paint Complete
111 Annandale | Rails Complete
111 Annandale | Paint Complete
161 Stonewood | Paint Complete
165 Stonewood | Paint Complete
131 Duncans Creek | Trellis Complete
14 Holding Village Mews TH | Paint Complete
140 Annandale | Paint Complete
381 Vineyards @ Chatham Park | Paint Complete
380 Vineyards @ Chatham Park | Paint Complete
38 Stanat Place TH | Paint Complete
82 Twinleaf Townes TH | Paint Complete
81 Twinleaf Townes TH | Paint Complete
80 Twinleaf Townes TH | Paint Complete
79 Twinleaf Townes TH | Paint Complete
42 Stanat Place TH | Paint Complete
157 Preserve @ Jones Dairy | Paint Complete
60 Meadow @ Jones Dairy | Invoiced
60 Meadow @ Jones Dairy | Job Complete/Inspected
776 Edge of Auburn - Classic | Invoiced
244 Turkey Ridge | Paint Complete
244 Turkey Ridge | 100% Job Complete
244 Turkey Ridge | Invoiced
244 Turkey Ridge | Job Complete/Inspected
433 Oak Manor | Invoiced
433 Oak Manor | Job Complete/Inspected
90 River Glen | Invoiced
90 River Glen | Job Complete/Inspected
91 River Glen | Invoiced
91 River Glen | Job Complete/Inspected
92 River Glen | Invoiced
92 River Glen | Job Complete/Inspected
120 Annandale | 100% Job Complete
120 Annandale | Invoiced
120 Annandale | Job Complete/Inspected
184 Falls Village | Invoiced
184 Falls Village | Job Complete/Inspected
183 Falls Village | Invoiced
183 Falls Village | Job Complete/Inspected
182 Falls Village | Invoiced
182 Falls Village | Job Complete/Inspected
251 Turkey Ridge | Paint Complete
251 Turkey Ridge | 100% Job Complete
251 Turkey Ridge | Invoiced
251 Turkey Ridge | Job Complete/Inspected
11 Ellington Estates | Invoiced
11 Ellington Estates | Job Complete/Inspected
3 Franklin Townes TH | Invoiced
2 Franklin Townes TH | Invoiced
245 Turkey Ridge | Paint Complete
245 Turkey Ridge | 100% Job Complete
245 Turkey Ridge | Invoiced
245 Turkey Ridge | Job Complete/Inspected
95 Meadow @ Jones Dairy | Invoiced
95 Meadow @ Jones Dairy | Job Complete/Inspected
50 Little River | 100% Job Complete
50 Little River | Invoiced
50 Little River | Job Complete/Inspected
37 Gardner Farms | 100% Job Complete
37 Gardner Farms | Invoiced
37 Gardner Farms | Job Complete/Inspected
49 Kipling Creek | Invoiced
49 Kipling Creek | Job Complete/Inspected
47 Kipling Creek | Invoiced
47 Kipling Creek | Job Complete/Inspected
39 Kipling Creek | Invoiced
39 Kipling Creek | Job Complete/Inspected
33 Kipling Creek | Invoiced
33 Kipling Creek | Job Complete/Inspected
21 Kipling Creek | Invoiced
21 Kipling Creek | Job Complete/Inspected
10 Kipling Creek | Invoiced
10 Kipling Creek | Job Complete/Inspected
137 Marin Woods | 100% Job Complete
137 Marin Woods | Invoiced
137 Marin Woods | Job Complete/Inspected
86 Ashcroft | Invoiced
86 Ashcroft | Job Complete/Inspected
96 Providence Oaks 30' | Paint Complete
84 Providence Oaks 40 | Paint Complete
83 Providence Oaks 40' | Paint Complete
80 Providence Oaks 40 | Paint Complete
105 Providence Oaks 30 | Paint Complete
97 Providence Oaks 30' | Paint Complete
99 Providence Oaks 30' | Paint Complete
21 Providence Oaks 30' | Paint Complete
50 Providence Oaks 40' | Paint Complete
49 Providence Oaks 40' | Paint Complete
87 Ashcroft | Invoiced
87 Ashcroft | Job Complete/Inspected
30 Elk Creek | 100% Job Complete
30 Elk Creek | Invoiced
30 Elk Creek | Job Complete/Inspected
25 Elk Creek | 100% Job Complete
25 Elk Creek | Invoiced
25 Elk Creek | Job Complete/Inspected
155 Preserve @ Jones Dairy | Paint Complete
155 Preserve @ Jones Dairy | 100% Job Complete
155 Preserve @ Jones Dairy | Invoiced
155 Preserve @ Jones Dairy | Job Complete/Inspected
348 Vineyards @ Chatham Park | Paint Complete
74 Caitlin Crossing | Invoiced
187 Falls Village | Invoiced
187 Falls Village | Job Complete/Inspected
111 Falls Village | Invoiced
111 Falls Village | Job Complete/Inspected
151 Falls Village | Invoiced
151 Falls Village | Job Complete/Inspected
246 Turkey Ridge | Paint Complete
246 Turkey Ridge | 100% Job Complete
246 Turkey Ridge | Invoiced
246 Turkey Ridge | Job Complete/Inspected
186 Falls Village | Invoiced
186 Falls Village | Job Complete/Inspected
307 S Elm | Invoiced
307 S Elm | Job Complete/Inspected
126 Hickory Grove | Paint Complete
153 Falls Village | Invoiced
153 Falls Village | Job Complete/Inspected
126 Hickory Grove | Invoiced
126 Hickory Grove | Job Complete/Inspected
125 Hickory Grove | Paint Complete
125 Hickory Grove | Invoiced
125 Hickory Grove | Job Complete/Inspected
106 Hickory Grove | Invoiced
106 Hickory Grove | Job Complete/Inspected
104 Hickory Grove | Paint Complete
104 Hickory Grove | Invoiced
104 Hickory Grove | Job Complete/Inspected
199 Falls Village | Invoiced
199 Falls Village | Job Complete/Inspected
89 Twinleaf Townes | Paint Complete
88 Twinleaf Townes | Paint Complete
80 Providence Oaks 40 | Invoiced
80 Providence Oaks 40 | Job Complete/Inspected
105 Providence Oaks 30 | Invoiced
105 Providence Oaks 30 | Job Complete/Inspected
106 Guin | Invoiced
106 Guin | Job Complete/Inspected
4 Rollins Acres | Invoiced
4 Rollins Acres | Job Complete/Inspected
87 Twinleaf Townes | Paint Complete
86 Twinleaf Townes | Paint Complete
85 Twinleaf Townes | Paint Complete
264 Turkey Ridge | Paint Complete
264 Turkey Ridge | 100% Job Complete
264 Turkey Ridge | Invoiced
264 Turkey Ridge | Job Complete/Inspected
128 Pines at Wake Crossing | Invoiced
128 Pines at Wake Crossing | Job Complete/Inspected
127 Pines at Wake Crossing | Invoiced
127 Pines at Wake Crossing | Job Complete/Inspected
159 Preserve @ Jones Dairy | Paint Complete
159 Preserve @ Jones Dairy | Invoiced
159 Preserve @ Jones Dairy | Job Complete/Inspected
876 Edge of Auburn - | Invoiced
878 Edge of Auburn - | Invoiced
845 Edge of Auburn - | Invoiced
842 Edge of Auburn - | Invoiced
73 Caitlin Crossing | Invoiced
158 Preserve @ Jones Dairy | Paint Complete
158 Preserve @ Jones Dairy | Invoiced
158 Preserve @ Jones Dairy | Job Complete/Inspected
777 Edge of Auburn - Classic | Invoiced
774 Edge of Auburn - Classic | Invoiced
774 Edge of Auburn - Classic | Job Complete/Inspected
12 Olivet | Invoiced
12 Olivet | Job Complete/Inspected
86 Carolina Landing | 100% Job Complete
86 Carolina Landing | Invoiced
86 Carolina Landing | Job Complete/Inspected
50 OYL | Invoiced
50 OYL | Job Complete/Inspected
48 Little River | 100% Job Complete
48 Little River | Invoiced
48 Little River | Job Complete/Inspected
78 Twinleaf Townes TH | Paint Complete
77 Twinleaf Townes TH | Paint Complete
72 Caitlin Crossing | Invoiced
46 Stanat Place TH | Paint Complete
45 Stanat Place TH | Paint Complete
44 Stanat Place TH | Paint Complete
41 Stanat Place TH | Paint Complete
40 Stanat Place TH | Paint Complete
39 Stanat Place TH | Paint Complete
30 Stanat Place TH | Trellis Complete
29 Stanat Place TH | Trellis Complete
28 Stanat Place TH | Trellis Complete
27 Stanat Place TH | Trellis Complete
23 Stanat Place TH | Trellis Complete
22 Stanat Place TH | Trellis Complete
26 Walnut Hall | Paint Complete
26 Walnut Hall | Invoiced
26 Walnut Hall | Job Complete/Inspected
21 Stanat Place TH | Trellis Complete
18 Stanat Place TH | Trellis Complete
16 Stanat Place TH | Trellis Complete
13 Stanat Place TH | Trellis Complete
12 Stanat Place TH | Trellis Complete
11 Stanat Place TH | Trellis Complete
8 Stanat Place TH | Trellis Complete
7 Stanat Place TH | Trellis Complete
6 Stanat Place TH | Trellis Complete
3 Stanat Place TH | Trellis Complete
85 Twinleaf Townes | Invoiced
85 Twinleaf Townes | Job Complete/Inspected
86 Twinleaf Townes | Invoiced
86 Twinleaf Townes | Job Complete/Inspected
87 Twinleaf Townes | Invoiced
87 Twinleaf Townes | Job Complete/Inspected
88 Twinleaf Townes | Invoiced
88 Twinleaf Townes | Job Complete/Inspected
89 Twinleaf Townes | Invoiced
89 Twinleaf Townes | Job Complete/Inspected
90 Twinleaf Townes | Invoiced
90 Twinleaf Townes | Job Complete/Inspected
159 Auburn Station | Invoiced
5 Auburn Station | Invoiced
16 Caitlin Crossing | Invoiced
16 Caitlin Crossing | Job Complete/Inspected
771 Edge of Auburn - Classic | Invoiced
771 Edge of Auburn - Classic | Job Complete/Inspected
197 Falls Village | 100% Job Complete
197 Falls Village | Invoiced
197 Falls Village | Job Complete/Inspected
179 Falls Village | Invoiced
179 Falls Village | Job Complete/Inspected
158 Falls Village | Invoiced
158 Falls Village | Job Complete/Inspected
155 Falls Village | Invoiced
155 Falls Village | Job Complete/Inspected
84 Summer Place | Invoiced
84 Summer Place | Job Complete/Inspected
83 Summer Place | 100% Job Complete
83 Summer Place | Invoiced
83 Summer Place | Job Complete/Inspected
82 Summer Place | 100% Job Complete
82 Summer Place | Invoiced
82 Summer Place | Job Complete/Inspected
78 Summer Place | Invoiced
78 Summer Place | Job Complete/Inspected
77 Summer Place | Invoiced
77 Summer Place | Job Complete/Inspected
76 Summer Place | Invoiced
76 Summer Place | Job Complete/Inspected
75 Summer Place | Invoiced
75 Summer Place | Job Complete/Inspected
81 Sorrell Oaks | Invoiced
81 Sorrell Oaks | Job Complete/Inspected
92 Finley Landing TH | Invoiced
91 Finley Landing TH | Invoiced
90 Finley Landing TH | Invoiced
89 Finley Landing TH | Invoiced
88 Finley Landing TH | Invoiced
123 Hickory Grove | Paint Complete
123 Hickory Grove | Invoiced
123 Hickory Grove | Job Complete/Inspected
124 Hickory Grove | Paint Complete
124 Hickory Grove | Invoiced
124 Hickory Grove | Job Complete/Inspected
16 Carolina Overlook Twin Villas | Paint Complete
146 Trails @ Young Farm | Paint Complete
710 Glascock | Invoiced
710 Glascock | Job Complete/Inspected
111 Annandale | Invoiced
111 Annandale | Job Complete/Inspected
192 Falls Village | Invoiced
192 Falls Village | Job Complete/Inspected
200 Falls Village | Invoiced
200 Falls Village | Job Complete/Inspected
191 Falls Village | Invoiced
191 Falls Village | Job Complete/Inspected
17 Carolina Overlook Twin Villas | Paint Complete
155 Chavis | Invoiced
155 Chavis | Job Complete/Inspected
20 Caitlin Crossing | Invoiced
20 Caitlin Crossing | Job Complete/Inspected
41 Gardner Farms | 100% Job Complete
41 Gardner Farms | Invoiced
41 Gardner Farms | Job Complete/Inspected
4517 Chatham Park North Village | Invoiced
4517 Chatham Park North Village | Job Complete/Inspected
157 Preserve @ Jones Dairy | Invoiced
157 Preserve @ Jones Dairy | Job Complete/Inspected
190 Falls Village | Invoiced
190 Falls Village | Job Complete/Inspected
63 Twinleaf Townes | Paint Complete
62 Twinleaf Townes | Paint Complete
61 Twinleaf Townes | Paint Complete
76 Stonewood | Paint Complete
168 Trails @ Young Farm | Paint Complete
168 Trails @ Young Farm | Invoiced
168 Trails @ Young Farm | Job Complete/Inspected
189 Falls Village | Invoiced
189 Falls Village | Job Complete/Inspected
161 Stonewood | Invoiced
161 Stonewood | Job Complete/Inspected
4518 Chatham Park North Village | Invoiced
4518 Chatham Park North Village | Job Complete/Inspected
110 Falls Village | Invoiced
110 Falls Village | Job Complete/Inspected
152 Falls Village | Invoiced
152 Falls Village | Job Complete/Inspected
381 Vineyards @ Chatham Park | Invoiced
381 Vineyards @ Chatham Park | Job Complete/Inspected
83 Providence Oaks 40' | Invoiced
83 Providence Oaks 40' | Job Complete/Inspected
96 Providence Oaks 30' | Invoiced
96 Providence Oaks 30' | Job Complete/Inspected
89 River Glen | Invoiced
89 River Glen | Job Complete/Inspected
88 River Glen | Invoiced
88 River Glen | Job Complete/Inspected
136 River Glen | Invoiced
136 River Glen | Job Complete/Inspected
79 Providence Oaks 40' | Paint Complete
59 Twinleaf Townes | Paint Complete
85 Providence Oaks 40' | Paint Complete
78 Providence Oaks 40' | Paint Complete
107 Annandale | Paint Complete
107 Annandale | Invoiced
107 Annandale | Job Complete/Inspected
16 Williams Grove | Screen Porch Complete
111 Trails @ Young Farm | Paint Complete
111 Trails @ Young Farm | Invoiced
111 Trails @ Young Farm | Job Complete/Inspected
9 Harvest Creek | Invoiced
9 Harvest Creek | Job Complete/Inspected
175 Williams Grove | Invoiced
175 Williams Grove | Job Complete/Inspected
86 Stonewood | Invoiced
86 Stonewood | Job Complete/Inspected
110 Trails at Young Farm | Paint Complete
137 River Glen | Invoiced
137 River Glen | Job Complete/Inspected
764 Edge of Auburn - Classic | Invoiced
764 Edge of Auburn - Classic | Job Complete/Inspected
93 Stonewood | Paint Complete
92 Stonewood | Paint Complete
90 Stonewood | Paint Complete
89 Stonewood | Paint Complete
88 Stonewood | Paint Complete
87 Stonewood | Paint Complete
75 Stonewood | Paint Complete
74 Stonewood | Paint Complete
72 Stonewood | Paint Complete
172 Trails at Young Farm | Paint Complete
164 Stonewood | Paint Complete
163 Stonewood | Paint Complete
73 Stonewood | Paint Complete
17 Caitlin Crossing | Invoiced
17 Caitlin Crossing | Job Complete/Inspected
175 Walton Farms PH2 | Invoiced
175 Walton Farms PH2 | Job Complete/Inspected
185 Falls Village | Invoiced
185 Falls Village | Job Complete/Inspected
195 Falls Village | Invoiced
195 Falls Village | Job Complete/Inspected
198 Falls Village | Invoiced
198 Falls Village | Job Complete/Inspected
188 Falls Village | Invoiced
188 Falls Village | Job Complete/Inspected
114 Falls Village | Invoiced
114 Falls Village | Job Complete/Inspected
113 Falls Village | Invoiced
113 Falls Village | Job Complete/Inspected
112 Falls Village | Invoiced
112 Falls Village | Job Complete/Inspected
108 Falls Village | Invoiced
108 Falls Village | Job Complete/Inspected
107 Falls Village | Invoiced
107 Falls Village | Job Complete/Inspected
18 Olivet | Invoiced
18 Olivet | Job Complete/Inspected
110 Carolina Landing | Invoiced
110 Carolina Landing | Job Complete/Inspected
109 Carolina Landing | Invoiced
109 Carolina Landing | Job Complete/Inspected
2 Providence Oaks 40' | Paint Complete
134 River Glen | Invoiced
134 River Glen | Job Complete/Inspected
135 River Glen | Invoiced
135 River Glen | Job Complete/Inspected
163 Stonewood | Invoiced
163 Stonewood | Job Complete/Inspected
164 Stonewood | Invoiced
164 Stonewood | Job Complete/Inspected
165 Stonewood | Invoiced
165 Stonewood | Job Complete/Inspected
87 Stonewood | Invoiced
87 Stonewood | Job Complete/Inspected
Pinehurst Ct- Pinehurst | Job Complete/Inspected
79 Southern Estates | Invoiced
79 Southern Estates | Job Complete/Inspected
7 Laurel Ridge | Invoiced
7 Laurel Ridge | Job Complete/Inspected
140 Annandale | 100% Job Complete
140 Annandale | Invoiced
140 Annandale | Job Complete/Inspected
105 Hickory Grove | Paint Complete
105 Hickory Grove | Invoiced
105 Hickory Grove | Job Complete/Inspected
122 Hickory Grove | Paint Complete
122 Hickory Grove | Invoiced
122 Hickory Grove | Job Complete/Inspected
148 Wilkins | Invoiced
148 Wilkins | Job Complete/Inspected
116 Chestnut | Invoiced
116 Chestnut | Job Complete/Inspected
2 Windfield | Invoiced
2 Windfield | Job Complete/Inspected
4 Windfield | Invoiced
4 Windfield | Job Complete/Inspected
3 Windfield | Invoiced
3 Windfield | Job Complete/Inspected
1 Windfield | Invoiced
1 Windfield | Job Complete/Inspected
84 Providence Oaks 40 | Invoiced
84 Providence Oaks 40 | Job Complete/Inspected
79 Providence Oaks 40' | Invoiced
79 Providence Oaks 40' | Job Complete/Inspected
78 Providence Oaks 40' | Invoiced
78 Providence Oaks 40' | Job Complete/Inspected
Wilder Farms | Invoiced
Wilder Farms | Job Complete/Inspected
104 Stonewood | Paint Complete
103 Stonewood | Paint Complete
102 Stonewood | Paint Complete
74 Stonewood | Invoiced
74 Stonewood | Job Complete/Inspected
Dunn House | Invoiced
Dunn House | Job Complete/Inspected
12 Eller Farms | Invoiced
12 Eller Farms | Job Complete/Inspected
19 Caitlin Crossing | Invoiced
19 Caitlin Crossing | Job Complete/Inspected
18 Caitlin Crossing | Invoiced
18 Caitlin Crossing | Job Complete/Inspected
6 Caitlin Crossing | Invoiced
6 Caitlin Crossing | Job Complete/Inspected
5 Caitlin Crossing | Invoiced
5 Caitlin Crossing | Job Complete/Inspected
16 Maison Ridge | Invoiced
16 Maison Ridge | Job Complete/Inspected
47 Stanat Place TH | Invoiced
47 Stanat Place TH | Job Complete/Inspected
46 Stanat Place TH | Invoiced
46 Stanat Place TH | Job Complete/Inspected
45 Stanat Place TH | Invoiced
45 Stanat Place TH | Job Complete/Inspected
44 Stanat Place TH | Invoiced
44 Stanat Place TH | Job Complete/Inspected
43 Stanat Place TH | Invoiced
43 Stanat Place TH | Job Complete/Inspected
40 Raven Ridge Place TH | Invoiced
40 Raven Ridge Place TH | Job Complete/Inspected
39 Raven Ridge Place TH | Invoiced
39 Raven Ridge Place TH | Job Complete/Inspected
38 Raven Ridge Place TH | Invoiced
38 Raven Ridge Place TH | Job Complete/Inspected
37 Raven Ridge Place TH | Invoiced
37 Raven Ridge Place TH | Job Complete/Inspected
11 Olivet | Invoiced
11 Olivet | Job Complete/Inspected
133 River Glen | Invoiced
133 River Glen | Job Complete/Inspected
132 River Glen | Invoiced
132 River Glen | Job Complete/Inspected
131 River Glen | Invoiced
131 River Glen | Job Complete/Inspected
130 River Glen | Invoiced
130 River Glen | Job Complete/Inspected
27 Williams Grove | Invoiced
27 Williams Grove | Job Complete/Inspected
187 Trails at Young Farm | Paint Complete
187 Trails at Young Farm | Invoiced
187 Trails at Young Farm | Job Complete/Inspected
113 Trails at Young Farm | Paint Complete
113 Trails at Young Farm | Invoiced
113 Trails at Young Farm | Job Complete/Inspected
103 Duncans Creek | Invoiced
103 Duncans Creek | Job Complete/Inspected
52 Duncans Creek | Invoiced
52 Duncans Creek | Job Complete/Inspected
45 Duncans Creek | Invoiced
45 Duncans Creek | Job Complete/Inspected
23 Duncans Creek | Invoiced
23 Duncans Creek | Job Complete/Inspected
38 Duncans Creek | Invoiced
38 Duncans Creek | Job Complete/Inspected
36 Duncans Creek | Invoiced
36 Duncans Creek | Job Complete/Inspected
30 Duncans Creek | Invoiced
30 Duncans Creek | Job Complete/Inspected
60 Twinleaf Townes | Paint Complete
57 Summer Place | Invoiced
57 Summer Place | Job Complete/Inspected
58 Summer Place | Invoiced
58 Summer Place | Job Complete/Inspected
59 Summer Place | Invoiced
59 Summer Place | Job Complete/Inspected
60 Summer Place | Invoiced
60 Summer Place | Job Complete/Inspected
69 Summer Place | Invoiced
69 Summer Place | Job Complete/Inspected
110 Trails at Young Farm | Invoiced
110 Trails at Young Farm | Job Complete/Inspected
145 Trails at Young Farm | Invoiced
145 Trails at Young Farm | Job Complete/Inspected
32 Duncans Creek | Invoiced
32 Duncans Creek | Job Complete/Inspected
163 Edge of Auburn - Summit | 100% Job Complete
9 Caitlin Crossing | Invoiced
9 Caitlin Crossing | Job Complete/Inspected
30 Williams Grove | Invoiced
30 Williams Grove | Job Complete/Inspected
24 Williams Grove | Invoiced
24 Williams Grove | Job Complete/Inspected
21 Williams Grove | Invoiced
21 Williams Grove | Job Complete/Inspected
4 Caitlin Crossing | Invoiced
4 Caitlin Crossing | Job Complete/Inspected
8 Caitlin Crossing | Invoiced
8 Caitlin Crossing | Job Complete/Inspected
3 Caitlin Crossing | Invoiced
3 Caitlin Crossing | Job Complete/Inspected
2 Caitlin Crossing - Model | Invoiced
2 Caitlin Crossing - Model | Job Complete/Inspected
87 River Glen | Invoiced
87 River Glen | Job Complete/Inspected
112 Trails at Young Farm | Paint Complete
112 Trails at Young Farm | Invoiced
112 Trails at Young Farm | Job Complete/Inspected
14 Holding Village Mews TH | Invoiced
14 Holding Village Mews TH | Job Complete/Inspected
41 Millstone | Invoiced
41 Millstone | Job Complete/Inspected
40 Millstone | Invoiced
86 River Glen | Invoiced
86 River Glen | Job Complete/Inspected
28 Harvest Creek | Invoiced
28 Harvest Creek | Job Complete/Inspected
7 Harvest Creek | Invoiced
7 Harvest Creek | Job Complete/Inspected
754 Edge of Auburn - Classic | Invoiced
754 Edge of Auburn - Classic | Job Complete/Inspected
75 Stonewood | Invoiced
75 Stonewood | Job Complete/Inspected
106 Falls Village | Invoiced
106 Falls Village | Job Complete/Inspected
196 Falls Village | Invoiced
196 Falls Village | Job Complete/Inspected
109 Falls Village | Invoiced
109 Falls Village | Job Complete/Inspected
85 River Glen | Invoiced
85 River Glen | Job Complete/Inspected
44 Williams Grove | Invoiced
44 Williams Grove | Job Complete/Inspected
26 Williams Grove | Invoiced
26 Williams Grove | Job Complete/Inspected
Pierre Morin Residence | Invoiced
Pierre Morin Residence | Job Complete/Inspected
17 Carolina Overlook Twin Villas | Invoiced
17 Carolina Overlook Twin Villas | Job Complete/Inspected
16 Carolina Overlook Twin Villas | Invoiced
16 Carolina Overlook Twin Villas | Job Complete/Inspected
171 Trails at Young Farm | Paint Complete
1 Tart Town Rd | Invoiced
1 Tart Town Rd | Job Complete/Inspected
93 Regency @ Olde Towne | Invoiced
93 Regency @ Olde Towne | Job Complete/Inspected
153 Trails at Young Farm | Paint Complete
153 Trails at Young Farm | Invoiced
153 Trails at Young Farm | Job Complete/Inspected
99 Providence Oaks 30' | Invoiced
99 Providence Oaks 30' | Job Complete/Inspected
98 Providence Oaks 30' | Invoiced
98 Providence Oaks 30' | Job Complete/Inspected
97 Providence Oaks 30' | Invoiced
97 Providence Oaks 30' | Job Complete/Inspected
373 Vineyards @ Chatham Park | Invoiced
373 Vineyards @ Chatham Park | Job Complete/Inspected
72 Summer Place | Invoiced
72 Summer Place | Job Complete/Inspected
68 Summer Place | Invoiced
68 Summer Place | Job Complete/Inspected
71 Summer Place | Invoiced
71 Summer Place | Job Complete/Inspected
70 Summer Place | Invoiced
70 Summer Place | Job Complete/Inspected
61 Summer Place | Invoiced
61 Summer Place | Job Complete/Inspected
42 Stanat Place TH | Invoiced
42 Stanat Place TH | Job Complete/Inspected
41 Stanat Place TH | Invoiced
41 Stanat Place TH | Job Complete/Inspected
40 Stanat Place TH | Invoiced
40 Stanat Place TH | Job Complete/Inspected
39 Stanat Place TH | Invoiced
39 Stanat Place TH | Job Complete/Inspected
38 Stanat Place TH | Invoiced
38 Stanat Place TH | Job Complete/Inspected
53 Summer Place | Invoiced
53 Summer Place | Job Complete/Inspected
67 Summer Place | Invoiced
67 Summer Place | Job Complete/Inspected
66 Summer Place | Invoiced
66 Summer Place | Job Complete/Inspected
171 Trails at Young Farm | Invoiced
171 Trails at Young Farm | Job Complete/Inspected
152 Trails at Young Farm | Paint Complete
152 Trails at Young Farm | Invoiced
152 Trails at Young Farm | Job Complete/Inspected
3302 Hall Place | Invoiced
3302 Hall Place | Job Complete/Inspected
110 Hickory Grove | Paint Complete
4531 Chatham Park North Village | Invoiced
4531 Chatham Park North Village | Job Complete/Inspected
43 Turnberry Rd | Invoiced
43 Turnberry Rd | Job Complete/Inspected
84 River Glen | Invoiced
84 River Glen | Job Complete/Inspected
48 Page Townes TH | Invoiced
48 Page Townes TH | Job Complete/Inspected
47 Page Townes TH | Invoiced
47 Page Townes TH | Job Complete/Inspected
46 Page Townes TH | Invoiced
46 Page Townes TH | Job Complete/Inspected
151Trails at Young Farm | Invoiced
151Trails at Young Farm | Job Complete/Inspected
5 Gardner Farms | 100% Job Complete
5 Gardner Farms | Invoiced
5 Gardner Farms | Job Complete/Inspected
39 Watkins Grove | Invoiced
39 Watkins Grove | Job Complete/Inspected
90 Stonewood | Invoiced
90 Stonewood | Job Complete/Inspected
89 Stonewood | Invoiced
89 Stonewood | Job Complete/Inspected
88 Stonewood | Invoiced
88 Stonewood | Job Complete/Inspected
93 Stonewood | Invoiced
93 Stonewood | Job Complete/Inspected
94 Stonewood | Invoiced
94 Stonewood | Job Complete/Inspected
76 Stonewood | Invoiced
76 Stonewood | Job Complete/Inspected
92 Stonewood | Invoiced
92 Stonewood | Job Complete/Inspected
73 Stonewood | Invoiced
73 Stonewood | Job Complete/Inspected
125 River Glen | Invoiced
125 River Glen | Job Complete/Inspected
81 River Glen | Invoiced
81 River Glen | Job Complete/Inspected
83 River Glen | Invoiced
83 River Glen | Job Complete/Inspected
72 Stonewood | Invoiced
72 Stonewood | Job Complete/Inspected
110 Hickory Grove | Invoiced
110 Hickory Grove | Job Complete/Inspected
121 Hickory Grove | Paint Complete
121 Hickory Grove | Invoiced
121 Hickory Grove | Job Complete/Inspected
6 Rollins Acres | Invoiced
6 Rollins Acres | Job Complete/Inspected
5 Rollins Acre | Invoiced
5 Rollins Acre | Job Complete/Inspected
10 Ballard Rd | Invoiced
10 Ballard Rd | Job Complete/Inspected
9 Ballard Rd | Invoiced
9 Ballard Rd | Job Complete/Inspected
171 Keith Hills | Invoiced
171 Keith Hills | Job Complete/Inspected
152 Preserve @ Jones Dairy | Paint Complete
152 Preserve @ Jones Dairy | Invoiced
152 Preserve @ Jones Dairy | Job Complete/Inspected
64 Southern Estates | Invoiced
64 Southern Estates | Job Complete/Inspected
146 Trails @ Young Farm | Invoiced
146 Trails @ Young Farm | Job Complete/Inspected
6 Southern Estates | Invoiced
6 Southern Estates | Job Complete/Inspected
82 River Glen | Invoiced
82 River Glen | Job Complete/Inspected
380 Vineyards @ Chatham Park | Invoiced
380 Vineyards @ Chatham Park | Job Complete/Inspected
100 Providence Oaks 30' | Invoiced
100 Providence Oaks 30' | Job Complete/Inspected
21 Providence Oaks 30' | Invoiced
21 Providence Oaks 30' | Job Complete/Inspected
85 Providence Oaks 40' | Invoiced
85 Providence Oaks 40' | Job Complete/Inspected
50 Providence Oaks 40' | Invoiced
50 Providence Oaks 40' | Job Complete/Inspected
2 Providence Oaks 40' | Invoiced
2 Providence Oaks 40' | Job Complete/Inspected
70 Stonewood | Paint Complete
69 Stonewood | Paint Complete
68 Stonewood | Paint Complete
172 Trails at Young Farm | Invoiced
172 Trails at Young Farm | Job Complete/Inspected
275 Oak Manor | Invoiced
275 Oak Manor | Job Complete/Inspected
129 River Glen | Invoiced
129 River Glen | Job Complete/Inspected
128 River Glen | Invoiced
128 River Glen | Job Complete/Inspected
17 Twinleaf Townes | Paint Complete
16 Twinleaf Townes | Paint Complete
15 Twinleaf Townes | Paint Complete
14 Twinleaf Townes | Paint Complete
13 Twinleaf Townes | Paint Complete
75 Harvest Meadows | Invoiced
75 Harvest Meadows | Job Complete/Inspected
5 Regency @ Olde Towne | Invoiced
5 Regency @ Olde Towne | Job Complete/Inspected
90 Falls of The Cape | Invoiced
90 Falls of The Cape | Job Complete/Inspected
89 Falls of The Cape | Invoiced
89 Falls of The Cape | Job Complete/Inspected
88 Falls of The Cape | 100% Job Complete
88 Falls of The Cape | Invoiced
88 Falls of The Cape | Job Complete/Inspected
87 Falls of The Cape | Invoiced
87 Falls of The Cape | Job Complete/Inspected
97 Falls of The Cape | Invoiced
97 Falls of The Cape | Job Complete/Inspected
96 Falls of The Cape | Invoiced
96 Falls of The Cape | Job Complete/Inspected
93 Falls of The Cape | Invoiced
93 Falls of The Cape | Job Complete/Inspected
92 Falls of The Cape | Invoiced
92 Falls of The Cape | Job Complete/Inspected
8 Ballard Road | Invoiced
8 Ballard Road | Job Complete/Inspected
2 Eller Farms 2 | Invoiced
2 Eller Farms 2 | Job Complete/Inspected
37 Stanat Place TH | Paint Complete
36 Stanat Place TH | Paint Complete
37 Stanat Place TH | Invoiced
37 Stanat Place TH | Job Complete/Inspected
20 Providence Oaks 40' | Paint Complete
36 Stanat Place TH | Invoiced
36 Stanat Place TH | Job Complete/Inspected
35 Stanat Place TH | Paint Complete
35 Stanat Place TH | Invoiced
35 Stanat Place TH | Job Complete/Inspected
34 Stanat Place TH | Paint Complete
34 Stanat Place TH | Invoiced
34 Stanat Place TH | Job Complete/Inspected
33 Stanat Place TH | Paint Complete
33 Stanat Place TH | Invoiced
33 Stanat Place TH | Job Complete/Inspected
32 Stanat Place TH | Paint Complete
32 Stanat Place TH | Invoiced
32 Stanat Place TH | Job Complete/Inspected
89 Regency @ Olde Towne | Invoiced
89 Regency @ Olde Towne | Job Complete/Inspected
49 Millstone | Invoiced
60 Millstone | Invoiced
55 Millstone | Invoiced
55 Millstone | Job Complete/Inspected
7 Ballard Road | Invoiced
7 Ballard Road | Job Complete/Inspected
346 Vineyards @ Chatham Park | Paint Complete
346 Vineyards @ Chatham Park | Invoiced
346 Vineyards @ Chatham Park | Job Complete/Inspected
49 Providence Oaks 40' | Invoiced
49 Providence Oaks 40' | Job Complete/Inspected
6 Ballard Road | Invoiced
6 Ballard Road | Job Complete/Inspected
4551 Chatham Park North Village | Invoiced
4551 Chatham Park North Village | Job Complete/Inspected
109 Trails @ Young Farm | Paint Complete
109 Trails @ Young Farm | Invoiced
109 Trails @ Young Farm | Job Complete/Inspected
18 Williams Grove | Invoiced
18 Williams Grove | Job Complete/Inspected
16 Williams Grove | Invoiced
16 Williams Grove | Job Complete/Inspected
46 Williams Grove | Invoiced
46 Williams Grove | Job Complete/Inspected
31 Williams Grove | Invoiced
31 Williams Grove | Job Complete/Inspected
4532 Chatham Park North Village | Invoiced
4532 Chatham Park North Village | Job Complete/Inspected
12 Twinleaf Townes | Paint Complete
11 Twinleaf Townes | Paint Complete
9 Twinleaf Townes | Paint Complete
8 Twinleaf Townes | Paint Complete
7 Twinleaf Townes | Paint Complete
76 Twinleaf Townes TH | Paint Complete
75 Twinleaf Townes TH | Paint Complete
74 Twinleaf Townes TH | Paint Complete
73 Twinleaf Townes TH | Paint Complete
9 North Lakes at South Lakes | Paint Complete
8 North Lakes @ South Lakes | Paint Complete
7 North Lakes @ South Lakes | Paint Complete
65 North Lakes @ South Lakes | Paint Complete
61 North Lakes @ South Lakes | Paint Complete
60 North Lakes at South Lakes | Paint Complete
59 North Lakes @ South Lakes | Paint Complete
5 North Lakes @ South Lakes | Paint Complete
376 Paddington Station 60' | Paint Complete
3 North Lakes @ South Lakes | Paint Complete
2 North Lakes @ South Lakes | Paint Complete
150 Trails @ Young Farm | Paint Complete
147 Trails @ Young Farm | Paint Complete
13 North Lakes at South Lakes | Paint Complete
12 North Lakes @ South Lakes | Paint Complete
11 North Lakes at South Lakes | Paint Complete
383 Vineyards @ Chatham Park | Paint Complete
304 Vineyards @ Chatham Park | Paint Complete
383 Vineyards @ Chatham Park | Invoiced
383 Vineyards @ Chatham Park | Job Complete/Inspected
23 Providence Oaks 40' | Paint Complete
23 Providence Oaks 40' | Invoiced
23 Providence Oaks 40' | Job Complete/Inspected
19 Providence Oaks 30' | Paint Complete
20 Providence Oaks 40' | Invoiced
20 Providence Oaks 40' | Job Complete/Inspected
19 Providence Oaks 30' | Invoiced
19 Providence Oaks 30' | Job Complete/Inspected
18 Providence Oaks 30' | Paint Complete
18 Providence Oaks 30' | Invoiced
18 Providence Oaks 30' | Job Complete/Inspected
71 Stonewood | Invoiced
71 Stonewood | Job Complete/Inspected
45 Page Townes TH | Invoiced
45 Page Townes TH | Job Complete/Inspected
44 Page Townes TH | Invoiced
44 Page Townes TH | Job Complete/Inspected
43 Page Townes TH | Invoiced
43 Page Townes TH | Job Complete/Inspected
11 Raven Ridge Place TH | Paint Complete
36 Raven Ridge Place TH | Paint Complete
36 Raven Ridge Place TH | Invoiced
36 Raven Ridge Place TH | Job Complete/Inspected
11 Mulhollem | Invoiced
11 Mulhollem | Job Complete/Inspected
35 Raven Ridge Place TH | Paint Complete
35 Raven Ridge Place TH | Invoiced
35 Raven Ridge Place TH | Job Complete/Inspected
34 Raven Ridge Place TH | Paint Complete
34 Raven Ridge Place TH | Invoiced
34 Raven Ridge Place TH | Job Complete/Inspected
33 Raven Ridge Place TH | Paint Complete
33 Raven Ridge Place TH | Invoiced
33 Raven Ridge Place TH | Job Complete/Inspected
32 Raven Ridge Place TH | Paint Complete
32 Raven Ridge Place TH | Invoiced
32 Raven Ridge Place TH | Job Complete/Inspected
31 Raven Ridge Place TH | Paint Complete
31 Raven Ridge Place TH | Invoiced
31 Raven Ridge Place TH | Job Complete/Inspected
30 Raven Ridge Place TH | Paint Complete
30 Raven Ridge Place TH | Invoiced
30 Raven Ridge Place TH | Job Complete/Inspected
29 Raven Ridge Place TH | Paint Complete
29 Raven Ridge Place TH | Invoiced
29 Raven Ridge Place TH | Job Complete/Inspected
28 Raven Ridge Place TH | Paint Complete
28 Raven Ridge Place TH | Invoiced
28 Raven Ridge Place TH | Job Complete/Inspected
11 Raven Ridge Place TH | Invoiced
11 Raven Ridge Place TH | Job Complete/Inspected
10 Raven Ridge Place TH | Paint Complete
74 Archer's Park | Invoiced
74 Archer's Park | Job Complete/Inspected
73 Archer's Park | Invoiced
73 Archer's Park | Job Complete/Inspected
10 Raven Ridge Place TH | Invoiced
10 Raven Ridge Place TH | Job Complete/Inspected
9 Raven Ridge Place TH | Paint Complete
9 Raven Ridge Place TH | Invoiced
9 Raven Ridge Place TH | Job Complete/Inspected
8 Raven Ridge Place TH | Paint Complete
7 Raven Ridge Place TH | Paint Complete
6 Raven Ridge Place TH | Paint Complete
8 Raven Ridge Place TH | Invoiced
8 Raven Ridge Place TH | Job Complete/Inspected
7 Raven Ridge Place TH | Invoiced
7 Raven Ridge Place TH | Job Complete/Inspected
6 Raven Ridge Place TH | Invoiced
6 Raven Ridge Place TH | Job Complete/Inspected
88 Providence Oaks 40' | Paint Complete
87 Providence Oaks 40' | Paint Complete
16 Providence Oaks 30' | Paint Complete
75 Olive Grove SF | Paint Complete
150 Trails @ Young Farm | Invoiced
150 Trails @ Young Farm | Job Complete/Inspected
86 Providence Oaks 40' | Paint Complete
22 Providence Oaks 40' | Paint Complete
17 Providence Oaks 30' | Paint Complete
15 Providence Oaks 30' | Paint Complete
14 Providence Oaks 30' | Paint Complete
13 Providence Oaks 30' | Paint Complete
348 Vineyards @ Chatham Park | Invoiced
348 Vineyards @ Chatham Park | Job Complete/Inspected
304 Vineyards @ Chatham Park | Invoiced
304 Vineyards @ Chatham Park | Job Complete/Inspected
88 Providence Oaks 40' | Invoiced
88 Providence Oaks 40' | Job Complete/Inspected
87 Providence Oaks 40' | Invoiced
87 Providence Oaks 40' | Job Complete/Inspected
86 Providence Oaks 40' | Invoiced
86 Providence Oaks 40' | Job Complete/Inspected
22 Providence Oaks 40' | Invoiced
22 Providence Oaks 40' | Job Complete/Inspected
17 Providence Oaks 30' | Invoiced
17 Providence Oaks 30' | Job Complete/Inspected
16 Providence Oaks 30' | Invoiced
16 Providence Oaks 30' | Job Complete/Inspected
15 Providence Oaks 30' | Invoiced
15 Providence Oaks 30' | Job Complete/Inspected
14 Providence Oaks 30' | Invoiced
14 Providence Oaks 30' | Job Complete/Inspected
13 Providence Oaks 30' | Invoiced
13 Providence Oaks 30' | Job Complete/Inspected
4533 Chatham Park North Village | Invoiced
4533 Chatham Park North Village | Job Complete/Inspected
80 River Glen | Invoiced
80 River Glen | Job Complete/Inspected
50 Millstone | Invoiced
50 Millstone | Job Complete/Inspected
79 River Glen | Invoiced
79 River Glen | Job Complete/Inspected
84 Twinleaf Townes TH | Invoiced
84 Twinleaf Townes TH | Job Complete/Inspected
83 Twinleaf Townes TH | Invoiced
83 Twinleaf Townes TH | Job Complete/Inspected
82 Twinleaf Townes TH | Invoiced
82 Twinleaf Townes TH | Job Complete/Inspected
81 Twinleaf Townes TH | Invoiced
81 Twinleaf Townes TH | Job Complete/Inspected
80 Twinleaf Townes TH | Invoiced
80 Twinleaf Townes TH | Job Complete/Inspected
79 Twinleaf Townes TH | Invoiced
79 Twinleaf Townes TH | Job Complete/Inspected
70 Stonewood | Invoiced
70 Stonewood | Job Complete/Inspected
78 River Glen | Invoiced
78 River Glen | Job Complete/Inspected
31 Stanat Place TH | Paint Complete
31 Stanat Place TH | Invoiced
31 Stanat Place TH | Job Complete/Inspected
30 Stanat Place TH | Paint Complete
30 Stanat Place TH | Invoiced
30 Stanat Place TH | Job Complete/Inspected
29 Stanat Place TH | Paint Complete
29 Stanat Place TH | Invoiced
29 Stanat Place TH | Job Complete/Inspected
28 Stanat Place TH | Paint Complete
28 Stanat Place TH | Invoiced
28 Stanat Place TH | Job Complete/Inspected
27 Stanat Place TH | Paint Complete
27 Stanat Place TH | Invoiced
27 Stanat Place TH | Job Complete/Inspected
26 Stanat Place TH | Paint Complete
26 Stanat Place TH | Invoiced
26 Stanat Place TH | Job Complete/Inspected
76 River Glen | Invoiced
76 River Glen | Job Complete/Inspected
75 River Glen | Invoiced
75 River Glen | Job Complete/Inspected
77 River Glen | Invoiced
77 River Glen | Job Complete/Inspected
49 Southern Estates | Invoiced
49 Southern Estates | Job Complete/Inspected
48 Southern Estates | Invoiced
48 Southern Estates | Job Complete/Inspected
1 Southern Estates | Invoiced
1 Southern Estates | Job Complete/Inspected
28 Hickory Grove | Invoiced
28 Hickory Grove | Job Complete/Inspected
60 North Lakes at South Lakes | Invoiced
60 North Lakes at South Lakes | Job Complete/Inspected
11 North Lakes at South Lakes | Invoiced
11 North Lakes at South Lakes | Job Complete/Inspected
9 North Lakes at South Lakes | Invoiced
9 North Lakes at South Lakes | Job Complete/Inspected
13 North Lakes at South Lakes | Invoiced
13 North Lakes at South Lakes | Job Complete/Inspected
4549 Chatham Park North Village | Invoiced
4549 Chatham Park North Village | Job Complete/Inspected
4550 Chatham Park North Village | Invoiced
4550 Chatham Park North Village | Job Complete/Inspected
4534 Chatham Park North Village | Invoiced
4534 Chatham Park North Village | Job Complete/Inspected
2 Southern Estates | Invoiced
2 Southern Estates | Job Complete/Inspected
11 Providence Oaks 30' | Invoiced
11 Providence Oaks 30' | Job Complete/Inspected
44 Kipling Creek | Invoiced
44 Kipling Creek | Job Complete/Inspected
104 Stonewood | Invoiced
104 Stonewood | Job Complete/Inspected
103 Stonewood | Invoiced
103 Stonewood | Job Complete/Inspected
102 Stonewood | Invoiced
102 Stonewood | Job Complete/Inspected
69 Stonewood | Invoiced
69 Stonewood | Job Complete/Inspected
68 Stonewood | Invoiced
68 Stonewood | Job Complete/Inspected
43 Kipling Creek | Invoiced
43 Kipling Creek | Job Complete/Inspected
41 Kipling Creek | Invoiced
41 Kipling Creek | Job Complete/Inspected
4548 Chatham Park North Village | Invoiced
4548 Chatham Park North Village | Job Complete/Inspected
40 Kipling Creek | Invoiced
40 Kipling Creek | Job Complete/Inspected
24 Kipling Creek | Invoiced
24 Kipling Creek | Job Complete/Inspected
23 Kipling Creek | Invoiced
23 Kipling Creek | Job Complete/Inspected
22 Kipling Creek | Invoiced
22 Kipling Creek | Job Complete/Inspected
8 Southern Estates | Invoiced
8 Southern Estates | Job Complete/Inspected
Smith's Farmhouse Lodge | Invoiced
Smith's Farmhouse Lodge | Job Complete/Inspected
3 Heritage @ Neills Creek | Invoiced
3 Heritage @ Neills Creek | Job Complete/Inspected
12 Providence Oaks 30' | Paint Complete
12 Providence Oaks 30' | Invoiced
12 Providence Oaks 30' | Job Complete/Inspected
10 Providence Oaks 30' | Paint Complete
10 Providence Oaks 30' | Invoiced
10 Providence Oaks 30' | Job Complete/Inspected
9 Providence Oaks 30' | Paint Complete
6 Providence Oaks 30' | Paint Complete
8 Providence Oaks 30' | Paint Complete
9 Providence Oaks 30' | Invoiced
9 Providence Oaks 30' | Job Complete/Inspected
8 Providence Oaks 30' | Invoiced
8 Providence Oaks 30' | Job Complete/Inspected
90 Providence Oaks 40' | Paint Complete
90 Providence Oaks 40' | Invoiced
90 Providence Oaks 40' | Job Complete/Inspected
89 Providence Oaks 40' | Paint Complete
89 Providence Oaks 40' | Invoiced
89 Providence Oaks 40' | Job Complete/Inspected
93 Providence Oaks 40' | Paint Complete
375 Vineyards @ Chatham Park | Paint Complete
375 Vineyards @ Chatham Park | Invoiced
375 Vineyards @ Chatham Park | Job Complete/Inspected
46 Little River | Invoiced
46 Little River | Job Complete/Inspected
6 North Lakes at South Lakes | Paint Complete
347 Vineyards @ Chatham Park | Paint Complete
345 Vineyards @ Chatham Park | Paint Complete
340 Vineyards @ Chatham Park | Paint Complete
13 Page Townes TH | Paint Complete
12 Page Townes TH | Paint Complete
11 Page Townes TH | Paint Complete
13 Page Townes TH | Invoiced
13 Page Townes TH | Job Complete/Inspected
12 Page Townes TH | Invoiced
12 Page Townes TH | Job Complete/Inspected
11 Page Townes TH | Invoiced
11 Page Townes TH | Job Complete/Inspected
7 Providence Oaks 30' | Paint Complete
78 Twinleaf Townes TH | Invoiced
78 Twinleaf Townes TH | Job Complete/Inspected
77 Twinleaf Townes TH | Invoiced
77 Twinleaf Townes TH | Job Complete/Inspected
76 Twinleaf Townes TH | Invoiced
76 Twinleaf Townes TH | Job Complete/Inspected
75 Twinleaf Townes TH | Invoiced
75 Twinleaf Townes TH | Job Complete/Inspected
74 Twinleaf Townes TH | Invoiced
74 Twinleaf Townes TH | Job Complete/Inspected
73 Twinleaf Townes TH | Invoiced
73 Twinleaf Townes TH | Job Complete/Inspected
25 Stanat Place TH | Paint Complete
25 Stanat Place TH | Invoiced
25 Stanat Place TH | Job Complete/Inspected
24 Stanat Place TH | Paint Complete
24 Stanat Place TH | Invoiced
24 Stanat Place TH | Job Complete/Inspected
23 Stanat Place TH | Paint Complete
23 Stanat Place TH | Invoiced
23 Stanat Place TH | Job Complete/Inspected
22 Stanat Place TH | Paint Complete
22 Stanat Place TH | Invoiced
22 Stanat Place TH | Job Complete/Inspected
21 Stanat Place TH | Paint Complete
21 Stanat Place TH | Invoiced
21 Stanat Place TH | Job Complete/Inspected
9 Southern Estates | Invoiced
9 Southern Estates | Job Complete/Inspected
91 Providence Oaks 40' | Invoiced
91 Providence Oaks 40' | Job Complete/Inspected
7 Providence Oaks 30' | Invoiced
7 Providence Oaks 30' | Job Complete/Inspected
20 Stanat Place TH | Paint Complete
4 Southern Estates | Invoiced
4 Southern Estates | Job Complete/Inspected
20 Stanat Place TH | Invoiced
20 Stanat Place TH | Job Complete/Inspected
42 Kipling Creek | Invoiced
42 Kipling Creek | Job Complete/Inspected
35 Kipling Creek | Invoiced
35 Kipling Creek | Job Complete/Inspected
3 Southern Estates | Invoiced
3 Southern Estates | Job Complete/Inspected
2 Regency @ Olde Towne | Invoiced
2 Regency @ Olde Towne | Job Complete/Inspected
1 Regency @ Olde Towne | Invoiced
1 Regency @ Olde Towne | Job Complete/Inspected
36 Regency @ Olde Towne | Invoiced
36 Regency @ Olde Towne | Job Complete/Inspected
8 Millstone | Invoiced
8 Millstone | Job Complete/Inspected
3 Regency @ Olde Towne | Invoiced
3 Regency @ Olde Towne | Job Complete/Inspected
10 Millstone | Invoiced
10 Millstone | Job Complete/Inspected
147 Trails @ Young Farm | Invoiced
147 Trails @ Young Farm | Job Complete/Inspected
183 Trails @ Young Farm | Invoiced
183 Trails @ Young Farm | Job Complete/Inspected
59 North Lakes @ South Lakes | Invoiced
59 North Lakes @ South Lakes | Job Complete/Inspected
5 North Lakes @ South Lakes | Invoiced
5 North Lakes @ South Lakes | Job Complete/Inspected
12 North Lakes @ South Lakes | Invoiced
12 North Lakes @ South Lakes | Job Complete/Inspected
8 North Lakes @ South Lakes | Invoiced
8 North Lakes @ South Lakes | Job Complete/Inspected
376 Paddington Station 60' | 100% Job Complete
10 Twinleaf Townes | Paint Complete
92 Providence Oaks 40' | Paint Complete
93 Providence Oaks 40' | Invoiced
93 Providence Oaks 40' | Job Complete/Inspected
92 Providence Oaks 40' | Invoiced
92 Providence Oaks 40' | Job Complete/Inspected
59 Twinleaf Townes | Invoiced
59 Twinleaf Townes | Job Complete/Inspected
62 Twinleaf Townes | Invoiced
62 Twinleaf Townes | Job Complete/Inspected
60 Twinleaf Townes | Invoiced
60 Twinleaf Townes | Job Complete/Inspected
63 Twinleaf Townes | Invoiced
63 Twinleaf Townes | Job Complete/Inspected
61 Twinleaf Townes | Invoiced
61 Twinleaf Townes | Job Complete/Inspected
7 North Lakes @ South Lakes | Invoiced
7 North Lakes @ South Lakes | Job Complete/Inspected
2 North Lakes @ South Lakes | Invoiced
2 North Lakes @ South Lakes | Job Complete/Inspected
3 North Lakes @ South Lakes | Invoiced
3 North Lakes @ South Lakes | Job Complete/Inspected
19 Stanat Place TH | Paint Complete
19 Stanat Place TH | Invoiced
19 Stanat Place TH | Job Complete/Inspected
18 Stanat Place TH | Paint Complete
18 Stanat Place TH | Invoiced
18 Stanat Place TH | Job Complete/Inspected
17 Stanat Place TH | Paint Complete
17 Stanat Place TH | Invoiced
17 Stanat Place TH | Job Complete/Inspected
16 Stanat Place TH | Paint Complete
16 Stanat Place TH | Invoiced
16 Stanat Place TH | Job Complete/Inspected
15 Stanat Place TH | Paint Complete
15 Stanat Place TH | Invoiced
15 Stanat Place TH | Job Complete/Inspected
94 Providence Oaks 40' | Paint Complete
347 Vineyards @ Chatham Park | Invoiced
347 Vineyards @ Chatham Park | Job Complete/Inspected
95 Providence Oaks 40' | Invoiced
95 Providence Oaks 40' | Job Complete/Inspected
94 Providence Oaks 40' | Invoiced
94 Providence Oaks 40' | Job Complete/Inspected
6 Providence Oaks 30' | Invoiced
6 Providence Oaks 30' | Job Complete/Inspected
5 Providence Oaks 30' | Invoiced
5 Providence Oaks 30' | Job Complete/Inspected
58 Millstone | Invoiced
58 Millstone | Job Complete/Inspected
3 Millstone | Invoiced
3 Millstone | Job Complete/Inspected
11 Millstone | Invoiced
11 Millstone | Job Complete/Inspected
46 Millstone | Invoiced
46 Millstone | Job Complete/Inspected
9 Millstone | Invoiced
9 Millstone | Job Complete/Inspected
12 Millstone | Invoiced
12 Millstone | Job Complete/Inspected
56 Millstone | Invoiced
56 Millstone | Job Complete/Inspected
57 Millstone | Invoiced
57 Millstone | Job Complete/Inspected
112 Regency @ Olde Towne | Invoiced
112 Regency @ Olde Towne | Job Complete/Inspected
2 Millstone | Invoiced
2 Millstone | Job Complete/Inspected
54 Millstone | Invoiced
54 Millstone | Job Complete/Inspected
51 Millstone | Invoiced
51 Millstone | Job Complete/Inspected
48 Millstone | Invoiced
48 Millstone | Job Complete/Inspected
45 Millstone | Invoiced
45 Millstone | Job Complete/Inspected
13 Millstone | Invoiced
13 Millstone | Job Complete/Inspected
6 Millstone | Invoiced
6 Millstone | Job Complete/Inspected
5 Millstone | Invoiced
5 Millstone | Job Complete/Inspected
4 Millstone | Invoiced
4 Millstone | Job Complete/Inspected
65 North Lakes @ South Lakes | Invoiced
65 North Lakes @ South Lakes | Job Complete/Inspected
61 North Lakes @ South Lakes | Invoiced
61 North Lakes @ South Lakes | Job Complete/Inspected
14 Stanat Place TH | Paint Complete
14 Stanat Place TH | Invoiced
14 Stanat Place TH | Job Complete/Inspected
13 Stanat Place TH | Paint Complete
13 Stanat Place TH | Invoiced
13 Stanat Place TH | Job Complete/Inspected
12 Stanat Place TH | Paint Complete
12 Stanat Place TH | Invoiced
12 Stanat Place TH | Job Complete/Inspected
11 Stanat Place TH | Paint Complete
11 Stanat Place TH | Invoiced
11 Stanat Place TH | Job Complete/Inspected
10 Stanat Place TH | Paint Complete
10 Stanat Place TH | Invoiced
10 Stanat Place TH | Job Complete/Inspected
17 Page Townes TH | Paint Complete
16 Page Townes TH | Paint Complete
15 Page Townes TH | Paint Complete
14 Page Townes TH | Paint Complete
17 Page Townes TH | Invoiced
17 Page Townes TH | Job Complete/Inspected
16 Page Townes TH | Invoiced
16 Page Townes TH | Job Complete/Inspected
15 Page Townes TH | Invoiced
15 Page Townes TH | Job Complete/Inspected
14 Page Townes TH | Invoiced
14 Page Townes TH | Job Complete/Inspected
6 North Lakes at South Lakes | Invoiced
6 North Lakes at South Lakes | Job Complete/Inspected
349 Vineyards @ Chatham Park | Paint Complete
39 Carolina Landing | Invoiced
39 Carolina Landing | Job Complete/Inspected
17 Twinleaf Townes | Invoiced
17 Twinleaf Townes | Job Complete/Inspected
16 Twinleaf Townes | Invoiced
16 Twinleaf Townes | Job Complete/Inspected
15 Twinleaf Townes | Invoiced
15 Twinleaf Townes | Job Complete/Inspected
14 Twinleaf Townes | Invoiced
14 Twinleaf Townes | Job Complete/Inspected
13 Twinleaf Townes | Invoiced
13 Twinleaf Townes | Job Complete/Inspected
349 Vineyards @ Chatham Park | Invoiced
349 Vineyards @ Chatham Park | Job Complete/Inspected
345 Vineyards @ Chatham Park | Invoiced
345 Vineyards @ Chatham Park | Job Complete/Inspected
84 Regency @ Olde Towne | Invoiced
84 Regency @ Olde Towne | Job Complete/Inspected
7 Millstone | Invoiced
7 Millstone | Job Complete/Inspected
90 Regency @ Olde Towne | Invoiced
90 Regency @ Olde Towne | Job Complete/Inspected
157 Duncans Creek | Invoiced
157 Duncans Creek | Job Complete/Inspected
156 Duncans Creek | Invoiced
156 Duncans Creek | Job Complete/Inspected
155 Duncans Creek | Invoiced
155 Duncans Creek | Job Complete/Inspected
154 Duncans Creek | Invoiced
154 Duncans Creek | Job Complete/Inspected
153 Duncans Creek | Invoiced
153 Duncans Creek | Job Complete/Inspected
152 Duncans Creek | Invoiced
152 Duncans Creek | Job Complete/Inspected
160 Duncans Creek | Invoiced
160 Duncans Creek | Job Complete/Inspected
158 Duncans Creek | Invoiced
158 Duncans Creek | Job Complete/Inspected
151 Duncans Creek | Invoiced
151 Duncans Creek | Job Complete/Inspected
131 Duncans Creek | Invoiced
131 Duncans Creek | Job Complete/Inspected
124 Duncans Creek | Invoiced
124 Duncans Creek | Job Complete/Inspected
123 Duncans Creek | Invoiced
123 Duncans Creek | Job Complete/Inspected
16 Sippihaw Springs | Invoiced
16 Sippihaw Springs | Job Complete/Inspected
15 Sippihaw Springs | Invoiced
15 Sippihaw Springs | Job Complete/Inspected
8 Sippihaw Springs | Invoiced
8 Sippihaw Springs | Job Complete/Inspected
7 Sippihaw Springs | Invoiced
7 Sippihaw Springs | Job Complete/Inspected
4 Sippihaw Springs | Invoiced
4 Sippihaw Springs | Job Complete/Inspected
3 Sippihaw Springs | Invoiced
3 Sippihaw Springs | Job Complete/Inspected
73 Regency @ Olde Towne | Invoiced
73 Regency @ Olde Towne | Job Complete/Inspected
340 Vineyards @ Chatham Park | Invoiced
340 Vineyards @ Chatham Park | Job Complete/Inspected
12 Twinleaf Townes | Invoiced
12 Twinleaf Townes | Job Complete/Inspected
11 Twinleaf Townes | Invoiced
11 Twinleaf Townes | Job Complete/Inspected
10 Twinleaf Townes | Invoiced
10 Twinleaf Townes | Job Complete/Inspected
9 Twinleaf Townes | Invoiced
9 Twinleaf Townes | Job Complete/Inspected
8 Twinleaf Townes | Invoiced
8 Twinleaf Townes | Job Complete/Inspected
7 Twinleaf Townes | Invoiced
7 Twinleaf Townes | Job Complete/Inspected
6069 Jones Circle | Invoiced
6069 Jones Circle | Job Complete/Inspected
3258 Yorkshire Circle | Invoiced
3258 Yorkshire Circle | Job Complete/Inspected
3260 Yorkshire Circle | Invoiced
3260 Yorkshire Circle | Job Complete/Inspected
9 Stanat Place TH | Paint Complete
9 Stanat Place TH | Invoiced
9 Stanat Place TH | Job Complete/Inspected
8 Stanat Place TH | Paint Complete
8 Stanat Place TH | Invoiced
8 Stanat Place TH | Job Complete/Inspected
7 Stanat Place TH | Paint Complete
7 Stanat Place TH | Invoiced
7 Stanat Place TH | Job Complete/Inspected
6 Stanat Place TH | Paint Complete
6 Stanat Place TH | Invoiced
6 Stanat Place TH | Job Complete/Inspected
5 Stanat Place TH | Paint Complete
5 Stanat Place TH | Invoiced
5 Stanat Place TH | Job Complete/Inspected
4 Stanat Place TH | Paint Complete
4 Stanat Place TH | Invoiced
4 Stanat Place TH | Job Complete/Inspected
3 Stanat Place TH | Paint Complete
3 Stanat Place TH | Invoiced
3 Stanat Place TH | Job Complete/Inspected
1 Stanat Place TH | Paint Complete
2 Stanat Place TH | Paint Complete
2 Stanat Place TH | Invoiced
2 Stanat Place TH | Job Complete/Inspected
1 Stanat Place TH | Invoiced
1 Stanat Place TH | Job Complete/Inspected
16 Ellington Estates | Invoiced
16 Ellington Estates | Job Complete/Inspected
30 Magnolia Estates | Invoiced
30 Magnolia Estates | Job Complete/Inspected
28 Magnolia Estates | Invoiced
28 Magnolia Estates | Job Complete/Inspected
25 Magnolia Estates | Invoiced
25 Magnolia Estates | Job Complete/Inspected
24 Magnolia Estates | Invoiced
24 Magnolia Estates | Job Complete/Inspected
16 Magnolia Estates | Invoiced
16 Magnolia Estates | Job Complete/Inspected
39 Falls Of the Cape | Invoiced
39 Falls Of the Cape | Job Complete/Inspected
15 Ellington Estates | Invoiced
15 Ellington Estates | Job Complete/Inspected
84 Southern Estates | Invoiced
84 Southern Estates | Job Complete/Inspected
83 Southern Estates | Invoiced
83 Southern Estates | Job Complete/Inspected
63 Southern Estates | Invoiced
63 Southern Estates | Job Complete/Inspected
46 Southern Estates | Invoiced
46 Southern Estates | Job Complete/Inspected
91 Falls of The Cape | Invoiced
91 Falls of The Cape | Job Complete/Inspected
74 Olive Grove SF | Paint Complete
75 Olive Grove SF | Invoiced
75 Olive Grove SF | Job Complete/Inspected
74 Olive Grove SF | Invoiced
74 Olive Grove SF | Job Complete/Inspected
94 Falls of the Cape | Invoiced
94 Falls of the Cape | Job Complete/Inspected
73 Falls of the Cape | Invoiced
73 Falls of the Cape | Job Complete/Inspected
72 Falls of the Cape | Invoiced
72 Falls of the Cape | Job Complete/Inspected
54 Kipling Creek | Invoiced
54 Kipling Creek | Job Complete/Inspected
51 Kipling Creek | Invoiced
51 Kipling Creek | Job Complete/Inspected
74 Harvest Meadows | Invoiced
74 Harvest Meadows | Job Complete/Inspected
20 Coolwater | Invoiced
20 Coolwater | Job Complete/Inspected
26 Ellington Estates | Invoiced
26 Ellington Estates | Job Complete/Inspected
114 Hickory Grove | Invoiced
114 Hickory Grove | Job Complete/Inspected
113 Hickory Grove | Invoiced
113 Hickory Grove | Job Complete/Inspected
11 Kipling Creek | Invoiced
11 Kipling Creek | Job Complete/Inspected
51 Southern Estates | Invoiced
51 Southern Estates | Job Complete/Inspected
32 Harvest Creek | Invoiced
32 Harvest Creek | Job Complete/Inspected
Smith Farmhouse | Invoiced
Smith Farmhouse | Job Complete/Inspected
157 Neill's Creek | Invoiced
157 Neill's Creek | Job Complete/Inspected
9 Mason Landing | Invoiced
9 Mason Landing | Job Complete/Inspected
18 Heritage at Neill's Creek | Invoiced
18 Heritage at Neill's Creek | Job Complete/Inspected
10 Heritage at Neill's Creek | Invoiced
10 Heritage at Neill's Creek | Job Complete/Inspected
5 Heritage at Neill's Creek | Invoiced
5 Heritage at Neill's Creek | Job Complete/Inspected
2 Heritage at Neill's Creek | Invoiced
2 Heritage at Neill's Creek | Job Complete/Inspected
115 Ashcroft | Invoiced

## Paid False Data (hidden)
Siding Not Paid | Painters Not Paid | Columns Not Paid | Trellis Not Paid | Rails Not Paid | Screen Porch Not Paid | Decking Not Paid | Waterproof Deck Not Paid | Louvered Wall To Pay | Gutters Not Paid | Invoiced False | Invoiced True
318 Oak Manor | 47 Stanat Place TH | Column Template | 46 Stanat Place TH | 86 Falls of The Cape | 31 Williams Grove | #N/A | 16 Maison Ridge | #N/A | Gutter Template | 318 Oak Manor | 60 Meadow @ Jones Dairy
436 Oak Manor | 43 Stanat Place TH |  | 45 Stanat Place TH | 16 Maison Ridge | 198 Falls Village |  | Waterproof Deck Template |  |  | 436 Oak Manor | 776 Edge of Auburn - Classic
421 Oak Manor | 90 Twinleaf Townes |  | 44 Stanat Place TH | Rail Template | 190 Falls Village |  |  |  |  | 421 Oak Manor | 244 Turkey Ridge
776 Edge of Auburn - Classic | 165 Trails at Young Farm |  | 41 Stanat Place TH |  | 187 Falls Village |  |  |  |  | 124 Carpenter Falls TH | 433 Oak Manor
124 Carpenter Falls TH | 83 Twinleaf Townes TH |  | 40 Stanat Place TH |  | 185 Falls Village |  |  |  |  | 123 Carpenter Falls TH | 90 River Glen
123 Carpenter Falls TH | 84 Twinleaf Townes TH |  | 39 Stanat Place TH |  | 195 Falls Village |  |  |  |  | 122 Carpenter Falls TH | 91 River Glen
122 Carpenter Falls TH | 311 Carolina Overlook |  | 36 Stanat Place TH |  | 111 Falls Village |  |  |  |  | 121 Carpenter Falls TH | 92 River Glen
121 Carpenter Falls TH | 373 Vineyards @ Chatham Park |  | 35 Stanat Place TH |  | 107 Falls Village |  |  |  |  | 120 Carpenter Falls TH | 120 Annandale
120 Carpenter Falls TH | 55 providence Oaks 40 |  | 34 Stanat Place TH |  | 46 Williams Grove |  |  |  |  | 119 Carpenter Falls TH | 184 Falls Village
119 Carpenter Falls TH | 109 Providence Oaks 30 |  | 33 Stanat Place TH |  | 18 Williams Grove |  |  |  |  | 118 Carpenter Falls TH | 183 Falls Village
118 Carpenter Falls TH | 100 Providence Oaks 30' |  | 24 Stanat Place TH |  | 30 Williams Grove |  |  |  |  | 117 Carpenter Falls TH | 182 Falls Village
117 Carpenter Falls TH | 98 Providence Oaks 30' |  | 17 Stanat Place TH |  | 27 Williams Grove |  |  |  |  | 116 Carpenter Falls TH | 251 Turkey Ridge
116 Carpenter Falls TH | 106 Hickory Grove |  | 5 Heritage at Neill's Creek |  | 26 Williams Grove |  |  |  |  | 115 Carpenter Falls TH | 11 Ellington Estates
115 Carpenter Falls TH | 5 Regency @ Olde Towne |  | Trellis Template |  | Screen Porch Template |  |  |  |  | 114 Carpenter Falls TH | 3 Franklin Townes TH
114 Carpenter Falls TH | 94 Stonewood | [8 empty] | 113 Carpenter Falls TH | 2 Franklin Townes TH
113 Carpenter Falls TH | 91 Stonewood | [8 empty] | 15 Finley Landing | 245 Turkey Ridge
15 Finley Landing | 71 Stonewood | [8 empty] | 93 River Glen | 95 Meadow @ Jones Dairy
93 River Glen | 46 Page Townes TH | [8 empty] | 94 River Glen | 50 Little River
94 River Glen | 47 Page Townes TH | [8 empty] | 96 River Glen | 37 Gardner Farms
96 River Glen | 48 Page Townes TH | [8 empty] | 156 Grove at Wendell TH | 49 Kipling Creek
156 Grove at Wendell TH | 426 Paddington Station 30' | [8 empty] | 155 Grove at Wendell TH | 47 Kipling Creek
155 Grove at Wendell TH | 23 Forestville TH | [8 empty] | 154 Grove at Wendell TH | 39 Kipling Creek
154 Grove at Wendell TH | 22 Forestville TH | [8 empty] | 153 Grove at Wendell TH | 33 Kipling Creek
153 Grove at Wendell TH | 21 Forestville TH | [8 empty] | 139 Annandale | 21 Kipling Creek
139 Annandale | 20 Forestville TH | [8 empty] | 138 Annandale | 10 Kipling Creek
138 Annandale | 17 Forestville TH | [8 empty] | 165 Trails at Young Farm | 137 Marin Woods
165 Trails at Young Farm | 19 Forestville TH | [8 empty] | 4 Franklin Townes TH | 86 Ashcroft
4 Franklin Townes TH | 183 Trails @ Young Farm | [8 empty] | 114 Caitlin Crossing TH | 87 Ashcroft
3 Franklin Townes TH | 18 Forestville TH | [8 empty] | 854 Edge of Auburn - Sterling | 30 Elk Creek
2 Franklin Townes TH | 45 Page Townes TH | [8 empty] | 48 Kipling Creek | 25 Elk Creek
114 Caitlin Crossing TH | 44 Page Townes TH | [8 empty] | 32 Kipling Creek | 155 Preserve @ Jones Dairy
854 Edge of Auburn - Sterling | 43 Page Townes TH | [8 empty] | 30 Kipling Creek | 74 Caitlin Crossing
30 Kipling Creek | 113 Hickory Grove | [8 empty] | 50 Elk Creek | 187 Falls Village
50 Elk Creek | 11 Providence Oaks 30' | [8 empty] | 85 Ashcroft | 111 Falls Village
85 Ashcroft | 2 Providence Oaks 30' | [8 empty] | 49 Elk Creek | 151 Falls Village
49 Elk Creek | 95 Providence Oaks 40' | [8 empty] | 4 OYL | 246 Turkey Ridge
74 Caitlin Crossing | 115 Test Job | [8 empty] | 55 providence Oaks 40 | 186 Falls Village
4 OYL | 52 Louisbury Preserve Test | [8 empty] | 110 Providence Oaks 30 | 307 S Elm
55 providence Oaks 40 | 37 Glenmere Gardens test | [8 empty] | 109 Providence Oaks 30 | 153 Falls Village
110 Providence Oaks 30 | 24 River Glen TEST | [8 empty] | 378 Carolina Overlook | 126 Hickory Grove
109 Providence Oaks 30 | Paint Template | [8 empty] | 314 Carolina Overlook | 125 Hickory Grove
378 Carolina Overlook | [9 empty] | 312 Carolina Overlook | 106 Hickory Grove
314 Carolina Overlook | [9 empty] | 311 Carolina Overlook | 104 Hickory Grove
312 Carolina Overlook | [9 empty] | 877 Edge of Auburn - | 199 Falls Village
311 Carolina Overlook | [9 empty] | 844 Edge of Auburn - | 80 Providence Oaks 40
876 Edge of Auburn - | [9 empty] | 843 Edge of Auburn - | 105 Providence Oaks 30
877 Edge of Auburn - | [9 empty] | 103 Sagewood | 106 Guin
878 Edge of Auburn - | [9 empty] | 773 Edge of Auburn - Classic | 4 Rollins Acres
845 Edge of Auburn - | [9 empty] | 15 Caitlin Crossing | 264 Turkey Ridge
844 Edge of Auburn - | [9 empty] | 134 Athens Acres | 128 Pines at Wake Crossing
843 Edge of Auburn - | [9 empty] | 14 Caitlin Crossing | 127 Pines at Wake Crossing
842 Edge of Auburn - | [9 empty] | 13 Caitlin Crossing | 159 Preserve @ Jones Dairy
73 Caitlin Crossing | [9 empty] | 20 Auburn Station | 876 Edge of Auburn -
103 Sagewood | [9 empty] | 83 Stonewood | 878 Edge of Auburn -
777 Edge of Auburn - Classic | [9 empty] | 59 Watkins Grove | 845 Edge of Auburn -
773 Edge of Auburn - Classic | [9 empty] | 61 Watkins Grove | 842 Edge of Auburn -
72 Caitlin Crossing | [9 empty] | 46 Watkins Grove | 73 Caitlin Crossing
159 Auburn Station | [9 empty] | 196 Annandale | 158 Preserve @ Jones Dairy
5 Auburn Station | [9 empty] | 91 Stonewood | 777 Edge of Auburn - Classic
15 Caitlin Crossing | [9 empty] | 105 Stonewood | 774 Edge of Auburn - Classic
92 Finley Landing TH | [9 empty] | Pinehurst Ct- Pinehurst | 12 Olivet
91 Finley Landing TH | [9 empty] | Pinehurst Ct- Magnolia | 86 Carolina Landing
90 Finley Landing TH | [9 empty] | 38 Watkins Grove | 50 OYL
89 Finley Landing TH | [9 empty] | 60 Watkins Grove | 48 Little River
88 Finley Landing TH | [9 empty] | 68 Watkins Grove | 72 Caitlin Crossing
134 Athens Acres | [9 empty] | 64 Watkins Grove | 26 Walnut Hall
20 Auburn Station | [9 empty] | 231 Turkey Ridge | 85 Twinleaf Townes
83 Stonewood | [9 empty] | 234 Turkey Ridge | 86 Twinleaf Townes
59 Watkins Grove | [9 empty] | 233 Turkey Ridge | 87 Twinleaf Townes
61 Watkins Grove | [9 empty] | delete | 88 Twinleaf Townes
46 Watkins Grove | [9 empty] | 102 Duncans Creek | 89 Twinleaf Townes
196 Annandale | [9 empty] | 91 Elk Creek | 90 Twinleaf Townes
91 Stonewood | [9 empty] | 163 Edge of Auburn - Summit | 159 Auburn Station
105 Stonewood | [9 empty] | 41 Watkins Grove | 5 Auburn Station
Pinehurst Ct- Magnolia | [9 empty] | 426 Paddington Station 30' | 16 Caitlin Crossing
38 Watkins Grove | [9 empty] | 23 Forestville TH | 771 Edge of Auburn - Classic
60 Watkins Grove | [9 empty] | 22 Forestville TH | 197 Falls Village
68 Watkins Grove | [9 empty] | 21 Forestville TH | 179 Falls Village
64 Watkins Grove | [9 empty] | 20 Forestville TH | 158 Falls Village
231 Turkey Ridge | [9 empty] | 39 Millstone | 155 Falls Village
234 Turkey Ridge | [9 empty] | 29 Millstone | 84 Summer Place
233 Turkey Ridge | [9 empty] | 28 Millstone | 83 Summer Place
delete | [9 empty] | 24 Millstone | 82 Summer Place
91 Elk Creek | [9 empty] | 16 Millstone | 78 Summer Place
163 Edge of Auburn - Summit | [9 empty] | 15 Millstone | 77 Summer Place
41 Watkins Grove | [9 empty] | 10 Southern Estates | 76 Summer Place
426 Paddington Station 30' | [9 empty] | 18 Chapel Oaks | 75 Summer Place
23 Forestville TH | [9 empty] | 16 Chapel Oaks | 81 Sorrell Oaks
22 Forestville TH | [9 empty] | 20 Chapel Oaks | 92 Finley Landing TH
21 Forestville TH | [9 empty] | 42 Millstone | 91 Finley Landing TH
20 Forestville TH | [9 empty] | 19 Chapel Oaks | 90 Finley Landing TH
40 Millstone | [9 empty] | 86 Falls of The Cape | 89 Finley Landing TH
39 Millstone | [9 empty] | 85 Falls of The Cape | 88 Finley Landing TH
29 Millstone | [9 empty] | 233 Oak Manors | 123 Hickory Grove
28 Millstone | [9 empty] | 19 Forestville TH | 124 Hickory Grove
24 Millstone | [9 empty] | 18 Forestville TH | 710 Glascock
16 Millstone | [9 empty] | 17 Forestville TH | 111 Annandale
15 Millstone | [9 empty] | 2 Providence Oaks 30' | 192 Falls Village
10 Southern Estates | [9 empty] | 9 Watkins Grove | 200 Falls Village
18 Chapel Oaks | [9 empty] | 59 Millstone | 191 Falls Village
16 Chapel Oaks | [9 empty] | 376 Paddington Station 60' | 155 Chavis
20 Chapel Oaks | [9 empty] | 111 Chatham Park | 20 Caitlin Crossing
42 Millstone | [9 empty] | 101 Fieldview Village | 41 Gardner Farms
19 Chapel Oaks | [9 empty] | 100 Fieldview Village | 4517 Chatham Park North Village
86 Falls of The Cape | [9 empty] | 60 Fieldview Village | 157 Preserve @ Jones Dairy
49 Millstone | [9 empty] | 59 Fieldview Village | 190 Falls Village
60 Millstone | [9 empty] | 58 Fieldview Village | 168 Trails @ Young Farm
233 Oak Manors | [9 empty] | 57 Fieldview Village | 189 Falls Village
19 Forestville TH | [9 empty] | 56 Fieldview Village | 161 Stonewood
18 Forestville TH | [9 empty] | 55 Fieldview Village | 4518 Chatham Park North Village
17 Forestville TH | [9 empty] | 54 Fieldview Village | 110 Falls Village
2 Providence Oaks 30' | [9 empty] | 53 Fieldview Village | 152 Falls Village
9 Watkins Grove | [9 empty] | 52 Fieldview Village | 381 Vineyards @ Chatham Park
59 Millstone | [9 empty] | 10 Carson's Landing | 83 Providence Oaks 40'
376 Paddington Station 60' | [9 empty] | 9 Carson's Landing | 96 Providence Oaks 30'
111 Chatham Park | [9 empty] | 8 Carson's Landing | 89 River Glen
101 Fieldview Village | [9 empty] | 7 Carson's Landing | 88 River Glen
100 Fieldview Village | [9 empty] | 6 Carson's Landing | 136 River Glen
60 Fieldview Village | [9 empty] | 5 Carson's Landing | 107 Annandale
59 Fieldview Village | [9 empty] | 98 Magnolia Square West | 111 Trails @ Young Farm
58 Fieldview Village | [9 empty] | 28 Pearl Street TH | 9 Harvest Creek
57 Fieldview Village | [9 empty] | 27 Pearl Street TH | 175 Williams Grove
56 Fieldview Village | [9 empty] | 26 Pearl Street TH | 86 Stonewood
55 Fieldview Village | [9 empty] | 25 Pearl Street TH | 137 River Glen
54 Fieldview Village | [9 empty] | 16 Pearl Street TH | 764 Edge of Auburn - Classic
53 Fieldview Village | [9 empty] | 15 Pearl Street TH | 17 Caitlin Crossing
52 Fieldview Village | [9 empty] | 14 Pearl Street TH | 175 Walton Farms PH2
10 Carson's Landing | [9 empty] | 13 Pearl Street TH | 185 Falls Village
9 Carson's Landing | [9 empty] | 115 Test Job | 195 Falls Village
8 Carson's Landing | [9 empty] | Thompson Residence | 198 Falls Village
7 Carson's Landing | [9 empty] | Faircloth Residence | 188 Falls Village
6 Carson's Landing | [9 empty] | Brogden Residence | 114 Falls Village
5 Carson's Landing | [9 empty] | 52 Louisbury Preserve Test | 113 Falls Village
98 Magnolia Square West | [9 empty] | 71 Falls of the Cape | 112 Falls Village
28 Pearl Street TH | [9 empty] | 55 Louisbury Test | 108 Falls Village
27 Pearl Street TH | [9 empty] | 37 Glenmere Gardens test | 107 Falls Village
26 Pearl Street TH | [9 empty] | 23 Holding Village | 18 Olivet
25 Pearl Street TH | [9 empty] | 26 Coolwater | 110 Carolina Landing
16 Pearl Street TH | [9 empty] | 24 River Glen TEST | 109 Carolina Landing
15 Pearl Street TH | [9 empty] | 51 Fieldview Village | 134 River Glen
14 Pearl Street TH | [9 empty] | 50 Fieldview Village | 135 River Glen
13 Pearl Street TH | [9 empty] | 6 Emerson Fields | 163 Stonewood
115 Test Job | [9 empty] | 116 Ashcroft | 164 Stonewood
Thompson Residence | [9 empty] | 15 Duncan's Creek | 165 Stonewood
Faircloth Residence | [9 empty] | 36 High Gate Community | 87 Stonewood
Brogden Residence | [9 empty] | 34 High Gate Community | 79 Southern Estates
52 Louisbury Preserve Test | [9 empty] | 33 High Gate Community | 7 Laurel Ridge
71 Falls of the Cape | [9 empty] | 32 High Gate Community | 140 Annandale
55 Louisbury Test | [9 empty] | 31 High Gate Community | 105 Hickory Grove
37 Glenmere Gardens test | [9 empty] | 30 High Gate Community | 122 Hickory Grove
23 Holding Village | [9 empty] | 29 High Gate Community | 148 Wilkins
26 Coolwater | [9 empty] | 27 High Gate Community | 116 Chestnut
24 River Glen TEST | [9 empty] | 26 High Gate Community | 2 Windfield
51 Fieldview Village | [9 empty] | 19 High Gate Community | 4 Windfield
50 Fieldview Village | [9 empty] | 17 High Gate Community | 3 Windfield
6 Emerson Fields | [9 empty] | 16 High Gate Community | 1 Windfield
116 Ashcroft | [9 empty] | 15 High Gate Community | 84 Providence Oaks 40
15 Duncan's Creek | [9 empty] | 14 High Gate Community | 79 Providence Oaks 40'
36 High Gate Community | [9 empty] | 13 High Gate Community | 78 Providence Oaks 40'
34 High Gate Community | [9 empty] | 12 High Gate Community | Wilder Farms
33 High Gate Community | [9 empty] | 10 High Gate Community | 74 Stonewood
32 High Gate Community | [9 empty] | 4 Neill's Pointe | Dunn House
31 High Gate Community | [9 empty] | 206 Neill's Pointe | 12 Eller Farms
30 High Gate Community | [9 empty] | 205 Neill's Pointe | 19 Caitlin Crossing
29 High Gate Community | [9 empty] | 204 Neill's Pointe | 18 Caitlin Crossing
27 High Gate Community | [9 empty] | 195 Neill's Pointe | 6 Caitlin Crossing
26 High Gate Community | [9 empty] | 194 Neill's Pointe | 5 Caitlin Crossing
19 High Gate Community | [9 empty] | 193 Neill's Pointe | 16 Maison Ridge
17 High Gate Community | [9 empty] | 168 Neill's Pointe | 47 Stanat Place TH
16 High Gate Community | [9 empty] | 165 Neill's Pointe | 46 Stanat Place TH
15 High Gate Community | [9 empty] | 164 Neill's Pointe | 45 Stanat Place TH
14 High Gate Community | [9 empty] | 158 Neill's Creek | 44 Stanat Place TH
13 High Gate Community | [9 empty] | 11 Carson's Landing | 43 Stanat Place TH
12 High Gate Community | [9 empty] | 20 Griffon Pointe | 40 Raven Ridge Place TH
10 High Gate Community | [9 empty] | 18 Mill Stream | 39 Raven Ridge Place TH
4 Neill's Pointe | [9 empty] | Siding Template | 38 Raven Ridge Place TH
206 Neill's Pointe | [10 empty] | 37 Raven Ridge Place TH
205 Neill's Pointe | [10 empty] | 11 Olivet
204 Neill's Pointe | [10 empty] | 133 River Glen
195 Neill's Pointe | [10 empty] | 132 River Glen
194 Neill's Pointe | [10 empty] | 131 River Glen
193 Neill's Pointe | [10 empty] | 130 River Glen
168 Neill's Pointe | [10 empty] | 27 Williams Grove
165 Neill's Pointe | [10 empty] | 187 Trails at Young Farm
164 Neill's Pointe | [10 empty] | 113 Trails at Young Farm
158 Neill's Creek | [10 empty] | 103 Duncans Creek
11 Carson's Landing | [10 empty] | 52 Duncans Creek
115 Ashcroft | [10 empty] | 45 Duncans Creek
18 Mill Stream | [10 empty] | 23 Duncans Creek
Siding Template | [10 empty] | 38 Duncans Creek
36 Duncans Creek
30 Duncans Creek
57 Summer Place
58 Summer Place
59 Summer Place
60 Summer Place
69 Summer Place
110 Trails at Young Farm
145 Trails at Young Farm
32 Duncans Creek
9 Caitlin Crossing
30 Williams Grove
24 Williams Grove
21 Williams Grove
4 Caitlin Crossing
8 Caitlin Crossing
3 Caitlin Crossing
2 Caitlin Crossing - Model
87 River Glen
112 Trails at Young Farm
14 Holding Village Mews TH
41 Millstone
40 Millstone
86 River Glen
28 Harvest Creek
7 Harvest Creek
754 Edge of Auburn - Classic
75 Stonewood
106 Falls Village
196 Falls Village
109 Falls Village
85 River Glen
44 Williams Grove
26 Williams Grove
Pierre Morin Residence
17 Carolina Overlook Twin Villas
16 Carolina Overlook Twin Villas
1 Tart Town Rd
93 Regency @ Olde Towne
153 Trails at Young Farm
99 Providence Oaks 30'
98 Providence Oaks 30'
97 Providence Oaks 30'
373 Vineyards @ Chatham Park
72 Summer Place
68 Summer Place
71 Summer Place
70 Summer Place
61 Summer Place
42 Stanat Place TH
41 Stanat Place TH
40 Stanat Place TH
39 Stanat Place TH
38 Stanat Place TH
53 Summer Place
67 Summer Place
66 Summer Place
171 Trails at Young Farm
152 Trails at Young Farm
3302 Hall Place
4531 Chatham Park North Village
43 Turnberry Rd
84 River Glen
48 Page Townes TH
47 Page Townes TH
46 Page Townes TH
151Trails at Young Farm
5 Gardner Farms
39 Watkins Grove
90 Stonewood
89 Stonewood
88 Stonewood
93 Stonewood
94 Stonewood
76 Stonewood
92 Stonewood
73 Stonewood
125 River Glen
81 River Glen
83 River Glen
72 Stonewood
110 Hickory Grove
121 Hickory Grove
6 Rollins Acres
5 Rollins Acre
10 Ballard Rd
9 Ballard Rd
171 Keith Hills
152 Preserve @ Jones Dairy
64 Southern Estates
146 Trails @ Young Farm
6 Southern Estates
82 River Glen
380 Vineyards @ Chatham Park
100 Providence Oaks 30'
21 Providence Oaks 30'
85 Providence Oaks 40'
50 Providence Oaks 40'
2 Providence Oaks 40'
172 Trails at Young Farm
275 Oak Manor
129 River Glen
128 River Glen
75 Harvest Meadows
5 Regency @ Olde Towne
90 Falls of The Cape
89 Falls of The Cape
88 Falls of The Cape
87 Falls of The Cape
97 Falls of The Cape
96 Falls of The Cape
93 Falls of The Cape
92 Falls of The Cape
8 Ballard Road
2 Eller Farms 2
37 Stanat Place TH
36 Stanat Place TH
35 Stanat Place TH
34 Stanat Place TH
33 Stanat Place TH
32 Stanat Place TH
89 Regency @ Olde Towne
49 Millstone
60 Millstone
55 Millstone
7 Ballard Road
346 Vineyards @ Chatham Park
49 Providence Oaks 40'
6 Ballard Road
4551 Chatham Park North Village
109 Trails @ Young Farm
18 Williams Grove
16 Williams Grove
46 Williams Grove
31 Williams Grove
4532 Chatham Park North Village
383 Vineyards @ Chatham Park
23 Providence Oaks 40'
20 Providence Oaks 40'
19 Providence Oaks 30'
18 Providence Oaks 30'
71 Stonewood
45 Page Townes TH
44 Page Townes TH
43 Page Townes TH
36 Raven Ridge Place TH
11 Mulhollem
35 Raven Ridge Place TH
34 Raven Ridge Place TH
33 Raven Ridge Place TH
32 Raven Ridge Place TH
31 Raven Ridge Place TH
30 Raven Ridge Place TH
29 Raven Ridge Place TH
28 Raven Ridge Place TH
11 Raven Ridge Place TH
74 Archer's Park
73 Archer's Park
10 Raven Ridge Place TH
9 Raven Ridge Place TH
8 Raven Ridge Place TH
7 Raven Ridge Place TH
6 Raven Ridge Place TH
150 Trails @ Young Farm
348 Vineyards @ Chatham Park
304 Vineyards @ Chatham Park
88 Providence Oaks 40'
87 Providence Oaks 40'
86 Providence Oaks 40'
22 Providence Oaks 40'
17 Providence Oaks 30'
16 Providence Oaks 30'
15 Providence Oaks 30'
14 Providence Oaks 30'
13 Providence Oaks 30'
4533 Chatham Park North Village
80 River Glen
50 Millstone
79 River Glen
84 Twinleaf Townes TH
83 Twinleaf Townes TH
82 Twinleaf Townes TH
81 Twinleaf Townes TH
80 Twinleaf Townes TH
79 Twinleaf Townes TH
70 Stonewood
78 River Glen
31 Stanat Place TH
30 Stanat Place TH
29 Stanat Place TH
28 Stanat Place TH
27 Stanat Place TH
26 Stanat Place TH
76 River Glen
75 River Glen
77 River Glen
49 Southern Estates
48 Southern Estates
1 Southern Estates
28 Hickory Grove
60 North Lakes at South Lakes
11 North Lakes at South Lakes
9 North Lakes at South Lakes
13 North Lakes at South Lakes
4549 Chatham Park North Village
4550 Chatham Park North Village
4534 Chatham Park North Village
2 Southern Estates
11 Providence Oaks 30'
44 Kipling Creek
104 Stonewood
103 Stonewood
102 Stonewood
69 Stonewood
68 Stonewood
43 Kipling Creek
41 Kipling Creek
4548 Chatham Park North Village
40 Kipling Creek
24 Kipling Creek
23 Kipling Creek
22 Kipling Creek
8 Southern Estates
Smith's Farmhouse Lodge
3 Heritage @ Neills Creek
12 Providence Oaks 30'
10 Providence Oaks 30'
9 Providence Oaks 30'
8 Providence Oaks 30'
90 Providence Oaks 40'
89 Providence Oaks 40'
375 Vineyards @ Chatham Park
46 Little River
13 Page Townes TH
12 Page Townes TH
11 Page Townes TH
78 Twinleaf Townes TH
77 Twinleaf Townes TH
76 Twinleaf Townes TH
75 Twinleaf Townes TH
74 Twinleaf Townes TH
73 Twinleaf Townes TH
25 Stanat Place TH
24 Stanat Place TH
23 Stanat Place TH
22 Stanat Place TH
21 Stanat Place TH
9 Southern Estates
91 Providence Oaks 40'
7 Providence Oaks 30'
4 Southern Estates
20 Stanat Place TH
42 Kipling Creek
35 Kipling Creek
3 Southern Estates
2 Regency @ Olde Towne
1 Regency @ Olde Towne
36 Regency @ Olde Towne
8 Millstone
3 Regency @ Olde Towne
10 Millstone
147 Trails @ Young Farm
183 Trails @ Young Farm
59 North Lakes @ South Lakes
5 North Lakes @ South Lakes
12 North Lakes @ South Lakes
8 North Lakes @ South Lakes
93 Providence Oaks 40'
92 Providence Oaks 40'
59 Twinleaf Townes
62 Twinleaf Townes
60 Twinleaf Townes
63 Twinleaf Townes
61 Twinleaf Townes
7 North Lakes @ South Lakes
2 North Lakes @ South Lakes
3 North Lakes @ South Lakes
19 Stanat Place TH
18 Stanat Place TH
17 Stanat Place TH
16 Stanat Place TH
15 Stanat Place TH
347 Vineyards @ Chatham Park
95 Providence Oaks 40'
94 Providence Oaks 40'
6 Providence Oaks 30'
5 Providence Oaks 30'
58 Millstone
3 Millstone
11 Millstone
46 Millstone
9 Millstone
12 Millstone
56 Millstone
57 Millstone
112 Regency @ Olde Towne
2 Millstone
54 Millstone
51 Millstone
48 Millstone
45 Millstone
13 Millstone
6 Millstone
5 Millstone
4 Millstone
65 North Lakes @ South Lakes
61 North Lakes @ South Lakes
14 Stanat Place TH
13 Stanat Place TH
12 Stanat Place TH
11 Stanat Place TH
10 Stanat Place TH
17 Page Townes TH
16 Page Townes TH
15 Page Townes TH
14 Page Townes TH
6 North Lakes at South Lakes
39 Carolina Landing
17 Twinleaf Townes
16 Twinleaf Townes
15 Twinleaf Townes
14 Twinleaf Townes
13 Twinleaf Townes
349 Vineyards @ Chatham Park
345 Vineyards @ Chatham Park
84 Regency @ Olde Towne
7 Millstone
90 Regency @ Olde Towne
157 Duncans Creek
156 Duncans Creek
155 Duncans Creek
154 Duncans Creek
153 Duncans Creek
152 Duncans Creek
160 Duncans Creek
158 Duncans Creek
151 Duncans Creek
131 Duncans Creek
124 Duncans Creek
123 Duncans Creek
16 Sippihaw Springs
15 Sippihaw Springs
8 Sippihaw Springs
7 Sippihaw Springs
4 Sippihaw Springs
3 Sippihaw Springs
73 Regency @ Olde Towne
340 Vineyards @ Chatham Park
12 Twinleaf Townes
11 Twinleaf Townes
10 Twinleaf Townes
9 Twinleaf Townes
8 Twinleaf Townes
7 Twinleaf Townes
6069 Jones Circle
3258 Yorkshire Circle
3260 Yorkshire Circle
9 Stanat Place TH
8 Stanat Place TH
7 Stanat Place TH
6 Stanat Place TH
5 Stanat Place TH
4 Stanat Place TH
3 Stanat Place TH
2 Stanat Place TH
1 Stanat Place TH
16 Ellington Estates
30 Magnolia Estates
28 Magnolia Estates
25 Magnolia Estates
24 Magnolia Estates
16 Magnolia Estates
39 Falls Of the Cape
15 Ellington Estates
84 Southern Estates
83 Southern Estates
63 Southern Estates
46 Southern Estates
91 Falls of The Cape
75 Olive Grove SF
74 Olive Grove SF
94 Falls of the Cape
73 Falls of the Cape
72 Falls of the Cape
54 Kipling Creek
51 Kipling Creek
74 Harvest Meadows
20 Coolwater
26 Ellington Estates
114 Hickory Grove
113 Hickory Grove
11 Kipling Creek
51 Southern Estates
32 Harvest Creek
Smith Farmhouse
157 Neill's Creek
9 Mason Landing
18 Heritage at Neill's Creek
10 Heritage at Neill's Creek
5 Heritage at Neill's Creek
2 Heritage at Neill's Creek
115 Ashcroft

## Load Data Here (052124)
Job | Title | Marked Complete | Percent Complete | Phase | Dur. | Start | End | Assigned To | Confirm Accepted Count | Confirm Pending Count | Confirm Declined Count
88 Falls of The Cape | Paid Rails | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
88 Falls of The Cape | Rails Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
86 Falls of The Cape | Paid Rails | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
86 Falls of The Cape | Rails Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
47 Stanat Place TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
47 Stanat Place TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
43 Stanat Place TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
43 Stanat Place TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
90 Twinleaf Townes | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
90 Twinleaf Townes | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16 | Torres Painting Professional
120 Annandale | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
120 Annandale | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-27 | 2025-08-27 | Torres Painting Professional
111 Annandale | Paid Rails | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
111 Annandale | Rails Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05 | Roy Ingle
111 Annandale | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
111 Annandale | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-22 | 2025-08-22 | Torres Painting Professional
161 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-21 | 2025-08-21
161 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-20 | 2025-08-20 | Torres Painting Professional
165 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-21 | 2025-08-21
165 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-20 | 2025-08-20 | Torres Painting Professional
131 Duncans Creek | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
131 Duncans Creek | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-04 | 2025-08-04 | Roy Ingle
14 Holding Village Mews TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-24 | 2025-07-24
14 Holding Village Mews TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-23 | 2025-07-23 | Chay Morales Painting [Javier]
140 Annandale | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-14 | 2025-07-14
140 Annandale | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-23 | 2025-07-23 | Torres Painting Professional
381 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-03 | 2025-07-03
381 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02 | Torres Painting Professional
380 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-03 | 2025-07-03
380 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02 | Torres Painting Professional
31 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
31 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
198 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
198 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
190 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
190 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
187 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
187 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
185 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
185 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
195 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
195 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
111 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
111 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
107 Falls Village | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01
107 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
165 Trails at Young Farm | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-10 | 2025-07-10
165 Trails at Young Farm | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-09 | 2025-07-09
83 Twinleaf Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
83 Twinleaf Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
84 Twinleaf Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
84 Twinleaf Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
38 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
38 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17 | Torres Painting Professional
82 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
82 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17 | Torres Painting Professional
81 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
81 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17 | Torres Painting Professional
80 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
80 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17 | Torres Painting Professional
79 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
79 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | Torres Painting Professional
42 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
42 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | Torres Painting Professional
157 Preserve @ Jones Dairy | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
157 Preserve @ Jones Dairy | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | MTR Painting LLC [Moises]
311 Carolina Overlook | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-11 | 2025-07-11
311 Carolina Overlook | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-10 | 2025-07-10
373 Vineyards @ Chatham Park | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
373 Vineyards @ Chatham Park | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29
60 Meadow @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-23 | 2025-07-23
60 Meadow @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-21 | 2025-07-21
60 Meadow @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-17 | 2025-07-17
60 Meadow @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-15 | 2025-07-15
60 Meadow @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-11 | 2025-07-11 | Mendez Siding & Boxing LLC
60 Meadow @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
60 Meadow @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
60 Meadow @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
60 Meadow @ Jones Dairy | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-09 | 2025-05-09
318 Oak Manor | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
318 Oak Manor | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
318 Oak Manor | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
318 Oak Manor | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
318 Oak Manor | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-04 | 2025-08-04
318 Oak Manor | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
318 Oak Manor | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-04 | 2025-08-04
318 Oak Manor | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
318 Oak Manor | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
196 Falls Village | Paid Screen Porch | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
196 Falls Village | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-14 | 2025-05-14 | Screen Builders, Inc.
436 Oak Manor | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
436 Oak Manor | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-12 | 2025-09-12
436 Oak Manor | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
436 Oak Manor | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
436 Oak Manor | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-28 | 2025-07-28
436 Oak Manor | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
436 Oak Manor | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-28 | 2025-07-28
436 Oak Manor | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-26 | 2025-05-26
436 Oak Manor | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-26 | 2025-05-26
421 Oak Manor | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-08 | 2025-09-08
421 Oak Manor | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-04 | 2025-09-04
421 Oak Manor | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
421 Oak Manor | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-29 | 2025-08-29
421 Oak Manor | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-18 | 2025-07-18
421 Oak Manor | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
421 Oak Manor | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-18 | 2025-07-18
421 Oak Manor | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-16 | 2025-05-16
421 Oak Manor | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-16 | 2025-05-16
776 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-06 | 2025-10-06
776 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-21 | 2025-07-21
776 Edge of Auburn - Classic | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-30 | 2025-09-30
776 Edge of Auburn - Classic | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-26 | 2025-09-26
776 Edge of Auburn - Classic | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-15 | 2025-08-15
776 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
776 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-15 | 2025-08-15
776 Edge of Auburn - Classic | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-13 | 2025-06-13
776 Edge of Auburn - Classic | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-13 | 2025-06-13
244 Turkey Ridge | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
244 Turkey Ridge | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-09 | 2025-09-09 | Torres Painting Professional
244 Turkey Ridge | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-09 | 2025-09-09
244 Turkey Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-07 | 2025-08-07
244 Turkey Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
244 Turkey Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-01 | 2025-08-01 | JTD SIDING CONSTRUCTION LLC
244 Turkey Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-29 | 2025-07-29 | JTD SIDING CONSTRUCTION LLC
244 Turkey Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-07-21 | 2025-07-21
244 Turkey Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-29 | 2025-07-29
244 Turkey Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-27 | 2025-05-27
244 Turkey Ridge | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-27 | 2025-05-27
124 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-09 | 2025-10-09
124 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-07 | 2025-10-07
124 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-03 | 2025-10-03
124 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-01 | 2025-10-01
124 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-20 | 2025-08-20
124 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-19 | 2025-08-19
124 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-20 | 2025-06-20
124 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-18 | 2025-06-18
124 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-18 | 2025-06-18
123 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-08 | 2025-10-08
123 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-06 | 2025-10-06
123 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-02 | 2025-10-02
123 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-30 | 2025-09-30
123 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-19 | 2025-08-19
123 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-18 | 2025-08-18
123 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-19 | 2025-06-19
123 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-17 | 2025-06-17
123 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-17 | 2025-06-17
122 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-07 | 2025-10-07
122 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-03 | 2025-10-03
122 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-01 | 2025-10-01
122 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-29 | 2025-09-29
122 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-18 | 2025-08-18
122 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-15 | 2025-08-15
122 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-18 | 2025-06-18
122 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-16 | 2025-06-16
122 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-16 | 2025-06-16
121 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-06 | 2025-10-06
121 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-02 | 2025-10-02
121 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-30 | 2025-09-30
121 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-26 | 2025-09-26
121 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-15 | 2025-08-15
121 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-14 | 2025-08-14
121 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-17 | 2025-06-17
121 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-13 | 2025-06-13
121 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-13 | 2025-06-13
120 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-03 | 2025-10-03
120 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
120 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-29 | 2025-09-29
120 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
120 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-14 | 2025-08-14
120 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-13 | 2025-08-13
120 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-16 | 2025-06-16
120 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-12 | 2025-06-12
120 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-12 | 2025-06-12
119 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
119 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
119 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
119 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
119 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-11 | 2025-08-11
119 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-08 | 2025-08-08
119 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-11 | 2025-06-11
119 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-09 | 2025-06-09
119 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-09 | 2025-06-09
118 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
118 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
118 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
118 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
118 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
118 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
118 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
118 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
118 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
117 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
117 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
117 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
117 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
117 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
117 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
117 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
117 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
117 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
116 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-26 | 2025-08-26
116 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-22 | 2025-08-22
116 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-20 | 2025-08-20
116 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-18 | 2025-08-18
116 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-07 | 2025-07-07
116 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-07-04 | 2025-07-04
116 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-16 | 2025-06-16
116 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-12 | 2025-06-12
116 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-12 | 2025-06-12
115 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-14 | 2025-10-14
115 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-10 | 2025-10-10
115 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-08 | 2025-10-08
115 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-06 | 2025-10-06
115 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-25 | 2025-08-25
115 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-22 | 2025-08-22
115 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-25 | 2025-06-25
115 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-23 | 2025-06-23
115 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-23 | 2025-06-23
114 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-11 | 2025-09-11
114 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
114 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05
114 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
114 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-23 | 2025-07-23
114 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
114 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23
114 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-21 | 2025-05-21
114 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-21 | 2025-05-21
113 Carpenter Falls TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-10 | 2025-09-10
113 Carpenter Falls TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-08 | 2025-09-08
113 Carpenter Falls TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
113 Carpenter Falls TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
113 Carpenter Falls TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-22 | 2025-07-22
113 Carpenter Falls TH | Measurements | FALSE | 0 | Measured | 1 | 2025-07-21 | 2025-07-21
113 Carpenter Falls TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-22 | 2025-05-22
113 Carpenter Falls TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-20 | 2025-05-20
113 Carpenter Falls TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-20 | 2025-05-20
15 Finley Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-10 | 2025-10-10
15 Finley Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-08 | 2025-10-08
15 Finley Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-06 | 2025-10-06
15 Finley Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-02 | 2025-10-02
15 Finley Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-21 | 2025-08-21
15 Finley Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-20 | 2025-08-20
15 Finley Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-23 | 2025-06-23
15 Finley Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-19 | 2025-06-19
15 Finley Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-19 | 2025-06-19
433 Oak Manor | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
433 Oak Manor | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-19 | 2025-06-19
433 Oak Manor | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
433 Oak Manor | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
433 Oak Manor | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-16 | 2025-06-16 | Martinez NC Construction LLC [Luis]
433 Oak Manor | Measurements | TRUE | 100 | Measured | 1 | 2025-05-13 | 2025-05-13
433 Oak Manor | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-16 | 2025-06-16
433 Oak Manor | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-14 | 2025-04-14
433 Oak Manor | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-14 | 2025-04-14
90 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
90 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
90 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
90 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
90 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-06 | 2025-06-06 | New World Siding Construction Inc.
90 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-30 | 2025-07-30
90 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
90 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-04 | 2025-04-04
90 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-08 | 2025-04-08
91 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
91 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
91 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
91 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
91 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-03 | 2025-06-03 | Jesus Construction
91 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-21 | 2025-07-21
91 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03
91 River Glen | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-01 | 2025-04-01
91 River Glen | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-01 | 2025-04-01
92 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
92 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
92 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
92 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
92 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-06 | 2025-06-06 | Leones Construction LLC
92 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-11 | 2025-07-11
92 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
92 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-09 | 2025-04-09
92 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
93 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-02 | 2025-09-02
93 River Glen | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-29 | 2025-08-29
93 River Glen | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-27 | 2025-08-27
93 River Glen | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
93 River Glen | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-14 | 2025-07-14
93 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-11 | 2025-07-11
93 River Glen | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
93 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-15 | 2025-05-15
93 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
94 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-03 | 2025-09-03
94 River Glen | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-01 | 2025-09-01
94 River Glen | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-28 | 2025-08-28
94 River Glen | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-26 | 2025-08-26
94 River Glen | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-15 | 2025-07-15
94 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-14 | 2025-07-14
94 River Glen | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
94 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-15 | 2025-05-15
94 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
96 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-08 | 2025-09-08
96 River Glen | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-04 | 2025-09-04
96 River Glen | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
96 River Glen | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-29 | 2025-08-29
96 River Glen | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-18 | 2025-07-18
96 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-17 | 2025-07-17
96 River Glen | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20
96 River Glen | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-16 | 2025-05-16
96 River Glen | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-16 | 2025-05-16
156 Grove at Wendell TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-13 | 2025-10-13
156 Grove at Wendell TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-09 | 2025-10-09
156 Grove at Wendell TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-07 | 2025-10-07
156 Grove at Wendell TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-03 | 2025-10-03
156 Grove at Wendell TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-22 | 2025-08-22
156 Grove at Wendell TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-21 | 2025-08-21
156 Grove at Wendell TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
156 Grove at Wendell TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-20 | 2025-06-20
156 Grove at Wendell TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-20 | 2025-06-20
155 Grove at Wendell TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-13 | 2025-10-13
155 Grove at Wendell TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-09 | 2025-10-09
155 Grove at Wendell TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-07 | 2025-10-07
155 Grove at Wendell TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-03 | 2025-10-03
155 Grove at Wendell TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-22 | 2025-08-22
155 Grove at Wendell TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-21 | 2025-08-21
155 Grove at Wendell TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
155 Grove at Wendell TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-20 | 2025-06-20
155 Grove at Wendell TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-20 | 2025-06-20
154 Grove at Wendell TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-13 | 2025-10-13
154 Grove at Wendell TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-09 | 2025-10-09
154 Grove at Wendell TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-07 | 2025-10-07
154 Grove at Wendell TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-03 | 2025-10-03
154 Grove at Wendell TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-22 | 2025-08-22
154 Grove at Wendell TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-21 | 2025-08-21
154 Grove at Wendell TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
154 Grove at Wendell TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-20 | 2025-06-20
154 Grove at Wendell TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-20 | 2025-06-20
153 Grove at Wendell TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-13 | 2025-10-13
153 Grove at Wendell TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-09 | 2025-10-09
153 Grove at Wendell TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-07 | 2025-10-07
153 Grove at Wendell TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-03 | 2025-10-03
153 Grove at Wendell TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-22 | 2025-08-22
153 Grove at Wendell TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-21 | 2025-08-21
153 Grove at Wendell TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
153 Grove at Wendell TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-20 | 2025-06-20
153 Grove at Wendell TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-20 | 2025-06-20
139 Annandale | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
139 Annandale | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-12 | 2025-09-12
139 Annandale | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
139 Annandale | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
139 Annandale | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-28 | 2025-07-28
139 Annandale | Measurements | FALSE | 0 | Measured | 1 | 2025-07-25 | 2025-07-25
139 Annandale | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-28 | 2025-07-28
139 Annandale | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-26 | 2025-05-26
139 Annandale | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-26 | 2025-05-26
138 Annandale | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
138 Annandale | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-15 | 2025-09-15
138 Annandale | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
138 Annandale | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-09 | 2025-09-09
138 Annandale | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-29 | 2025-07-29
138 Annandale | Measurements | FALSE | 0 | Measured | 1 | 2025-07-28 | 2025-07-28
138 Annandale | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-29 | 2025-07-29
138 Annandale | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-27 | 2025-05-27
138 Annandale | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-27 | 2025-05-27
120 Annandale | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
120 Annandale | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-21 | 2025-07-21
120 Annandale | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-23 | 2025-07-23
120 Annandale | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-21 | 2025-07-21 | JTD SIDING CONSTRUCTION LLC
120 Annandale | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-17 | 2025-07-17 | JTD SIDING CONSTRUCTION LLC
120 Annandale | Measurements | TRUE | 100 | Measured | 1 | 2025-06-16 | 2025-06-16
120 Annandale | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-17 | 2025-07-17 | JTD SIDING CONSTRUCTION LLC
120 Annandale | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
120 Annandale | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-14 | 2025-05-14
184 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-01 | 2025-07-01
184 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
184 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-25 | 2025-06-25
184 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23 | Siding Express, LLC [Israel]
184 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
184 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
184 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
184 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-18 | 2025-04-18
184 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-18 | 2025-04-18
183 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
183 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
183 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
183 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24 | Siding Express, LLC [Israel]
183 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
183 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
183 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
183 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-18 | 2025-04-18
183 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-18 | 2025-04-18
182 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-01 | 2025-07-01
182 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
182 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-25 | 2025-06-25
182 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23 | Siding Express, LLC [Israel]
182 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
182 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
182 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
182 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-18 | 2025-04-18
182 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-18 | 2025-04-18
251 Turkey Ridge | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
251 Turkey Ridge | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02 | Torres Painting Professional
251 Turkey Ridge | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
251 Turkey Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-15 | 2025-08-15
251 Turkey Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-13 | 2025-08-13
251 Turkey Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-11 | 2025-08-11 | Santiago Professional Siding [Santiago]
251 Turkey Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-08 | 2025-08-08 | Santiago Professional Siding [Santiago]
251 Turkey Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-07-28 | 2025-07-28
251 Turkey Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-08 | 2025-08-08 | Santiago Professional Siding [Santiago]
251 Turkey Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-06 | 2025-06-06
251 Turkey Ridge | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-09 | 2025-06-09
165 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
165 Trails at Young Farm | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-12 | 2025-09-12
165 Trails at Young Farm | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
165 Trails at Young Farm | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
165 Trails at Young Farm | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-28 | 2025-07-28
165 Trails at Young Farm | Measurements | FALSE | 0 | Measured | 1 | 2025-07-25 | 2025-07-25
165 Trails at Young Farm | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-28 | 2025-05-28
165 Trails at Young Farm | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-26 | 2025-05-26
11 Ellington Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
11 Ellington Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
11 Ellington Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
11 Ellington Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05 | Avery Siding LLC
11 Ellington Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-30 | 2025-05-30 | Avery Siding LLC
11 Ellington Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02 | Avery Siding LLC
11 Ellington Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02 | Avery Siding LLC
11 Ellington Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
11 Ellington Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-17 | 2025-03-17
4 Franklin Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
4 Franklin Townes TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
4 Franklin Townes TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
4 Franklin Townes TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
4 Franklin Townes TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-11 | 2025-08-11
4 Franklin Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-12 | 2025-05-12
4 Franklin Townes TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-11 | 2025-08-11
4 Franklin Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-12 | 2025-05-12
4 Franklin Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
3 Franklin Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
3 Franklin Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
3 Franklin Townes TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
3 Franklin Townes TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
3 Franklin Townes TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-11 | 2025-08-11
3 Franklin Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-12 | 2025-05-12
3 Franklin Townes TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-16 | 2025-07-16
3 Franklin Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-13 | 2025-05-13
3 Franklin Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-14 | 2025-05-14
2 Franklin Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
2 Franklin Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
2 Franklin Townes TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
2 Franklin Townes TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
2 Franklin Townes TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-11 | 2025-08-11
2 Franklin Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-12 | 2025-05-12
2 Franklin Townes TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-11 | 2025-08-11
2 Franklin Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
2 Franklin Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
114 Caitlin Crossing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
114 Caitlin Crossing TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
114 Caitlin Crossing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
114 Caitlin Crossing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
114 Caitlin Crossing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
114 Caitlin Crossing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
114 Caitlin Crossing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
114 Caitlin Crossing TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
114 Caitlin Crossing TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
245 Turkey Ridge | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
245 Turkey Ridge | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04 | Torres Painting Professional
245 Turkey Ridge | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-09 | 2025-09-09
245 Turkey Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-07 | 2025-08-07
245 Turkey Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
245 Turkey Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-01 | 2025-08-01 | JTD SIDING CONSTRUCTION LLC
245 Turkey Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-29 | 2025-07-29 | JTD SIDING CONSTRUCTION LLC
245 Turkey Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
245 Turkey Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-29 | 2025-07-29 | JTD SIDING CONSTRUCTION LLC
245 Turkey Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-27 | 2025-05-27
245 Turkey Ridge | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-29 | 2025-05-29
854 Edge of Auburn - Sterling | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
854 Edge of Auburn - Sterling | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
854 Edge of Auburn - Sterling | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
854 Edge of Auburn - Sterling | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
854 Edge of Auburn - Sterling | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-11 | 2025-08-11
854 Edge of Auburn - Sterling | Measurements | TRUE | 100 | Measured | 1 | 2025-05-08 | 2025-05-08
854 Edge of Auburn - Sterling | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-13 | 2025-08-13
854 Edge of Auburn - Sterling | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-08 | 2025-05-08
854 Edge of Auburn - Sterling | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-09 | 2025-05-09
95 Meadow @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-01 | 2025-07-01
95 Meadow @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-27 | 2025-06-27
95 Meadow @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-25 | 2025-06-25
95 Meadow @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
95 Meadow @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-17 | 2025-06-17 | Mendez Siding & Boxing LLC
95 Meadow @ Jones Dairy | Measurements | FALSE | 0 | Measured | 1 | 2025-08-07 | 2025-08-07
95 Meadow @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
95 Meadow @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-15 | 2025-04-15
95 Meadow @ Jones Dairy | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-15 | 2025-04-15
50 Little River | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-28 | 2025-08-28 | NC SIDING & REMODELING PRO LLC
50 Little River | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-05 | 2025-09-05
50 Little River | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-01 | 2025-09-01
50 Little River | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-28 | 2025-08-28 | NC SIDING & REMODELING PRO LLC
50 Little River | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-20 | 2025-08-20 | NC SIDING & REMODELING PRO LLC
50 Little River | Measurements | TRUE | 100 | Measured | 1 | 2025-08-26 | 2025-08-26 | NC SIDING & REMODELING PRO LLC
50 Little River | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-27 | 2025-08-27 | NC SIDING & REMODELING PRO LLC
50 Little River | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-18 | 2025-06-18
50 Little River | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-20 | 2025-06-20
37 Gardner Farms | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-09 | 2025-09-09
37 Gardner Farms | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-11 | 2025-09-11
37 Gardner Farms | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
37 Gardner Farms | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08 | Siding Boxing Construction [ARTURO]
37 Gardner Farms | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-04 | 2025-09-04 | Siding Boxing Construction [ARTURO]
37 Gardner Farms | Measurements | TRUE | 100 | Measured | 1 | 2025-07-22 | 2025-07-22
37 Gardner Farms | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-04 | 2025-09-04 | Siding Boxing Construction [ARTURO]
37 Gardner Farms | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-26 | 2025-06-26
37 Gardner Farms | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-26 | 2025-06-26
49 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-12 | 2025-09-12
49 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-11 | 2025-09-11
49 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
49 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
49 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-02 | 2025-09-02
49 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
49 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-02 | 2025-09-02
49 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-18 | 2025-06-18
49 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-19 | 2025-06-19
48 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-11 | 2025-09-11
48 Kipling Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
48 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05
48 Kipling Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
48 Kipling Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-23 | 2025-07-23
48 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
48 Kipling Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
48 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-08 | 2025-05-08
48 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-09 | 2025-05-09
47 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-24 | 2025-06-24
47 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-05 | 2025-08-05
47 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
47 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16
47 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-13 | 2025-06-13 | Hector Oliverio [Hector]
47 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-06-11 | 2025-06-11
47 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-11 | 2025-06-11
47 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
47 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
39 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-30 | 2025-05-30
39 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
39 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
39 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
39 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Hector Oliverio [Hector]
39 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
39 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20
39 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
39 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-06 | 2025-03-06
33 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-23 | 2025-06-23
33 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-05 | 2025-08-05
33 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
33 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
33 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-11 | 2025-06-11 | Hector Oliverio [Hector]
33 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-07-22 | 2025-07-22
33 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-11 | 2025-06-11
33 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-26 | 2025-03-26
33 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-28 | 2025-03-28
32 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-11 | 2025-09-11
32 Kipling Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
32 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05
32 Kipling Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
32 Kipling Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-23 | 2025-07-23
32 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
32 Kipling Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
32 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-07 | 2025-05-07
32 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-09 | 2025-05-09
30 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-11 | 2025-09-11
30 Kipling Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
30 Kipling Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05
30 Kipling Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
30 Kipling Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-23 | 2025-07-23
30 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
30 Kipling Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-23 | 2025-07-23
30 Kipling Creek | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-21 | 2025-05-21
30 Kipling Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-21 | 2025-05-21
21 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-30 | 2025-05-30
21 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
21 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
21 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
21 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Hector Oliverio [Hector]
21 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
21 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20
21 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-04 | 2025-03-04
21 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-06 | 2025-03-06
10 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
10 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-24 | 2025-06-24
10 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
10 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
10 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-05 | 2025-06-05 | Hector Oliverio [Hector]
10 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-07-22 | 2025-07-22
10 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05
10 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-20 | 2025-03-20
10 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
50 Elk Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
50 Elk Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
50 Elk Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
50 Elk Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
50 Elk Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-30 | 2025-07-30
50 Elk Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-09-19 | 2025-09-19
50 Elk Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-30 | 2025-07-30
50 Elk Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
50 Elk Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
137 Marin Woods | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-15 | 2025-09-15
137 Marin Woods | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-22 | 2025-09-22
137 Marin Woods | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
137 Marin Woods | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11 | Siding Boxing Construction [ARTURO]
137 Marin Woods | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-10 | 2025-09-10 | Siding Boxing Construction [ARTURO]
137 Marin Woods | Measurements | TRUE | 100 | Measured | 1 | 2025-08-07 | 2025-08-07
137 Marin Woods | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-10 | 2025-09-10 | Siding Boxing Construction [ARTURO]
137 Marin Woods | Ordered | TRUE | 100 | Ordered | 1 | 2025-07-09 | 2025-07-09
137 Marin Woods | Lien # | FALSE | 0 | Lien # | 1 | 2025-07-09 | 2025-07-09
85 Ashcroft | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
85 Ashcroft | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
85 Ashcroft | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
85 Ashcroft | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
85 Ashcroft | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
85 Ashcroft | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
85 Ashcroft | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
85 Ashcroft | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-15 | 2025-05-15
85 Ashcroft | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
86 Ashcroft | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-25 | 2025-08-25
86 Ashcroft | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-20 | 2025-08-20
86 Ashcroft | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-19 | 2025-08-19
86 Ashcroft | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-15 | 2025-08-15
86 Ashcroft | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-15 | 2025-08-15 | NC SIDING & REMODELING PRO LLC
86 Ashcroft | Measurements | TRUE | 100 | Measured | 1 | 2025-08-05 | 2025-08-05
86 Ashcroft | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-15 | 2025-08-15
86 Ashcroft | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-26 | 2025-05-26
86 Ashcroft | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-03 | 2025-06-03
96 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
96 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Lopez Painting Group Inc
84 Providence Oaks 40 | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
84 Providence Oaks 40 | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | MTR Painting LLC [Moises]
83 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
83 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | MTR Painting LLC [Moises]
80 Providence Oaks 40 | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
80 Providence Oaks 40 | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-30 | 2025-09-30 | MTR Painting LLC [Moises]
55 providence Oaks 40 | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
55 providence Oaks 40 | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
109 Providence Oaks 30 | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
109 Providence Oaks 30 | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
105 Providence Oaks 30 | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
105 Providence Oaks 30 | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | MTR Painting LLC [Moises]
100 Providence Oaks 30' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
100 Providence Oaks 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
98 Providence Oaks 30' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
98 Providence Oaks 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
97 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
97 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Lopez Painting Group Inc
99 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
99 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Lopez Painting Group Inc
21 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
21 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Lopez Painting Group Inc
50 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
50 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Lopez Painting Group Inc
49 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
49 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18 | Lopez Painting Group Inc
87 Ashcroft | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-25 | 2025-08-25
87 Ashcroft | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-20 | 2025-08-20
87 Ashcroft | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-19 | 2025-08-19
87 Ashcroft | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-15 | 2025-08-15
87 Ashcroft | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-15 | 2025-08-15 | NC SIDING & REMODELING PRO LLC
87 Ashcroft | Measurements | TRUE | 100 | Measured | 1 | 2025-08-05 | 2025-08-05
87 Ashcroft | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-15 | 2025-08-15
87 Ashcroft | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-26 | 2025-05-26
87 Ashcroft | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-03 | 2025-06-03
49 Elk Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-10 | 2025-09-10
49 Elk Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-08 | 2025-09-08
49 Elk Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
49 Elk Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
49 Elk Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-22 | 2025-07-22
49 Elk Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-09-19 | 2025-09-19
49 Elk Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-22 | 2025-07-22
49 Elk Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
49 Elk Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
30 Elk Creek | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-27 | 2025-08-27
30 Elk Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-22 | 2025-08-22
30 Elk Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
30 Elk Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-21 | 2025-08-21 | OCCZ Construction LLC
30 Elk Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-20 | 2025-08-20 | OCCZ Construction LLC
30 Elk Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-07-30 | 2025-07-30
30 Elk Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-20 | 2025-08-20 | OCCZ Construction LLC
30 Elk Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-28 | 2025-05-28
30 Elk Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-03 | 2025-06-03
25 Elk Creek | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-10 | 2025-09-10
25 Elk Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
25 Elk Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-05 | 2025-09-05
25 Elk Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03 | OCCZ Construction LLC
25 Elk Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-02 | 2025-09-02 | OCCZ Construction LLC
25 Elk Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-07-30 | 2025-07-30
25 Elk Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-02 | 2025-09-02 | OCCZ Construction LLC
25 Elk Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-17 | 2025-06-17
25 Elk Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-23 | 2025-06-23
155 Preserve @ Jones Dairy | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
155 Preserve @ Jones Dairy | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-31 | 2025-07-31 | MTR Painting LLC [Moises]
155 Preserve @ Jones Dairy | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-05 | 2025-08-05
155 Preserve @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-01 | 2025-08-01
155 Preserve @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-30 | 2025-07-30
155 Preserve @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
155 Preserve @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-25 | 2025-07-25 | H-Rojas Construction LLC [David]
155 Preserve @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-07-28 | 2025-07-28
155 Preserve @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
155 Preserve @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-23 | 2025-05-23
155 Preserve @ Jones Dairy | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-29 | 2025-05-29
348 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
348 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Lopez Painting Group Inc
74 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
74 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
74 Caitlin Crossing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
74 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
74 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
74 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
74 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
74 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-15 | 2025-05-15
74 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
4 OYL | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-27 | 2025-08-27
4 OYL | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-25 | 2025-08-25
4 OYL | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-21 | 2025-08-21
4 OYL | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-19 | 2025-08-19
4 OYL | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-08 | 2025-07-08
4 OYL | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
4 OYL | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
4 OYL | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
4 OYL | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
187 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-07 | 2025-05-07
187 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
187 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
187 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29 | Siding Express, LLC [Israel]
187 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
187 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
187 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
187 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-21 | 2025-03-21
187 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
111 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-29 | 2025-05-29
111 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-02 | 2025-06-02
111 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
111 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21 | Siding Express, LLC [Israel]
111 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Siding Express, LLC [Israel]
111 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
111 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Siding Express, LLC [Israel]
111 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-04 | 2025-03-04
111 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-04 | 2025-03-04
151 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
151 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-12 | 2025-06-12
151 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
151 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
151 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-03 | 2025-06-03 | Siding Express, LLC [Israel]
151 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-03 | 2025-06-03
151 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03 | Siding Express, LLC [Israel]
151 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-18 | 2025-03-18
151 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
246 Turkey Ridge | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
246 Turkey Ridge | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-08 | 2025-08-08 | Torres Painting Professional
246 Turkey Ridge | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
246 Turkey Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-30 | 2025-07-30
246 Turkey Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
246 Turkey Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-24 | 2025-07-24 | JTD SIDING CONSTRUCTION LLC
246 Turkey Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-22 | 2025-07-22 | JTD SIDING CONSTRUCTION LLC
246 Turkey Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
246 Turkey Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-22 | 2025-07-22 | JTD SIDING CONSTRUCTION LLC
246 Turkey Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-20 | 2025-05-20
246 Turkey Ridge | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-27 | 2025-05-27
186 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
186 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
186 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
186 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Siding Express, LLC [Israel]
186 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-29 | 2025-05-29 | Siding Express, LLC [Israel]
186 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-29 | 2025-05-29
186 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29 | Siding Express, LLC [Israel]
186 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
186 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-13 | 2025-03-13
307 S Elm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-20 | 2025-05-20
307 S Elm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
307 S Elm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-14 | 2025-05-14
307 S Elm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
307 S Elm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-09 | 2025-05-09 | Santiago Professional Siding [Santiago]
307 S Elm | Measurements | FALSE | 0 | Measured | 1 | 2025-07-04 | 2025-07-04
307 S Elm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-11 | 2025-03-11
307 S Elm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-07 | 2025-03-07
307 S Elm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-07 | 2025-03-07
126 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
126 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Torres Painting Professional
153 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-12 | 2025-06-12
153 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-12 | 2025-06-12
153 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06
153 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04 | Siding Express, LLC [Israel]
153 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | Siding Express, LLC [Israel]
153 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
153 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02 | Siding Express, LLC [Israel]
153 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
153 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-18 | 2025-03-18
126 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
126 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
126 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
126 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
126 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Delia Construction
126 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-08 | 2025-07-08
126 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
126 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-20 | 2025-03-20
126 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
125 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
125 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21 | Torres Painting Professional
125 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
125 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
125 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
125 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19 | Delia Construction
125 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Delia Construction
125 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-09 | 2025-07-09
125 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
125 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
125 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
106 Hickory Grove | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
106 Hickory Grove | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
106 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-30 | 2025-05-30
106 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
106 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
106 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Delia Construction
106 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21
106 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-08 | 2025-07-08
106 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
106 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-26 | 2025-03-26
106 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
104 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
104 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Torres Painting Professional
104 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
104 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
104 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
104 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
104 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-14 | 2025-05-14 | Delia Construction
104 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-09 | 2025-07-09
104 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
104 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
104 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-17 | 2025-03-17
199 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-06 | 2025-06-06
199 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-12 | 2025-06-12
199 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
199 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29 | Siding Express, LLC [Israel]
199 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-27 | 2025-05-27 | Siding Express, LLC [Israel]
199 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-27 | 2025-05-27
199 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27 | Siding Express, LLC [Israel]
199 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-11 | 2025-03-11
199 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-12 | 2025-03-12
89 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
89 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Torres Painting Professional
88 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
88 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Torres Painting Professional
80 Providence Oaks 40 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-05 | 2025-08-05
80 Providence Oaks 40 | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-29 | 2025-07-29
80 Providence Oaks 40 | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-30 | 2025-07-30
80 Providence Oaks 40 | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
80 Providence Oaks 40 | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-17 | 2025-07-17 | Delia Construction
80 Providence Oaks 40 | Measurements | FALSE | 0 | Measured | 1 | 2025-07-04 | 2025-07-04
80 Providence Oaks 40 | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-26 | 2025-05-26
80 Providence Oaks 40 | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-16 | 2025-05-16
80 Providence Oaks 40 | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-22 | 2025-05-22
55 providence Oaks 40 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
55 providence Oaks 40 | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-29 | 2025-09-29
55 providence Oaks 40 | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
55 providence Oaks 40 | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
55 providence Oaks 40 | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-12 | 2025-08-12
55 providence Oaks 40 | Measurements | FALSE | 0 | Measured | 1 | 2025-08-11 | 2025-08-11
55 providence Oaks 40 | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12
55 providence Oaks 40 | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-10 | 2025-06-10
55 providence Oaks 40 | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-10 | 2025-06-10
110 Providence Oaks 30 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
110 Providence Oaks 30 | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
110 Providence Oaks 30 | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
110 Providence Oaks 30 | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
110 Providence Oaks 30 | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
110 Providence Oaks 30 | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
110 Providence Oaks 30 | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
110 Providence Oaks 30 | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
110 Providence Oaks 30 | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
109 Providence Oaks 30 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
109 Providence Oaks 30 | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
109 Providence Oaks 30 | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
109 Providence Oaks 30 | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
109 Providence Oaks 30 | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-04 | 2025-08-04
109 Providence Oaks 30 | Measurements | FALSE | 0 | Measured | 1 | 2025-08-01 | 2025-08-01
109 Providence Oaks 30 | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
109 Providence Oaks 30 | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
109 Providence Oaks 30 | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
105 Providence Oaks 30 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
105 Providence Oaks 30 | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-19 | 2025-06-19
105 Providence Oaks 30 | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
105 Providence Oaks 30 | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
105 Providence Oaks 30 | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-13 | 2025-06-13 | Delia Construction
105 Providence Oaks 30 | Measurements | FALSE | 0 | Measured | 1 | 2025-07-15 | 2025-07-15
105 Providence Oaks 30 | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
105 Providence Oaks 30 | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-14 | 2025-04-14
105 Providence Oaks 30 | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-22 | 2025-04-22
378 Carolina Overlook | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-02 | 2025-10-02
378 Carolina Overlook | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
378 Carolina Overlook | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-26 | 2025-09-26
378 Carolina Overlook | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
378 Carolina Overlook | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-13 | 2025-08-13
378 Carolina Overlook | Measurements | FALSE | 0 | Measured | 1 | 2025-08-12 | 2025-08-12
378 Carolina Overlook | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-13 | 2025-06-13
378 Carolina Overlook | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-11 | 2025-06-11
378 Carolina Overlook | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-11 | 2025-06-11
314 Carolina Overlook | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
314 Carolina Overlook | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
314 Carolina Overlook | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
314 Carolina Overlook | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
314 Carolina Overlook | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
314 Carolina Overlook | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
314 Carolina Overlook | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
314 Carolina Overlook | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
314 Carolina Overlook | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
312 Carolina Overlook | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
312 Carolina Overlook | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
312 Carolina Overlook | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
312 Carolina Overlook | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
312 Carolina Overlook | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-05 | 2025-08-05
312 Carolina Overlook | Measurements | FALSE | 0 | Measured | 1 | 2025-08-04 | 2025-08-04
312 Carolina Overlook | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05
312 Carolina Overlook | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-03 | 2025-06-03
312 Carolina Overlook | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-03 | 2025-06-03
311 Carolina Overlook | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
311 Carolina Overlook | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
311 Carolina Overlook | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
311 Carolina Overlook | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
311 Carolina Overlook | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-04 | 2025-08-04
311 Carolina Overlook | Measurements | FALSE | 0 | Measured | 1 | 2025-08-01 | 2025-08-01
311 Carolina Overlook | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
311 Carolina Overlook | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
311 Carolina Overlook | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
106 Guin | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-15 | 2025-07-15
106 Guin | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-25 | 2025-08-25
106 Guin | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-09 | 2025-07-09
106 Guin | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-07 | 2025-07-07
106 Guin | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-03 | 2025-07-03 | Hector Oliverio [Hector]
106 Guin | Measurements | TRUE | 100 | Measured | 1 | 2025-07-02 | 2025-07-02
106 Guin | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-03 | 2025-07-03
106 Guin | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
106 Guin | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-01 | 2025-05-01
4 Rollins Acres | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
4 Rollins Acres | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
4 Rollins Acres | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
4 Rollins Acres | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
4 Rollins Acres | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Hector Oliverio [Hector]
4 Rollins Acres | Measurements | FALSE | 0 | Measured | 1 | 2025-07-02 | 2025-07-02
4 Rollins Acres | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
4 Rollins Acres | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-18 | 2025-03-18
4 Rollins Acres | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-18 | 2025-03-18
87 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
87 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Torres Painting Professional
86 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
86 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
85 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
85 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Torres Painting Professional
264 Turkey Ridge | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
264 Turkey Ridge | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02 | Torres Painting Professional
264 Turkey Ridge | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
264 Turkey Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-07 | 2025-08-07
264 Turkey Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
264 Turkey Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-01 | 2025-08-01 | JTD SIDING CONSTRUCTION LLC
264 Turkey Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-29 | 2025-07-29 | JTD SIDING CONSTRUCTION LLC
264 Turkey Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-07-21 | 2025-07-21
264 Turkey Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-29 | 2025-07-29
264 Turkey Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-27 | 2025-05-27
264 Turkey Ridge | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-27 | 2025-05-27
128 Pines at Wake Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
128 Pines at Wake Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-24 | 2025-06-24
128 Pines at Wake Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
128 Pines at Wake Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
128 Pines at Wake Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Wohlstand Construction LLC
128 Pines at Wake Crossing | Measurements | TRUE | 100 | Measured | 1 | 2025-05-01 | 2025-05-01
128 Pines at Wake Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
128 Pines at Wake Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-27 | 2025-02-27
128 Pines at Wake Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-27 | 2025-02-27
127 Pines at Wake Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
127 Pines at Wake Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
127 Pines at Wake Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
127 Pines at Wake Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
127 Pines at Wake Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-14 | 2025-05-14 | Wohlstand Construction LLC
127 Pines at Wake Crossing | Measurements | TRUE | 100 | Measured | 1 | 2025-05-01 | 2025-05-01
127 Pines at Wake Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
127 Pines at Wake Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
127 Pines at Wake Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-20 | 2025-02-20
159 Preserve @ Jones Dairy | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
159 Preserve @ Jones Dairy | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-10 | 2025-07-10 | MTR Painting LLC [Moises]
159 Preserve @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-11 | 2025-07-11
159 Preserve @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-11 | 2025-07-11
159 Preserve @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-09 | 2025-07-09
159 Preserve @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-07 | 2025-07-07
159 Preserve @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-03 | 2025-07-03 | H-Rojas Construction LLC [David]
159 Preserve @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-06-16 | 2025-06-16
159 Preserve @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
159 Preserve @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-01 | 2025-05-01
159 Preserve @ Jones Dairy | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
876 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
876 Edge of Auburn - | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-16 | 2025-07-16
876 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
876 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
876 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
876 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
876 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-30 | 2025-07-30
876 Edge of Auburn - | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-28 | 2025-05-28
876 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-28 | 2025-05-28
877 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
877 Edge of Auburn - | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
877 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
877 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
877 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
877 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
877 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
877 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
877 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
878 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
878 Edge of Auburn - | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-17 | 2025-07-17
878 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
878 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
878 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
878 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
878 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
878 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
878 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
845 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
845 Edge of Auburn - | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-12 | 2025-08-12
845 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
845 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
845 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
845 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
845 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
845 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
845 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
844 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
844 Edge of Auburn - | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
844 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
844 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
844 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
844 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
844 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
844 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
844 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
843 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
843 Edge of Auburn - | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
843 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
843 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
843 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
843 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
843 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
843 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
843 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
842 Edge of Auburn - | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
842 Edge of Auburn - | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-06 | 2025-08-06
842 Edge of Auburn - | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
842 Edge of Auburn - | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
842 Edge of Auburn - | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
842 Edge of Auburn - | Measurements | TRUE | 100 | Measured | 1 | 2025-04-30 | 2025-04-30
842 Edge of Auburn - | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
842 Edge of Auburn - | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-04 | 2025-06-04
842 Edge of Auburn - | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-04 | 2025-06-04
73 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
73 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-25 | 2025-07-25
73 Caitlin Crossing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
73 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
73 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
73 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-30 | 2025-07-30
73 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
73 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
73 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
103 Sagewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-20 | 2025-08-20
103 Sagewood | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-18 | 2025-08-18
103 Sagewood | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-14 | 2025-08-14
103 Sagewood | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-12 | 2025-08-12
103 Sagewood | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-01 | 2025-07-01
103 Sagewood | Measurements | FALSE | 0 | Measured | 1 | 2025-06-30 | 2025-06-30
103 Sagewood | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
103 Sagewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-29 | 2025-04-29
103 Sagewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-30 | 2025-04-30
158 Preserve @ Jones Dairy | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
158 Preserve @ Jones Dairy | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-10 | 2025-07-10 | MTR Painting LLC [Moises]
158 Preserve @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-15 | 2025-07-15
158 Preserve @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-11 | 2025-07-11
158 Preserve @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-09 | 2025-07-09
158 Preserve @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-07 | 2025-07-07
158 Preserve @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-03 | 2025-07-03 | H-Rojas Construction LLC [David]
158 Preserve @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
158 Preserve @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
158 Preserve @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-01 | 2025-05-01
158 Preserve @ Jones Dairy | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
777 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-16 | 2025-10-16
777 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
777 Edge of Auburn - Classic | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-10 | 2025-10-10
777 Edge of Auburn - Classic | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-08 | 2025-10-08
777 Edge of Auburn - Classic | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-27 | 2025-08-27
777 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-04-29 | 2025-04-29
777 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-27 | 2025-08-27
777 Edge of Auburn - Classic | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-25 | 2025-06-25
777 Edge of Auburn - Classic | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-25 | 2025-06-25
774 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-15 | 2025-08-15
774 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
774 Edge of Auburn - Classic | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-09 | 2025-07-09
774 Edge of Auburn - Classic | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-07 | 2025-07-07
774 Edge of Auburn - Classic | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-02 | 2025-07-02 | Jose Velasco Gaytan [Jimmy]
774 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-04-29 | 2025-04-29
774 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-02 | 2025-07-02
774 Edge of Auburn - Classic | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-28 | 2025-03-28
774 Edge of Auburn - Classic | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-28 | 2025-03-28
773 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-03 | 2025-10-03
773 Edge of Auburn - Classic | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
773 Edge of Auburn - Classic | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-29 | 2025-09-29
773 Edge of Auburn - Classic | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
773 Edge of Auburn - Classic | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-14 | 2025-08-14
773 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-04-29 | 2025-04-29
773 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-25 | 2025-07-25
773 Edge of Auburn - Classic | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-13 | 2025-05-13
773 Edge of Auburn - Classic | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-14 | 2025-05-14
12 Olivet | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
12 Olivet | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
12 Olivet | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
12 Olivet | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
12 Olivet | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | Solid Seal Siding LLC
12 Olivet | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
12 Olivet | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-02 | 2025-04-02
12 Olivet | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
12 Olivet | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
86 Carolina Landing | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-16 | 2025-09-16 | Requena Siding [Jairo]
86 Carolina Landing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-23 | 2025-09-23
86 Carolina Landing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
86 Carolina Landing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16 | Requena Siding [Jairo]
86 Carolina Landing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-10 | 2025-09-10 | Requena Siding [Jairo]
86 Carolina Landing | Measurements | TRUE | 100 | Measured | 1 | 2025-09-15 | 2025-09-15 | Requena Siding [Jairo]
86 Carolina Landing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-15 | 2025-09-15 | Requena Siding [Jairo]
86 Carolina Landing | Ordered | TRUE | 100 | Ordered | 1 | 2025-07-09 | 2025-07-09
86 Carolina Landing | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-09 | 2025-07-09
50 OYL | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-23 | 2025-05-23
50 OYL | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
50 OYL | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
50 OYL | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
50 OYL | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-13 | 2025-05-13 | Leones Construction LLC
50 OYL | Measurements | FALSE | 0 | Measured | 1 | 2025-06-27 | 2025-06-27
50 OYL | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-26 | 2025-03-26
50 OYL | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-11 | 2025-03-11
50 OYL | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-12 | 2025-03-12
48 Little River | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-28 | 2025-08-28 | New World Siding Construction Inc.,NC SIDING & REMODELING PRO LLC
48 Little River | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-23 | 2025-09-23
48 Little River | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-01 | 2025-09-01
48 Little River | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-28 | 2025-08-28 | New World Siding Construction Inc.,NC SIDING & REMODELING PRO LLC
48 Little River | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-20 | 2025-08-20 | New World Siding Construction Inc.
48 Little River | Measurements | TRUE | 100 | Measured | 1 | 2025-08-26 | 2025-08-26 | New World Siding Construction Inc.
48 Little River | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-26 | 2025-08-26 | New World Siding Construction Inc.
48 Little River | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-18 | 2025-06-18
48 Little River | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-19 | 2025-06-19
78 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
78 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
77 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
77 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
5 Regency @ Olde Towne | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
5 Regency @ Olde Towne | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
72 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
72 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
72 Caitlin Crossing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
72 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-09 | 2025-09-09
72 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-29 | 2025-07-29
72 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-28 | 2025-07-28
72 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
72 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-30 | 2025-04-30
72 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
46 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
46 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
46 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
46 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03 | Torres Painting Professional
45 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
45 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03 | Torres Painting Professional
45 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
45 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
44 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
44 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
44 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
44 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
41 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
41 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
41 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
41 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12 | Torres Painting Professional
40 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
40 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12 | Torres Painting Professional
40 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
40 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
39 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
39 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13 | Torres Painting Professional
39 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
39 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
36 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
36 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
35 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
35 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
34 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
34 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
33 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
33 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
30 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
30 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
29 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
29 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
28 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
28 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
27 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
27 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
24 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
24 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
23 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
23 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
22 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
22 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
26 Walnut Hall | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
26 Walnut Hall | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-01 | 2025-08-01 | Chay Morales Painting [Javier]
26 Walnut Hall | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-13 | 2025-05-13
26 Walnut Hall | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
26 Walnut Hall | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
26 Walnut Hall | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
26 Walnut Hall | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-30 | 2025-04-30 | Siding Pro Service LLC
26 Walnut Hall | Measurements | FALSE | 0 | Measured | 1 | 2025-05-02 | 2025-05-02
26 Walnut Hall | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-28 | 2025-02-28
26 Walnut Hall | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-25 | 2025-02-25
26 Walnut Hall | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-25 | 2025-02-25
21 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
21 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
18 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
18 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
17 Stanat Place TH | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
17 Stanat Place TH | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
16 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
16 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
13 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
13 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
12 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
12 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
11 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
11 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
8 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
8 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06 | Khanh Nguyen
7 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
7 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03 | Khanh Nguyen
6 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
6 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03 | Khanh Nguyen
3 Stanat Place TH | Paid Trellis | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
3 Stanat Place TH | Trellis Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04 | Khanh Nguyen
85 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
85 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
85 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
85 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10
85 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
85 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
85 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
85 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-03 | 2025-04-03
85 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
86 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
86 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
86 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
86 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Jimenez Services
86 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
86 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
86 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
86 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-03 | 2025-04-03
86 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
87 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
87 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
87 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
87 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Jimenez Services
87 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
87 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
87 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
87 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-03 | 2025-04-03
87 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
88 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
88 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
88 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
88 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Jimenez Services
88 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
88 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
88 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
88 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-04 | 2025-04-04
88 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-08 | 2025-04-08
89 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
89 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
89 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
89 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Jimenez Services
89 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
89 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
89 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
89 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-04 | 2025-04-04
89 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
90 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
90 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
90 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
90 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Jimenez Services
90 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
90 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
90 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04 | Jimenez Services
90 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-02 | 2025-04-02
90 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
159 Auburn Station | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
159 Auburn Station | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
159 Auburn Station | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
159 Auburn Station | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
159 Auburn Station | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
159 Auburn Station | Measurements | TRUE | 100 | Measured | 1 | 2025-04-23 | 2025-04-23
159 Auburn Station | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-01 | 2025-08-01
159 Auburn Station | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-30 | 2025-05-30
159 Auburn Station | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-30 | 2025-05-30
5 Auburn Station | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
5 Auburn Station | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
5 Auburn Station | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
5 Auburn Station | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
5 Auburn Station | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
5 Auburn Station | Measurements | TRUE | 100 | Measured | 1 | 2025-04-23 | 2025-04-23
5 Auburn Station | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-01 | 2025-08-01
5 Auburn Station | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-30 | 2025-05-30
5 Auburn Station | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-30 | 2025-05-30
16 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-01 | 2025-07-01
16 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
16 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-25 | 2025-06-25
16 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
16 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-19 | 2025-06-19 | Hector Oliverio [Hector]
16 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-23 | 2025-07-23
16 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-19 | 2025-06-19
16 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
16 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
771 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-23 | 2025-07-23
771 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
771 Edge of Auburn - Classic | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
771 Edge of Auburn - Classic | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
771 Edge of Auburn - Classic | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-13 | 2025-06-13 | Jose Velasco Gaytan [Jimmy]
771 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-04-23 | 2025-04-23
771 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-13 | 2025-06-13
771 Edge of Auburn - Classic | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-20 | 2025-03-20
771 Edge of Auburn - Classic | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
46 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
46 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
18 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
18 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
197 Falls Village | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-25 | 2025-08-25
197 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-26 | 2025-08-26
197 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
197 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Siding Express, LLC [Israel]
197 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-06 | 2025-06-06 | Siding Express, LLC [Israel]
197 Falls Village | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
197 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
197 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-24 | 2025-02-24
197 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-26 | 2025-02-26
179 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
179 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
179 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
179 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24 | Siding Express, LLC [Israel]
179 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
179 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-20 | 2025-06-20
179 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-20 | 2025-06-20 | Siding Express, LLC [Israel]
179 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
179 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-18 | 2025-03-18
158 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-24 | 2025-06-24
158 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
158 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
158 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | Siding Express, LLC [Israel]
158 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-13 | 2025-06-13 | Siding Express, LLC [Israel]
158 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-13 | 2025-06-13
158 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-13 | 2025-06-13 | Siding Express, LLC [Israel]
158 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-27 | 2025-03-27
158 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
155 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-08 | 2025-07-08
155 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-02 | 2025-07-02
155 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02
155 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30 | Siding Express, LLC [Israel]
155 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-27 | 2025-06-27 | Siding Express, LLC [Israel]
155 Falls Village | Measurements | FALSE | 0 | Measured | 1 | 2025-07-23 | 2025-07-23
155 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-27 | 2025-06-27 | Siding Express, LLC [Israel]
155 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-28 | 2025-03-28
155 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
84 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
84 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-29 | 2025-09-29
84 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
84 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
84 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-22 | 2025-09-22 | Rodriguez Contracting LLC [Hemeny]
84 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-07-15 | 2025-07-15
84 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-22 | 2025-09-22
84 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-30 | 2025-06-30
84 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-17 | 2025-07-17
83 Summer Place | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-10 | 2025-09-10
83 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-10 | 2025-09-10
83 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
83 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
83 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-03 | 2025-09-03 | Rodriguez Contracting LLC [Hemeny]
83 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-08-12 | 2025-08-12
83 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-03 | 2025-09-03
83 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-07-04 | 2025-07-04
83 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-04 | 2025-07-04
82 Summer Place | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-02 | 2025-09-02
82 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-23 | 2025-09-23
82 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
82 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
82 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-25 | 2025-08-25 | Rodriguez Contracting LLC [Hemeny]
82 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
82 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-25 | 2025-08-25
82 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-25 | 2025-06-25
82 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-26 | 2025-06-26
78 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
78 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-02 | 2025-07-02
78 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
78 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24
78 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-24 | 2025-06-24 | La Culebra Siding & Windows LLC
78 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-06-10 | 2025-06-10
78 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
78 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
78 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-25 | 2025-04-25
77 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
77 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-02 | 2025-07-02
77 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
77 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24
77 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-24 | 2025-06-24 | La Culebra Siding & Windows LLC
77 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
77 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05
77 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
77 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-25 | 2025-04-25
76 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-25 | 2025-06-25
76 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
76 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
76 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
76 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-17 | 2025-06-17 | La Culebra Siding & Windows LLC
76 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-06-10 | 2025-06-10
76 Summer Place | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-04 | 2025-04-04
76 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-28 | 2025-03-28
76 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
75 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-25 | 2025-06-25
75 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
75 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
75 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
75 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-17 | 2025-06-17 | La Culebra Siding & Windows LLC
75 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-06-06 | 2025-06-06
75 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-26 | 2025-05-26
75 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-09 | 2025-04-09
75 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-09 | 2025-04-09
15 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-10 | 2025-09-10
15 Caitlin Crossing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-08 | 2025-09-08
15 Caitlin Crossing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04
15 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-02 | 2025-09-02
15 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-22 | 2025-07-22
15 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-21 | 2025-07-21
15 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
15 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-21 | 2025-04-21
15 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-30 | 2025-04-30
81 Sorrell Oaks | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-16 | 2025-06-16
81 Sorrell Oaks | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
81 Sorrell Oaks | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10
81 Sorrell Oaks | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06
81 Sorrell Oaks | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | J&A Construction
81 Sorrell Oaks | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
81 Sorrell Oaks | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
81 Sorrell Oaks | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
81 Sorrell Oaks | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-03 | 2025-04-03
92 Finley Landing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
92 Finley Landing TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
92 Finley Landing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
92 Finley Landing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
92 Finley Landing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-24 | 2025-06-24
92 Finley Landing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
92 Finley Landing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24
92 Finley Landing TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-22 | 2025-04-22
92 Finley Landing TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-22 | 2025-04-22
91 Finley Landing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
91 Finley Landing TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
91 Finley Landing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
91 Finley Landing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
91 Finley Landing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-24 | 2025-06-24
91 Finley Landing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
91 Finley Landing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-04 | 2025-08-04
91 Finley Landing TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-29 | 2025-05-29
91 Finley Landing TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-02 | 2025-06-02
90 Finley Landing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
90 Finley Landing TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
90 Finley Landing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
90 Finley Landing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
90 Finley Landing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-24 | 2025-06-24
90 Finley Landing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
90 Finley Landing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-04 | 2025-08-04
90 Finley Landing TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-28 | 2025-05-28
90 Finley Landing TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-02 | 2025-06-02
89 Finley Landing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
89 Finley Landing TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
89 Finley Landing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
89 Finley Landing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
89 Finley Landing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-24 | 2025-06-24
89 Finley Landing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
89 Finley Landing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-04 | 2025-08-04
89 Finley Landing TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-28 | 2025-05-28
89 Finley Landing TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-02 | 2025-06-02
88 Finley Landing TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
88 Finley Landing TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
88 Finley Landing TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
88 Finley Landing TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-05 | 2025-08-05
88 Finley Landing TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-24 | 2025-06-24
88 Finley Landing TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
88 Finley Landing TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-04 | 2025-08-04
88 Finley Landing TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-28 | 2025-05-28
88 Finley Landing TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-02 | 2025-06-02
123 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
123 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21 | Torres Painting Professional
123 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-08 | 2025-05-08
123 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
123 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
123 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30 | Mendez Siding & Boxing LLC
123 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Mendez Siding & Boxing LLC
123 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-06-18 | 2025-06-18
123 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28 | Mendez Siding & Boxing LLC
123 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
123 Hickory Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-21 | 2025-02-21
124 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
124 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21 | Torres Painting Professional
124 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-08 | 2025-05-08
124 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 38 | 2025-05-06 | 2025-06-26
124 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
124 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30 | Mendez Siding & Boxing LLC
124 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Mendez Siding & Boxing LLC
124 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-06-17 | 2025-06-17
124 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28 | Mendez Siding & Boxing LLC
124 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-27 | 2025-02-27
124 Hickory Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-27 | 2025-02-27
16 Carolina Overlook Twin Villas | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
16 Carolina Overlook Twin Villas | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18 | Torres Painting Professional
146 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
146 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Torres Painting Professional
710 Glascock | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-22 | 2025-08-22
710 Glascock | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-17 | 2025-07-17
710 Glascock | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-16 | 2025-07-16
710 Glascock | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-14 | 2025-07-14
710 Glascock | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-08 | 2025-07-08 | Santiago Professional Siding [Santiago]
710 Glascock | Measurements | TRUE | 100 | Measured | 1 | 2025-06-17 | 2025-06-17
710 Glascock | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-08 | 2025-07-08
710 Glascock | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
710 Glascock | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-09 | 2025-05-09
134 Athens Acres | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-21 | 2025-08-21
134 Athens Acres | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-19 | 2025-08-19
134 Athens Acres | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-15 | 2025-08-15
134 Athens Acres | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-13 | 2025-08-13
134 Athens Acres | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-02 | 2025-07-02
134 Athens Acres | Measurements | FALSE | 0 | Measured | 1 | 2025-07-01 | 2025-07-01
134 Athens Acres | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
134 Athens Acres | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-14 | 2025-05-14
134 Athens Acres | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-14 | 2025-05-14
111 Annandale | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
111 Annandale | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-24 | 2025-07-24
111 Annandale | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
111 Annandale | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-24 | 2025-07-24 | JTD SIDING CONSTRUCTION LLC
111 Annandale | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-22 | 2025-07-22 | JTD SIDING CONSTRUCTION LLC
111 Annandale | Measurements | TRUE | 100 | Measured | 1 | 2025-06-04 | 2025-06-04
111 Annandale | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-22 | 2025-07-22 | JTD SIDING CONSTRUCTION LLC
111 Annandale | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
111 Annandale | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-14 | 2025-05-14
192 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-23 | 2025-06-23
192 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
192 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
192 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13 | Siding Express, LLC [Israel]
192 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
192 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
192 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
192 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
192 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-25 | 2025-03-25
200 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
200 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
200 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
200 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Siding Express, LLC [Israel]
200 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
200 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
200 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05 | Siding Express, LLC [Israel]
200 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-26 | 2025-03-26
200 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-27 | 2025-03-27
191 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
191 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
191 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
191 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Siding Express, LLC [Israel]
191 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-22 | 2025-05-22 | Siding Express, LLC [Israel]
191 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-22 | 2025-05-22
191 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-22 | 2025-05-22 | Siding Express, LLC [Israel]
191 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
191 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
14 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-05 | 2025-09-05
14 Caitlin Crossing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-03 | 2025-09-03
14 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-01 | 2025-09-01
14 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-28 | 2025-08-28
14 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-17 | 2025-07-17
14 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-16 | 2025-07-16
14 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
14 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-21 | 2025-04-21
14 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-30 | 2025-04-30
17 Carolina Overlook Twin Villas | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
17 Carolina Overlook Twin Villas | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18 | Torres Painting Professional
155 Chavis | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
155 Chavis | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
155 Chavis | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
155 Chavis | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
155 Chavis | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-29 | 2025-05-29 | Hector Oliverio [Hector]
155 Chavis | Measurements | FALSE | 0 | Measured | 1 | 2025-06-16 | 2025-06-16
155 Chavis | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
155 Chavis | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-27 | 2025-03-27
155 Chavis | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-27 | 2025-03-27
13 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-03 | 2025-09-03
13 Caitlin Crossing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-01 | 2025-09-01
13 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-28 | 2025-08-28
13 Caitlin Crossing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-26 | 2025-08-26
13 Caitlin Crossing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-15 | 2025-07-15
13 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-14 | 2025-07-14
13 Caitlin Crossing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
13 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-17 | 2025-04-17
13 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-30 | 2025-04-30
20 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
20 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
20 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
20 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
20 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-04 | 2025-06-04 | Hector Oliverio [Hector]
20 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-07-10 | 2025-07-10
20 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
20 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-24 | 2025-03-24
20 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
20 Auburn Station | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
20 Auburn Station | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
20 Auburn Station | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
20 Auburn Station | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
20 Auburn Station | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
20 Auburn Station | Measurements | TRUE | 100 | Measured | 1 | 2025-04-14 | 2025-04-14
20 Auburn Station | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-31 | 2025-07-31
20 Auburn Station | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-29 | 2025-05-29
20 Auburn Station | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-29 | 2025-05-29
41 Gardner Farms | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
41 Gardner Farms | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
41 Gardner Farms | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24
41 Gardner Farms | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-20 | 2025-06-20 | Siding Boxing Construction [ARTURO]
41 Gardner Farms | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-19 | 2025-06-19 | Siding Boxing Construction [ARTURO]
41 Gardner Farms | Measurements | TRUE | 100 | Measured | 1 | 2025-05-29 | 2025-05-29
41 Gardner Farms | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-19 | 2025-06-19 | Siding Boxing Construction [ARTURO]
41 Gardner Farms | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-03 | 2025-04-03
41 Gardner Farms | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-10 | 2025-04-10
4517 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
4517 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
4517 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
4517 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
4517 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | Delia Construction
4517 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
4517 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
4517 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
4517 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-07 | 2025-04-07
157 Preserve @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
157 Preserve @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-13 | 2025-06-13
157 Preserve @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
157 Preserve @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
157 Preserve @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-06 | 2025-06-06 | Mendez Siding & Boxing LLC
157 Preserve @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-05-13 | 2025-05-13
157 Preserve @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-15 | 2025-04-15
157 Preserve @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-04 | 2025-04-04
157 Preserve @ Jones Dairy | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-11 | 2025-04-11
190 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
190 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-02 | 2025-06-02
190 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
190 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Siding Express, LLC [Israel]
190 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-23 | 2025-05-23 | Siding Express, LLC [Israel]
190 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-23 | 2025-05-23
190 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23 | Siding Express, LLC [Israel]
190 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-07 | 2025-03-07
190 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
63 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
63 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Torres Painting Professional
62 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
62 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Torres Painting Professional
61 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
61 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Torres Painting Professional
76 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
76 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Torres Painting Professional
168 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
168 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11 | Torres Painting Professional
168 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
168 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
168 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
168 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
168 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-29 | 2025-05-29 | JO Brothers [Richard]
168 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-05-29 | 2025-05-29
168 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
168 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
168 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
189 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
189 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
189 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
189 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Siding Express, LLC [Israel]
189 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-08 | 2025-05-08 | Siding Express, LLC [Israel]
189 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-08 | 2025-05-08
189 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-08 | 2025-05-08 | Siding Express, LLC [Israel]
189 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
189 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
83 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
83 Stonewood | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
83 Stonewood | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
83 Stonewood | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
83 Stonewood | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-04 | 2025-08-04
83 Stonewood | Measurements | FALSE | 0 | Measured | 1 | 2025-08-01 | 2025-08-01
83 Stonewood | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
83 Stonewood | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
83 Stonewood | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
161 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-09 | 2025-07-09
161 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-07 | 2025-07-07
161 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-03 | 2025-07-03
161 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01 | Santiago Professional Siding [Santiago]
161 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-26 | 2025-06-26 | Santiago Professional Siding [Santiago]
161 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-07-17 | 2025-07-17
161 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-27 | 2025-06-27 | Santiago Professional Siding [Santiago]
161 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
161 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-24 | 2025-04-24
4518 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
4518 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
4518 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
4518 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
4518 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | Delia Construction
4518 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
4518 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
4518 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
4518 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-09 | 2025-04-09
110 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-16 | 2025-05-16
110 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
110 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
110 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08 | Siding Express, LLC [Israel]
110 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
110 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-07 | 2025-05-07
110 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
110 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
110 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-24 | 2025-02-24
152 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
152 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
152 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
152 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Siding Express, LLC [Israel]
152 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | Siding Express, LLC [Israel]
152 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-01 | 2025-05-01
152 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01 | Siding Express, LLC [Israel]
152 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-13 | 2025-02-13
152 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-25 | 2025-02-25
381 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-05 | 2025-08-05
381 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-29 | 2025-07-29
381 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-30 | 2025-07-30
381 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
381 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-26 | 2025-06-26 | JO Brothers [Richard]
381 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-06-13 | 2025-06-13
381 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-26 | 2025-06-26
381 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
381 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-06 | 2025-05-06
83 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-06 | 2025-06-06
83 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-03 | 2025-06-03
83 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
83 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29
83 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-27 | 2025-05-27 | Delia Construction
83 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-07-03 | 2025-07-03
83 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28
83 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
83 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
96 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
96 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
96 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
96 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
96 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Delia Construction
96 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-07-02 | 2025-07-02
96 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31
96 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
96 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
89 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
89 River Glen | Invoiced | TRUE | 100 | Close Out | 4 | 2025-05-23 | 2025-05-28
89 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
89 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
89 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Jesus Construction
89 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-20 | 2025-06-20
89 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
89 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-02 | 2025-04-02
89 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-07 | 2025-04-07
88 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
88 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
88 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
88 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
88 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-14 | 2025-05-14 | Jesus Construction
88 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-17 | 2025-06-17
88 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
88 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-02 | 2025-04-02
88 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
136 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
136 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
136 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
136 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
136 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-22 | 2025-05-22 | Jesus Construction
136 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-13 | 2025-06-13
136 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-22 | 2025-05-22
136 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-20 | 2025-03-20
136 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
79 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
79 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Lopez Painting Group Inc
59 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
59 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04 | Torres Painting Professional
85 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
85 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01 | Lopez Painting Group Inc
78 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
78 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30 | Lopez Painting Group Inc
107 Annandale | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22
107 Annandale | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16 | Torres Painting Professional
107 Annandale | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-13 | 2025-10-13
107 Annandale | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-08 | 2025-09-08
107 Annandale | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
107 Annandale | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-04 | 2025-09-04 | Santiago Professional Siding [Santiago]
107 Annandale | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-26 | 2025-08-26 | Santiago Professional Siding [Santiago]
107 Annandale | Measurements | TRUE | 100 | Measured | 1 | 2025-06-18 | 2025-06-18
107 Annandale | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-26 | 2025-08-26 | Santiago Professional Siding [Santiago]
107 Annandale | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-10 | 2025-06-10
107 Annandale | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-24 | 2025-06-24
30 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
30 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
27 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
27 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
26 Williams Grove | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
26 Williams Grove | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
16 Williams Grove | Paid Screen Porch | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
16 Williams Grove | Screen Porch Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Screen Builders, Inc.
111 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07
111 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Torres Painting Professional
111 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-10 | 2025-06-10
111 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
111 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
111 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
111 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-22 | 2025-05-22 | JO Brothers [Richard]
111 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-05-22 | 2025-05-22
111 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
111 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-01 | 2025-04-01
111 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-07 | 2025-04-07
9 Harvest Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-06 | 2025-06-06
9 Harvest Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-23 | 2025-06-23
9 Harvest Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
9 Harvest Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29 | NC SIDING & REMODELING PRO LLC
9 Harvest Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-28 | 2025-05-28 | NC SIDING & REMODELING PRO LLC
9 Harvest Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-05-29 | 2025-05-29 | NC SIDING & REMODELING PRO LLC
9 Harvest Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29 | NC SIDING & REMODELING PRO LLC
9 Harvest Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-12 | 2025-03-12
9 Harvest Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-28 | 2025-03-28
175 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
175 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
175 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
175 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Requena Siding [Jairo]
175 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Requena Siding [Jairo]
175 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22 | Requena Siding [Jairo]
175 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Requena Siding [Jairo]
175 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-04 | 2025-02-04
175 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-20 | 2025-02-20
59 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-29 | 2025-09-29
59 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
59 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
59 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
59 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-08 | 2025-08-08
59 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-08-07 | 2025-08-07
59 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-10 | 2025-06-10
59 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-06 | 2025-06-06
59 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-06 | 2025-06-06
61 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
61 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
61 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
61 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
61 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
61 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
61 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
61 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
61 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
46 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
46 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
46 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
46 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
46 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
46 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
46 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
46 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
46 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
86 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-23 | 2025-07-23
86 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-21 | 2025-07-21
86 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-17 | 2025-07-17
86 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-15 | 2025-07-15 | Santiago Professional Siding [Santiago]
86 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-11 | 2025-07-11 | Santiago Professional Siding [Santiago]
86 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-07-04 | 2025-07-04
86 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-11 | 2025-07-11 | Santiago Professional Siding [Santiago]
86 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
86 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-16 | 2025-05-16
110 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
110 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15 | Torres Painting Professional
137 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-04 | 2025-06-04
137 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
137 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29
137 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
137 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-23 | 2025-05-23 | Jesus Construction
137 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-30 | 2025-05-30
137 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23
137 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
137 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-02 | 2025-05-02
764 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-12 | 2025-08-12
764 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-04 | 2025-06-04
764 Edge of Auburn - Classic | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
764 Edge of Auburn - Classic | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
764 Edge of Auburn - Classic | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-28 | 2025-05-28 | Jose Velasco Gaytan [Jimmy]
764 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
764 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-28 | 2025-05-28
764 Edge of Auburn - Classic | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
764 Edge of Auburn - Classic | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-13 | 2025-02-13
94 Stonewood | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
94 Stonewood | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
93 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
93 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
92 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
92 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Torres Painting Professional
91 Stonewood | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
91 Stonewood | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
90 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
90 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29 | Torres Painting Professional
89 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
89 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29 | Torres Painting Professional
88 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
88 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
87 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
87 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10 | Torres Painting Professional
75 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
75 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
74 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
74 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
72 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
72 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04 | Torres Painting Professional
71 Stonewood | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
71 Stonewood | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
172 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
172 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
165 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
165 Stonewood | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
164 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
164 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30 | Torres Painting Professional
163 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
163 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30 | Torres Painting Professional
73 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
73 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
17 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
17 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-23 | 2025-05-23
17 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
17 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
17 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-14 | 2025-05-14 | Hector Oliverio [Hector]
17 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-26 | 2025-06-26
17 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
17 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
17 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-06 | 2025-03-06
175 Walton Farms PH2 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-24 | 2025-06-24
175 Walton Farms PH2 | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
175 Walton Farms PH2 | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
175 Walton Farms PH2 | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16
175 Walton Farms PH2 | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | Bladimir Garcia Alcantara / E.A.B.
175 Walton Farms PH2 | Measurements | TRUE | 100 | Measured | 1 | 2025-06-12 | 2025-06-12
175 Walton Farms PH2 | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-26 | 2025-06-26
175 Walton Farms PH2 | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-10 | 2025-04-10
175 Walton Farms PH2 | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
196 Annandale | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-15 | 2025-08-15
196 Annandale | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-13 | 2025-08-13
196 Annandale | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-11 | 2025-08-11
196 Annandale | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-07 | 2025-08-07
196 Annandale | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-26 | 2025-06-26
196 Annandale | Measurements | FALSE | 0 | Measured | 1 | 2025-06-25 | 2025-06-25
196 Annandale | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-27 | 2025-06-27
196 Annandale | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-24 | 2025-04-24
196 Annandale | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-24 | 2025-04-24
185 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-16 | 2025-05-16
185 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
185 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
185 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08 | Siding Express, LLC [Israel]
185 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
185 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-07 | 2025-05-07
185 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
185 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
185 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-27 | 2025-02-27
195 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
195 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
195 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
195 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19 | Siding Express, LLC [Israel]
195 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Siding Express, LLC [Israel]
195 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-16 | 2025-05-16
195 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16 | Siding Express, LLC [Israel]
195 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-26 | 2025-02-26
195 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-11 | 2025-03-11
198 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
198 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
198 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
198 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | Siding Express, LLC [Israel]
198 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-14 | 2025-05-14 | Siding Express, LLC [Israel]
198 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
198 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14 | Siding Express, LLC [Israel]
198 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-25 | 2025-02-25
198 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-07 | 2025-03-07
188 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
188 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
188 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
188 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Siding Express, LLC [Israel]
188 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | Siding Express, LLC [Israel]
188 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-01 | 2025-05-01
188 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01 | Siding Express, LLC [Israel]
188 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
188 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-21 | 2025-02-21
114 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-07 | 2025-05-07
114 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
114 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
114 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29 | Siding Express, LLC [Israel]
114 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Siding Express, LLC [Israel]
114 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-28 | 2025-04-28
114 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28 | Siding Express, LLC [Israel]
114 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-04 | 2025-02-04
114 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-18 | 2025-02-18
113 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
113 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
113 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
113 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Daniel's Construction & Repair [Roger]
113 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-08 | 2025-05-08 | Daniel's Construction & Repair [Roger]
113 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-08 | 2025-05-08
113 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-08 | 2025-05-08 | Daniel's Construction & Repair [Roger]
113 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
113 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-28 | 2025-02-28
112 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-16 | 2025-05-16
112 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
112 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
112 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08 | Daniel's Construction & Repair [Roger]
112 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | Daniel's Construction & Repair [Roger]
112 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-25 | 2025-04-25
112 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
112 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-18 | 2025-02-18
112 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-28 | 2025-02-28
108 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
108 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
108 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
108 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01 | Siding Express, LLC [Israel]
108 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-29 | 2025-04-29 | Siding Express, LLC [Israel]
108 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-29 | 2025-04-29
108 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29 | Siding Express, LLC [Israel]
108 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
108 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-20 | 2025-02-20
107 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
107 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-20 | 2025-05-20
107 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
107 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Siding Express, LLC [Israel]
107 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-06 | 2025-05-06 | Siding Express, LLC [Israel]
107 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-05-06 | 2025-05-06
107 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06 | Siding Express, LLC [Israel]
107 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-18 | 2025-02-18
107 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-27 | 2025-02-27
18 Olivet | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-08 | 2025-05-08
18 Olivet | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-09 | 2025-05-09
18 Olivet | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
18 Olivet | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
18 Olivet | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | Avery Siding LLC
18 Olivet | Measurements | TRUE | 100 | Measured | 1 | 2025-04-04 | 2025-04-04
18 Olivet | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18
18 Olivet | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-28 | 2025-02-28
18 Olivet | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-14 | 2025-02-14
110 Carolina Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-25 | 2025-07-25
110 Carolina Landing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
110 Carolina Landing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-21 | 2025-07-21
110 Carolina Landing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-17 | 2025-07-17 | Requena Siding [Jairo]
110 Carolina Landing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-11 | 2025-07-11 | Requena Siding [Jairo]
110 Carolina Landing | Measurements | TRUE | 100 | Measured | 1 | 2025-07-15 | 2025-07-15 | Requena Siding [Jairo]
110 Carolina Landing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-15 | 2025-07-15 | Requena Siding [Jairo]
110 Carolina Landing | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
110 Carolina Landing | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-02 | 2025-06-02
109 Carolina Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-08 | 2025-07-08
109 Carolina Landing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-14 | 2025-07-14
109 Carolina Landing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02
109 Carolina Landing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30 | Requena Siding [Jairo]
109 Carolina Landing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-24 | 2025-06-24 | Requena Siding [Jairo]
109 Carolina Landing | Measurements | TRUE | 100 | Measured | 1 | 2025-06-25 | 2025-06-25 | Requena Siding [Jairo]
109 Carolina Landing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-24 | 2025-06-24 | Requena Siding [Jairo]
109 Carolina Landing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-22 | 2025-04-22
109 Carolina Landing | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-16 | 2025-05-16
91 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
91 Providence Oaks 40' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Lopez Painting Group Inc
5 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
5 Providence Oaks 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
2 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
2 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Lopez Painting Group Inc
134 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
134 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
134 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
134 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
134 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | Jesus Construction
134 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-09 | 2025-06-09
134 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-07 | 2025-05-07
134 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
134 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-08 | 2025-04-08
135 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-30 | 2025-05-30
135 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
135 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
135 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
135 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Jesus Construction
135 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-10 | 2025-06-10
135 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
135 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
135 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-21 | 2025-04-21
163 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-09 | 2025-07-09
163 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-07 | 2025-07-07
163 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-03 | 2025-07-03
163 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-01 | 2025-07-01 | Santiago Professional Siding [Santiago]
163 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-27 | 2025-06-27 | Santiago Professional Siding [Santiago]
163 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-06-27 | 2025-06-27
163 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-27 | 2025-06-27 | Santiago Professional Siding [Santiago]
163 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-25 | 2025-04-25
163 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-25 | 2025-04-25
164 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-24 | 2025-06-24
164 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-20 | 2025-06-20
164 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
164 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | Santiago Professional Siding [Santiago]
164 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | Santiago Professional Siding [Santiago]
164 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-06-12 | 2025-06-12
164 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12 | Santiago Professional Siding [Santiago]
164 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-16 | 2025-04-16
164 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
165 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-24 | 2025-06-24
165 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
165 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
165 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | Santiago Professional Siding [Santiago]
165 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | Santiago Professional Siding [Santiago]
165 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-06-12 | 2025-06-12
165 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12 | Santiago Professional Siding [Santiago]
165 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-10 | 2025-04-10
165 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
91 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-21 | 2025-08-21
91 Stonewood | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-19 | 2025-08-19
91 Stonewood | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-15 | 2025-08-15
91 Stonewood | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-13 | 2025-08-13
91 Stonewood | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-02 | 2025-07-02
91 Stonewood | Measurements | FALSE | 0 | Measured | 1 | 2025-07-01 | 2025-07-01
91 Stonewood | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
91 Stonewood | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
91 Stonewood | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
105 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-22 | 2025-08-22
105 Stonewood | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-20 | 2025-08-20
105 Stonewood | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-18 | 2025-08-18
105 Stonewood | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-14 | 2025-08-14
105 Stonewood | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-03 | 2025-07-03
105 Stonewood | Measurements | FALSE | 0 | Measured | 1 | 2025-07-02 | 2025-07-02
105 Stonewood | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
105 Stonewood | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-02 | 2025-06-02
105 Stonewood | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-02 | 2025-06-02
87 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
87 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
87 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
87 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09 | Santiago Professional Siding [Santiago]
87 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-05 | 2025-06-05 | Santiago Professional Siding [Santiago]
87 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
87 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05 | Santiago Professional Siding [Santiago]
87 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-03 | 2025-04-03
87 Stonewood | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-03 | 2025-04-03
Pinehurst Ct- Pinehurst | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-06 | 2025-11-06
Pinehurst Ct- Pinehurst | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-02 | 2025-10-02
Pinehurst Ct- Pinehurst | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-30 | 2025-09-30
Pinehurst Ct- Pinehurst | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-09-26 | 2025-09-26
Pinehurst Ct- Pinehurst | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-09-25 | 2025-09-25
Pinehurst Ct- Pinehurst | Measurements | TRUE | 100 | Measured | 1 | 2025-06-26 | 2025-06-26
Pinehurst Ct- Pinehurst | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-09-25 | 2025-09-25
Pinehurst Ct- Pinehurst | Ordered | TRUE | 100 | Ordered | 1 | 2025-07-24 | 2025-07-24
Pinehurst Ct- Pinehurst | Lien # | FALSE | 0 | Lien # | 1 | 2025-07-24 | 2025-07-24
Pinehurst Ct- Magnolia | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-16 | 2025-07-16
Pinehurst Ct- Magnolia | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-14 | 2025-07-14
Pinehurst Ct- Magnolia | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-10 | 2025-07-10
Pinehurst Ct- Magnolia | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-08 | 2025-07-08
Pinehurst Ct- Magnolia | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-27 | 2025-05-27
Pinehurst Ct- Magnolia | Measurements | FALSE | 0 | Measured | 1 | 2025-05-26 | 2025-05-26
Pinehurst Ct- Magnolia | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27
Pinehurst Ct- Magnolia | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
Pinehurst Ct- Magnolia | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-25 | 2025-03-25
79 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-05 | 2025-06-05
79 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
79 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
79 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
79 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-27 | 2025-05-27 | Hector Oliverio [Hector]
79 Southern Estates | Measurements | FALSE | 0 | Measured | 1 | 2025-06-03 | 2025-06-03
79 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
79 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
79 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-06 | 2025-05-06
7 Laurel Ridge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-17 | 2025-04-17
7 Laurel Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
7 Laurel Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11
7 Laurel Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
7 Laurel Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | JO Brothers [Richard]
7 Laurel Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
7 Laurel Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-11 | 2025-02-11
7 Laurel Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
7 Laurel Ridge | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-30 | 2025-01-30
140 Annandale | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-08-28 | 2025-08-28
140 Annandale | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-16 | 2025-06-16
140 Annandale | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
140 Annandale | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16 | JTD SIDING CONSTRUCTION LLC
140 Annandale | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-11 | 2025-06-11 | JTD SIDING CONSTRUCTION LLC
140 Annandale | Measurements | TRUE | 100 | Measured | 1 | 2025-05-16 | 2025-05-16
140 Annandale | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-11 | 2025-06-11 | JTD SIDING CONSTRUCTION LLC
140 Annandale | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-02 | 2025-04-02
140 Annandale | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-25 | 2025-04-25
38 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-02 | 2025-09-02
38 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-29 | 2025-08-29
38 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-27 | 2025-08-27
38 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
38 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-14 | 2025-07-14
38 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-11 | 2025-07-11
38 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
38 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-12 | 2025-05-12
38 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-12 | 2025-05-12
60 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-02 | 2025-09-02
60 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-29 | 2025-08-29
60 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-27 | 2025-08-27
60 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-25 | 2025-08-25
60 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-14 | 2025-07-14
60 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-11 | 2025-07-11
60 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
60 Watkins Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-12 | 2025-05-12
60 Watkins Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
68 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
68 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-05 | 2025-09-05
68 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
68 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-01 | 2025-09-01
68 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-21 | 2025-07-21
68 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-18 | 2025-07-18
68 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
68 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-19 | 2025-05-19
68 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-19 | 2025-05-19
64 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-09 | 2025-09-09
64 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-05 | 2025-09-05
64 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-03 | 2025-09-03
64 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-01 | 2025-09-01
64 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-21 | 2025-07-21
64 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-07-18 | 2025-07-18
64 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
64 Watkins Grove | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-19 | 2025-05-19
64 Watkins Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-19 | 2025-05-19
105 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
105 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17 | Torres Painting Professional
105 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
105 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-15 | 2025-04-15
105 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
105 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Mendez Siding & Boxing LLC
105 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Mendez Siding & Boxing LLC
105 Hickory Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-03-19 | 2025-03-19
105 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-02 | 2025-04-02 | Mendez Siding & Boxing LLC
105 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
105 Hickory Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-27 | 2025-01-27
122 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
122 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17 | Torres Painting Professional
122 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
122 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-15 | 2025-04-15
122 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
122 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Mendez Siding & Boxing LLC
122 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Mendez Siding & Boxing LLC
122 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-05-23 | 2025-05-23
122 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-02 | 2025-04-02 | Mendez Siding & Boxing LLC
122 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-28 | 2025-01-28
122 Hickory Grove | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-28 | 2025-01-28
148 Wilkins | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-14 | 2025-05-14
148 Wilkins | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
148 Wilkins | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
148 Wilkins | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
148 Wilkins | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-30 | 2025-04-30 | Leones Construction LLC
148 Wilkins | Measurements | FALSE | 0 | Measured | 1 | 2025-05-21 | 2025-05-21
148 Wilkins | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-28 | 2025-02-28
148 Wilkins | Ordered | FALSE | 0 | Ordered | 1 | 2025-02-26 | 2025-02-26
148 Wilkins | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-26 | 2025-02-26
116 Chestnut | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
116 Chestnut | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
116 Chestnut | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
116 Chestnut | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
116 Chestnut | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-09 | 2025-04-09 | Santiago Professional Siding [Santiago]
116 Chestnut | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
116 Chestnut | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09
116 Chestnut | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-05 | 2025-02-05
116 Chestnut | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
2 Windfield | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-10 | 2025-06-10
2 Windfield | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
2 Windfield | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04
2 Windfield | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
2 Windfield | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | La Culebra Siding & Windows LLC
2 Windfield | Measurements | TRUE | 100 | Measured | 1 | 2025-05-02 | 2025-05-02
2 Windfield | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
2 Windfield | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
2 Windfield | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
4 Windfield | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
4 Windfield | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-02 | 2025-06-02
4 Windfield | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
4 Windfield | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
4 Windfield | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | NC SIDING & REMODELING PRO LLC
4 Windfield | Measurements | TRUE | 100 | Measured | 1 | 2025-05-07 | 2025-05-07
4 Windfield | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
4 Windfield | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-04 | 2025-03-04
4 Windfield | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
3 Windfield | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
3 Windfield | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-19 | 2025-06-19
3 Windfield | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
3 Windfield | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
3 Windfield | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | NC SIDING & REMODELING PRO LLC
3 Windfield | Measurements | TRUE | 100 | Measured | 1 | 2025-05-02 | 2025-05-02
3 Windfield | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
3 Windfield | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-04 | 2025-03-04
3 Windfield | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
1 Windfield | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-06 | 2025-10-06
1 Windfield | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-04 | 2025-08-04
1 Windfield | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-31 | 2025-07-31
1 Windfield | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-29 | 2025-07-29
1 Windfield | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-28 | 2025-07-28 | La Culebra Siding & Windows LLC
1 Windfield | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
1 Windfield | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-28 | 2025-07-28
1 Windfield | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-12 | 2025-05-12
1 Windfield | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-10 | 2025-06-10
84 Providence Oaks 40 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-30 | 2025-05-30
84 Providence Oaks 40 | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
84 Providence Oaks 40 | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26
84 Providence Oaks 40 | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
84 Providence Oaks 40 | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Delia Construction
84 Providence Oaks 40 | Measurements | FALSE | 0 | Measured | 1 | 2025-06-23 | 2025-06-23
84 Providence Oaks 40 | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16
84 Providence Oaks 40 | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
84 Providence Oaks 40 | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
79 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-22 | 2025-04-22
79 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
79 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
79 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Delia Construction
79 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-11 | 2025-04-11 | Delia Construction
79 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-06-20 | 2025-06-20
79 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-11 | 2025-04-11 | Delia Construction
79 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
79 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
78 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
78 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
78 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
78 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Delia Construction
78 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-21 | 2025-04-21 | Delia Construction
78 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-06-16 | 2025-06-16
78 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21 | Delia Construction
78 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
78 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-21 | 2025-02-21
Wilder Farms | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
Wilder Farms | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
Wilder Farms | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
Wilder Farms | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
Wilder Farms | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-23 | 2025-04-23 | Hector Oliverio [Hector]
Wilder Farms | Measurements | TRUE | 100 | Measured | 1 | 2025-04-07 | 2025-04-07
Wilder Farms | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27
Wilder Farms | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-19 | 2025-02-19
Wilder Farms | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
104 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-18 | 2025-03-18
104 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
103 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-18 | 2025-03-18
103 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
102 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-18 | 2025-03-18
102 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
74 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
74 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
74 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
74 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Daniel's Construction & Repair [Roger]
74 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Daniel's Construction & Repair [Roger]
74 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
74 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-02 | 2025-04-02 | Daniel's Construction & Repair [Roger]
74 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-29 | 2025-01-29
74 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
Dunn House | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-05 | 2025-08-05
Dunn House | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-28 | 2025-07-28
Dunn House | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-30 | 2025-07-30
Dunn House | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28 | OCCZ Construction LLC
Dunn House | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-24 | 2025-07-24 | OCCZ Construction LLC
Dunn House | Measurements | TRUE | 100 | Measured | 1 | 2025-07-24 | 2025-07-24
Dunn House | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-24 | 2025-07-24 | OCCZ Construction LLC
Dunn House | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-22 | 2025-05-22
Dunn House | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-07 | 2025-07-07
12 Eller Farms | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-16 | 2025-04-16
12 Eller Farms | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
12 Eller Farms | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
12 Eller Farms | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
12 Eller Farms | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Siding Pro Service LLC
12 Eller Farms | Measurements | TRUE | 100 | Measured | 1 | 2025-05-27 | 2025-05-27
12 Eller Farms | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-05 | 2025-02-05
12 Eller Farms | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
12 Eller Farms | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-23 | 2025-01-23
19 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-12 | 2025-06-12
19 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
19 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-06 | 2025-06-06
19 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04
19 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-03 | 2025-06-03 | Hector Oliverio [Hector]
19 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
19 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03
19 Caitlin Crossing | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-01 | 2025-04-01
19 Caitlin Crossing | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-01 | 2025-04-01
18 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
18 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-18 | 2025-06-18
18 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
18 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
18 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | Hector Oliverio [Hector]
18 Caitlin Crossing | Measurements | TRUE | 100 | Measured | 1 | 2025-06-05 | 2025-06-05
18 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
18 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-01 | 2025-04-01
18 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
6 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-22 | 2025-05-22
6 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
6 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
6 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-14 | 2025-05-14
6 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-13 | 2025-05-13 | Hector Oliverio [Hector]
6 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
6 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13 | Hector Oliverio [Hector]
6 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
6 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
5 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-02 | 2025-05-02
5 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-19 | 2025-05-19
5 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
5 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
5 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
5 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
5 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
5 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-05 | 2025-02-05
5 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
16 Maison Ridge | Paid Waterproof Deck | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
16 Maison Ridge | Waterproof Deck Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
16 Maison Ridge | Paid Rails | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
16 Maison Ridge | Rails Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
16 Maison Ridge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
16 Maison Ridge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
16 Maison Ridge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
16 Maison Ridge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
16 Maison Ridge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | Avery Siding LLC
16 Maison Ridge | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
16 Maison Ridge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-21 | 2025-03-21
16 Maison Ridge | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-13 | 2025-02-13
16 Maison Ridge | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
47 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
47 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
47 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
47 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Santiago Professional Siding [Santiago]
47 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
47 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
47 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
47 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
47 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
46 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
46 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-30 | 2025-05-30
46 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
46 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Santiago Professional Siding [Santiago]
46 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
46 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
46 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
46 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
46 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
45 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
45 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
45 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
45 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Santiago Professional Siding [Santiago]
45 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
45 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
45 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
45 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
45 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
44 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
44 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-30 | 2025-05-30
44 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
44 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Santiago Professional Siding [Santiago]
44 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
44 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
44 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
44 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-26 | 2025-03-26
44 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-11 | 2025-04-11
43 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-03 | 2025-06-03
43 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-30 | 2025-05-30
43 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
43 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-26 | 2025-05-26 | Santiago Professional Siding [Santiago]
43 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
43 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-21 | 2025-05-21
43 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21 | Santiago Professional Siding [Santiago]
43 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
43 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
40 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-28 | 2025-07-28
40 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
40 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-22 | 2025-07-22
40 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-18 | 2025-07-18 | Modern Exteriors Inc
40 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
40 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
40 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
40 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
40 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-21 | 2025-05-21
39 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-28 | 2025-07-28
39 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-22 | 2025-07-22
39 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-22 | 2025-07-22
39 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-18 | 2025-07-18 | Modern Exteriors Inc
39 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
39 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
39 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
39 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
39 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-21 | 2025-05-21
38 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-28 | 2025-07-28
38 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
38 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-22 | 2025-07-22
38 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-18 | 2025-07-18 | Modern Exteriors Inc
38 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
38 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
38 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
38 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
38 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-21 | 2025-05-21
37 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-28 | 2025-07-28
37 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-18 | 2025-07-18
37 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-22 | 2025-07-22
37 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-18 | 2025-07-18 | Modern Exteriors Inc
37 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
37 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-07-10 | 2025-07-10
37 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-07-14 | 2025-07-14 | Modern Exteriors Inc
37 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
37 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-21 | 2025-05-21
231 Turkey Ridge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-29 | 2025-09-29
231 Turkey Ridge | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
231 Turkey Ridge | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
231 Turkey Ridge | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
231 Turkey Ridge | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-08 | 2025-08-08
231 Turkey Ridge | Measurements | FALSE | 0 | Measured | 1 | 2025-08-07 | 2025-08-07
231 Turkey Ridge | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-08 | 2025-08-08
231 Turkey Ridge | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-06 | 2025-06-06
231 Turkey Ridge | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-06 | 2025-06-06
234 Turkey Ridge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-29 | 2025-09-29
234 Turkey Ridge | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
234 Turkey Ridge | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
234 Turkey Ridge | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
234 Turkey Ridge | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-08 | 2025-08-08
234 Turkey Ridge | Measurements | FALSE | 0 | Measured | 1 | 2025-08-07 | 2025-08-07
234 Turkey Ridge | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-08 | 2025-08-08
234 Turkey Ridge | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-06 | 2025-06-06
234 Turkey Ridge | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-06 | 2025-06-06
233 Turkey Ridge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-29 | 2025-09-29
233 Turkey Ridge | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
233 Turkey Ridge | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-23 | 2025-09-23
233 Turkey Ridge | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
233 Turkey Ridge | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-08 | 2025-08-08
233 Turkey Ridge | Measurements | FALSE | 0 | Measured | 1 | 2025-08-07 | 2025-08-07
233 Turkey Ridge | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-08 | 2025-08-08
233 Turkey Ridge | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-06 | 2025-06-06
233 Turkey Ridge | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-06 | 2025-06-06
11 Olivet | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-30 | 2025-04-30
11 Olivet | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
11 Olivet | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24
11 Olivet | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22
11 Olivet | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | Avery Siding LLC
11 Olivet | Measurements | TRUE | 100 | Measured | 1 | 2025-04-14 | 2025-04-14
11 Olivet | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-24 | 2025-03-24
11 Olivet | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
11 Olivet | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
133 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
133 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
133 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
133 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
133 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | Jesus Construction
133 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-30 | 2025-05-30
133 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
133 River Glen | Ordered | FALSE | 0 | Ordered | 1 | 2025-03-03 | 2025-03-03
133 River Glen | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-03 | 2025-03-03
delete | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-04 | 2025-07-04
delete | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
delete | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
delete | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
delete | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-15 | 2025-05-15
delete | Measurements | FALSE | 0 | Measured | 1 | 2025-05-14 | 2025-05-14
delete | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17
delete | Ordered | FALSE | 0 | Ordered | 1 | 2025-03-13 | 2025-03-13
delete | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-13 | 2025-03-13
132 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-02 | 2025-05-02
132 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
132 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
132 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24 | Jesus Construction
132 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Jesus Construction
132 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-22 | 2025-05-22
132 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Jesus Construction
132 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-07 | 2025-03-07
132 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
131 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
131 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
131 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
131 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
131 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | Jesus Construction
131 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-14 | 2025-05-14
131 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01
131 River Glen | Ordered | FALSE | 0 | Ordered | 1 | 2025-03-07 | 2025-03-07
131 River Glen | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-07 | 2025-03-07
130 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-21 | 2025-07-21
130 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
130 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
130 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
130 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | Jesus Construction
130 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-07-21 | 2025-07-21
130 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01
130 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-21 | 2025-03-21
130 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
27 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
27 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
27 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
27 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
27 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | J&A Construction
27 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
27 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
27 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
27 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-18 | 2025-04-18
187 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
187 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Torres Painting Professional
187 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
187 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
187 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
187 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
187 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-08 | 2025-05-08 | JO Brothers [Richard]
187 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-05-05 | 2025-05-05
187 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14
187 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
187 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
113 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
113 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12 | Torres Painting Professional
113 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-21 | 2025-05-21
113 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
113 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
113 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
113 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | JO Brothers [Richard]
113 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-05-02 | 2025-05-02
113 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20
113 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
113 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
103 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
103 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
103 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
103 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
103 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-03 | 2025-06-03 | Leones Construction LLC
103 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-20 | 2025-05-20
103 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03
103 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-09 | 2025-04-09
103 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-27 | 2025-05-27
102 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-10 | 2025-07-10
102 Duncans Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-08 | 2025-07-08
102 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-04 | 2025-07-04
102 Duncans Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02
102 Duncans Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-21 | 2025-05-21
102 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-20 | 2025-05-20
102 Duncans Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-25 | 2025-04-25
102 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-23 | 2025-04-23
102 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-23 | 2025-04-23
52 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-14 | 2025-05-14
52 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-20 | 2025-05-20
52 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
52 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
52 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | Hector Oliverio [Hector]
52 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-27 | 2025-05-27
52 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
52 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-18 | 2025-02-18
52 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-18 | 2025-02-18
45 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
45 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-20 | 2025-05-20
45 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
45 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
45 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-06 | 2025-05-06 | Hector Oliverio [Hector]
45 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-27 | 2025-05-27
45 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
45 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-25 | 2025-02-25
45 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-25 | 2025-02-25
23 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-17 | 2025-04-17
23 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
23 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11
23 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09 | Hector Oliverio [Hector]
23 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-07 | 2025-04-07 | Hector Oliverio [Hector]
23 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
23 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-07 | 2025-04-07 | Hector Oliverio [Hector]
23 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-10 | 2025-02-10
23 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-10 | 2025-02-10
38 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-21 | 2025-04-21
38 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-14 | 2025-04-14
38 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
38 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Hector Oliverio [Hector]
38 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-09 | 2025-04-09 | Hector Oliverio [Hector]
38 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-04-01 | 2025-04-01
38 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09 | Hector Oliverio [Hector]
38 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
38 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-30 | 2025-01-30
36 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-16 | 2025-05-16
36 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
36 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
36 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08
36 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | Hector Oliverio [Hector]
36 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-20 | 2025-05-20
36 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-07 | 2025-05-07
36 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
36 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-03 | 2025-04-03
30 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
30 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-14 | 2025-04-14
30 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
30 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Hector Oliverio [Hector]
30 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Hector Oliverio [Hector]
30 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
30 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08 | Hector Oliverio [Hector]
30 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-15 | 2025-01-15
30 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-15 | 2025-01-15
91 Elk Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
91 Elk Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-12 | 2025-09-12
91 Elk Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
91 Elk Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-08 | 2025-09-08
91 Elk Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-28 | 2025-07-28
91 Elk Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-09-19 | 2025-09-19
91 Elk Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-18 | 2025-09-18
91 Elk Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-12 | 2025-05-12
91 Elk Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-16 | 2025-06-16
60 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
60 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04 | Torres Painting Professional
57 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
57 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-25 | 2025-06-25
57 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
57 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
57 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | NC SIDING & REMODELING PRO LLC
57 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-05-12 | 2025-05-12
57 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23
57 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
57 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-22 | 2025-04-22
58 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
58 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-09 | 2025-06-09
58 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
58 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
58 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | NC SIDING & REMODELING PRO LLC
58 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-05-26 | 2025-05-26
58 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-09 | 2025-05-09
58 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
58 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-08 | 2025-04-08
59 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-29 | 2025-05-29
59 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
59 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
59 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
59 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | NC SIDING & REMODELING PRO LLC
59 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-05-26 | 2025-05-26
59 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14
59 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
59 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-10 | 2025-04-10
60 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
60 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
60 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
60 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
60 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-03 | 2025-06-03 | La Culebra Siding & Windows LLC
60 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-05-26 | 2025-05-26
60 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03
60 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-18 | 2025-03-18
60 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-23 | 2025-04-23
69 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-06 | 2025-05-06
69 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
69 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30
69 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
69 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | LA Siding Construction LLP [Hector]
69 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-04-23 | 2025-04-23
69 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
69 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
69 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
110 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-23 | 2025-05-23
110 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
110 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
110 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
110 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | JO Brothers [Richard]
110 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
110 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01
110 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
110 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
145 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-01 | 2025-07-01
145 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-25 | 2025-06-25
145 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-25 | 2025-06-25
145 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
145 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | JO Brothers [Richard]
145 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
145 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
145 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-27 | 2025-03-27
145 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-08 | 2025-04-08
32 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
32 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
32 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
32 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
32 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-13 | 2025-05-13 | Leones Construction LLC
32 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-05-23 | 2025-05-23
32 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
32 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-25 | 2025-02-25
32 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
163 Edge of Auburn - Summit | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-18 | 2025-09-18
163 Edge of Auburn - Summit | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-16 | 2025-09-16
163 Edge of Auburn - Summit | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
163 Edge of Auburn - Summit | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-10 | 2025-09-10
163 Edge of Auburn - Summit | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-30 | 2025-07-30
163 Edge of Auburn - Summit | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
163 Edge of Auburn - Summit | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-30 | 2025-07-30
163 Edge of Auburn - Summit | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-28 | 2025-05-28
163 Edge of Auburn - Summit | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-28 | 2025-05-28
9 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
9 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
9 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
9 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01 | Hector Oliverio [Hector]
9 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | Hector Oliverio [Hector]
9 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-06 | 2025-06-06
9 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-30 | 2025-04-30 | Hector Oliverio [Hector]
9 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-04 | 2025-02-04
9 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-10 | 2025-03-10
30 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
30 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
30 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
30 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
30 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-07 | 2025-05-07 | J&A Construction
30 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-21 | 2025-04-21
30 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-08 | 2025-05-08
30 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
30 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-11 | 2025-04-11
24 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
24 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
24 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
24 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
24 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | J&A Construction
24 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
24 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
24 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-24 | 2025-03-24
24 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-23 | 2025-04-23
21 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
21 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
21 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
21 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
21 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | J&A Construction
21 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
21 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
21 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
21 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-22 | 2025-04-22
4 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
4 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
4 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
4 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Hector Oliverio [Hector]
4 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
4 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-11 | 2025-06-11
4 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
4 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-17 | 2025-01-17
4 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-24 | 2025-02-24
8 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-06 | 2025-05-06
8 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-04 | 2025-06-04
8 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30
8 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28 | Hector Oliverio [Hector]
8 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
8 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-12 | 2025-06-12
8 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
8 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-20 | 2025-01-20
8 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-25 | 2025-02-25
3 Caitlin Crossing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-30 | 2025-04-30
3 Caitlin Crossing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
3 Caitlin Crossing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24
3 Caitlin Crossing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
3 Caitlin Crossing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-21 | 2025-04-21 | Hector Oliverio [Hector]
3 Caitlin Crossing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-11 | 2025-06-11
3 Caitlin Crossing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21 | Hector Oliverio [Hector]
3 Caitlin Crossing | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-16 | 2025-01-16
3 Caitlin Crossing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-21 | 2025-02-21
2 Caitlin Crossing - Model | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-28 | 2025-04-28
2 Caitlin Crossing - Model | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
2 Caitlin Crossing - Model | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22
2 Caitlin Crossing - Model | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18 | Hector Oliverio [Hector]
2 Caitlin Crossing - Model | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-17 | 2025-04-17 | Hector Oliverio [Hector]
2 Caitlin Crossing - Model | Measurements | FALSE | 0 | Measured | 1 | 2025-05-29 | 2025-05-29
2 Caitlin Crossing - Model | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-17 | 2025-04-17 | Hector Oliverio [Hector]
2 Caitlin Crossing - Model | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
2 Caitlin Crossing - Model | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-04 | 2025-03-04
46 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-14 | 2025-07-14
46 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-11 | 2025-07-11
47 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-14 | 2025-07-14
47 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-11 | 2025-07-11
48 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-14 | 2025-07-14
48 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-11 | 2025-07-11
41 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-04 | 2025-07-04
41 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-02 | 2025-07-02
41 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
41 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-26 | 2025-06-26
41 Watkins Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-15 | 2025-05-15 | NC SIDING & REMODELING PRO LLC
41 Watkins Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-05-15 | 2025-05-15
41 Watkins Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-19 | 2025-03-19
41 Watkins Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-13 | 2025-03-13
41 Watkins Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-17 | 2025-03-17
87 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-22 | 2025-04-22
87 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
87 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
87 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Jesus Construction
87 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | Jesus Construction
87 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-06-17 | 2025-06-17
87 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | Jesus Construction
87 River Glen | Ordered | FALSE | 0 | Ordered | 1 | 2025-02-06 | 2025-02-06
87 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
112 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
112 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15 | Torres Painting Professional
112 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
112 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
112 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
112 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
112 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | JO Brothers [Richard]
112 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
112 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
112 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-18 | 2025-02-18
112 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
14 Holding Village Mews TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
14 Holding Village Mews TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
14 Holding Village Mews TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
14 Holding Village Mews TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
14 Holding Village Mews TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Mendez Siding & Boxing LLC
14 Holding Village Mews TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-02 | 2025-05-02
14 Holding Village Mews TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-18 | 2025-04-18
14 Holding Village Mews TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-15 | 2025-04-15
14 Holding Village Mews TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
426 Paddington Station 30' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
426 Paddington Station 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
426 Paddington Station 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-01 | 2025-08-01
426 Paddington Station 30' | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-30 | 2025-07-30
426 Paddington Station 30' | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-28 | 2025-07-28
426 Paddington Station 30' | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-24 | 2025-07-24
426 Paddington Station 30' | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-12 | 2025-06-12
426 Paddington Station 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-06-11 | 2025-06-11
426 Paddington Station 30' | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
426 Paddington Station 30' | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-08 | 2025-05-08
23 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
23 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
23 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-08 | 2025-08-08
23 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-06 | 2025-08-06
23 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-04 | 2025-08-04
23 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-31 | 2025-07-31
23 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-19 | 2025-06-19
23 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-18 | 2025-06-18
23 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
23 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-08 | 2025-05-08
23 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-08 | 2025-05-08
22 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
22 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
22 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-08 | 2025-08-08
22 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-06 | 2025-08-06
22 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-04 | 2025-08-04
22 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-31 | 2025-07-31
22 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-19 | 2025-06-19
22 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-18 | 2025-06-18
22 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
22 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-15 | 2025-05-15
22 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-15 | 2025-05-15
21 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
21 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
21 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-08 | 2025-08-08
21 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-06 | 2025-08-06
21 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-04 | 2025-08-04
21 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-31 | 2025-07-31
21 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-19 | 2025-06-19
21 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-18 | 2025-06-18
21 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
21 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-08 | 2025-05-08
21 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-08 | 2025-05-08
20 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
20 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
17 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
17 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
20 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-19 | 2025-08-19
20 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-08-15 | 2025-08-15
20 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-13 | 2025-08-13
20 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-08-11 | 2025-08-11
20 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-06-30 | 2025-06-30
20 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-06-27 | 2025-06-27
20 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
20 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-15 | 2025-05-15
20 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-15 | 2025-05-15
41 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-08 | 2025-07-08
41 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
41 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-07-02 | 2025-07-02
41 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-30 | 2025-06-30
41 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-26 | 2025-06-26 | Wohlstand Construction LLC
41 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-06-25 | 2025-06-25
41 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-26 | 2025-06-26
41 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-23 | 2025-05-23
41 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-27 | 2025-06-27
40 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-26 | 2025-06-26
40 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-13 | 2025-08-13
40 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-20 | 2025-06-20
40 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-18 | 2025-06-18
40 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-07 | 2025-05-07
40 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-06-25 | 2025-06-25
40 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05
40 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-07 | 2025-04-07
40 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-13 | 2025-05-13
39 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
39 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-25 | 2025-06-25
39 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
39 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
39 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-08 | 2025-05-08
39 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-07 | 2025-05-07
39 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
39 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
39 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
29 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-25 | 2025-06-25
29 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-23 | 2025-06-23
29 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
29 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
29 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-06 | 2025-05-06
29 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-05 | 2025-05-05
29 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01
29 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
29 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
28 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-30 | 2025-06-30
28 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-26 | 2025-06-26
28 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24
28 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-20 | 2025-06-20
28 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-09 | 2025-05-09
28 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-08 | 2025-05-08
28 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
28 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
28 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
24 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
24 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-25 | 2025-06-25
24 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
24 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19
24 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-08 | 2025-05-08
24 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-07 | 2025-05-07
24 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
24 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
24 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
16 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-30 | 2025-06-30
16 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-26 | 2025-06-26
16 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-24 | 2025-06-24
16 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-20 | 2025-06-20
16 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-09 | 2025-05-09
16 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-08 | 2025-05-08
16 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
16 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
16 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
15 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-07-14 | 2025-07-14
15 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-07-10 | 2025-07-10
15 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-08 | 2025-07-08
15 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-07-04 | 2025-07-04
15 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-23 | 2025-05-23
15 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-05-22 | 2025-05-22
15 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09
15 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
15 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
86 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-02 | 2025-05-02
86 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
86 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
86 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24
86 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-21 | 2025-04-21 | Jesus Construction
86 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-16 | 2025-05-16
86 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21
86 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-24 | 2025-02-24
86 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
28 Harvest Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
28 Harvest Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-21 | 2025-04-21
28 Harvest Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
28 Harvest Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16 | Prime Exterior [Siding] LLC [Miguel]
28 Harvest Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-17 | 2025-04-17 | Prime Exterior [Siding] LLC [Miguel]
28 Harvest Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-04-16 | 2025-04-16 | Prime Exterior [Siding] LLC [Miguel]
28 Harvest Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-17 | 2025-04-17 | Prime Exterior [Siding] LLC [Miguel]
28 Harvest Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-05 | 2025-02-05
28 Harvest Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-05 | 2025-02-05
7 Harvest Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
7 Harvest Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
7 Harvest Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
7 Harvest Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17 | Martinez NC Construction LLC [Luis]
7 Harvest Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-15 | 2025-04-15 | Martinez NC Construction LLC [Luis]
7 Harvest Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-04-16 | 2025-04-16 | Martinez NC Construction LLC [Luis]
7 Harvest Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16 | Martinez NC Construction LLC [Luis]
7 Harvest Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-03 | 2025-02-03
7 Harvest Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-03 | 2025-02-03
754 Edge of Auburn - Classic | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-12 | 2025-08-12
754 Edge of Auburn - Classic | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
754 Edge of Auburn - Classic | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
754 Edge of Auburn - Classic | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
754 Edge of Auburn - Classic | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Jose Velasco Gaytan [Jimmy]
754 Edge of Auburn - Classic | Measurements | TRUE | 100 | Measured | 1 | 2025-02-26 | 2025-02-26
754 Edge of Auburn - Classic | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
754 Edge of Auburn - Classic | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-06 | 2025-01-06
754 Edge of Auburn - Classic | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-13 | 2025-02-13
75 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
75 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
75 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
75 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Daniel's Construction & Repair [Roger]
75 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-04 | 2025-04-04 | Daniel's Construction & Repair [Roger]
75 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-04 | 2025-04-04
75 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-04 | 2025-04-04 | Daniel's Construction & Repair [Roger]
75 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-31 | 2025-01-31
75 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
106 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-08 | 2025-04-08
106 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
106 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
106 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Siding Express, LLC [Israel]
106 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-28 | 2025-03-28 | Siding Express, LLC [Israel]
106 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-03-28 | 2025-03-28
106 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28 | Siding Express, LLC [Israel]
106 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
106 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
196 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-21 | 2025-04-21
196 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
196 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
196 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Siding Express, LLC [Israel]
196 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-09 | 2025-04-09 | Siding Express, LLC [Israel]
196 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-07 | 2025-04-07
196 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09 | Siding Express, LLC [Israel]
196 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
196 Falls Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
109 Falls Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-04 | 2025-04-04
109 Falls Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-04 | 2025-04-04
109 Falls Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
109 Falls Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27 | Siding Express, LLC [Israel]
109 Falls Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-25 | 2025-03-25 | Siding Express, LLC [Israel]
109 Falls Village | Measurements | TRUE | 100 | Measured | 1 | 2025-03-25 | 2025-03-25
109 Falls Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-25 | 2025-03-25 | Siding Express, LLC [Israel]
109 Falls Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-28 | 2025-01-28
109 Falls Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-28 | 2025-01-28
85 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-21 | 2025-04-21
85 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
85 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
85 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Jesus Construction
85 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Jesus Construction
85 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-05-22 | 2025-05-22
85 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08 | Jesus Construction
85 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-16 | 2025-01-16
85 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-21 | 2025-04-21
44 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
44 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
44 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
44 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
44 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-01 | 2025-05-01 | J&A Construction
44 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-17 | 2025-04-17
44 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-01 | 2025-05-01
44 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-24 | 2025-03-24
44 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-28 | 2025-04-28
26 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
26 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-07 | 2025-05-07
26 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
26 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
26 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-30 | 2025-04-30 | J&A Construction
26 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-17 | 2025-04-17
26 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-30 | 2025-04-30
26 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
26 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
Pierre Morin Residence | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-19 | 2025-03-19
Pierre Morin Residence | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
Pierre Morin Residence | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
Pierre Morin Residence | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
Pierre Morin Residence | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-03 | 2025-03-03 | Siding Pro Service LLC
Pierre Morin Residence | Measurements | TRUE | 100 | Measured | 1 | 2025-03-03 | 2025-03-03
Pierre Morin Residence | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-03 | 2025-03-03
Pierre Morin Residence | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-25 | 2025-02-25
Pierre Morin Residence | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-25 | 2025-02-25
17 Carolina Overlook Twin Villas | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
17 Carolina Overlook Twin Villas | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
17 Carolina Overlook Twin Villas | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
17 Carolina Overlook Twin Villas | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
17 Carolina Overlook Twin Villas | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | NC Stark Construction Inc. [Amando]
17 Carolina Overlook Twin Villas | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
17 Carolina Overlook Twin Villas | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
17 Carolina Overlook Twin Villas | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
17 Carolina Overlook Twin Villas | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
16 Carolina Overlook Twin Villas | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
16 Carolina Overlook Twin Villas | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
16 Carolina Overlook Twin Villas | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
16 Carolina Overlook Twin Villas | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
16 Carolina Overlook Twin Villas | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | NC Stark Construction Inc. [Amando]
16 Carolina Overlook Twin Villas | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
16 Carolina Overlook Twin Villas | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
16 Carolina Overlook Twin Villas | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
16 Carolina Overlook Twin Villas | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
171 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
171 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Torres Painting Professional
1 Tart Town Rd | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
1 Tart Town Rd | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
1 Tart Town Rd | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
1 Tart Town Rd | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Leones Construction LLC
1 Tart Town Rd | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Leones Construction LLC
1 Tart Town Rd | Measurements | FALSE | 0 | Measured | 1 | 2025-05-05 | 2025-05-05
1 Tart Town Rd | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08 | Leones Construction LLC
1 Tart Town Rd | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
1 Tart Town Rd | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-26 | 2025-02-26
93 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
93 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-04 | 2025-06-04
93 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
93 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
93 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-22 | 2025-05-22 | NC Stark Construction Inc. [Amando]
93 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-05-28 | 2025-05-28
93 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-04 | 2025-06-04
93 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-06 | 2025-05-06
93 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-09 | 2025-05-09
153 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-25 | 2025-02-25
153 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Torres Painting Professional
153 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
153 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
153 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
153 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
153 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | JO Brothers [Richard]
153 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
153 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27
153 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
153 Trails at Young Farm | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-07 | 2025-02-07
99 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
99 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
99 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
99 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Delia Construction
99 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Delia Construction
99 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-11 | 2025-03-11
99 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-30 | 2025-06-30 | Delia Construction
99 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-22 | 2025-01-22
99 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
98 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
98 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
98 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
98 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
98 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Delia Construction
98 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-28 | 2025-05-28
98 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Delia Construction
98 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-07 | 2025-03-07
98 Providence Oaks 30' | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-07 | 2025-03-07
97 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
97 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
97 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
97 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
97 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Delia Construction
97 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-26 | 2025-05-26
97 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28
97 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-10 | 2025-03-10
97 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
373 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
373 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
373 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
373 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
373 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | JO Brothers [Richard]
373 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
373 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-18 | 2025-04-18
373 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
373 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
72 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
72 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
72 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
72 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
72 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | Toluca Construction
72 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
72 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-03 | 2025-04-03
72 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
72 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-11 | 2025-03-11
68 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
68 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
68 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
68 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
68 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | J Ortiz Siding Inc [Jose]
68 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
68 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-04 | 2025-04-04 | J Ortiz Siding Inc [Jose]
68 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
68 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-12 | 2025-03-12
71 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
71 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
71 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
71 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
71 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-16 | 2025-04-16 | Toluca Construction
71 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
71 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-04 | 2025-04-04
71 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
71 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
70 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
70 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
70 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
70 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
70 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-23 | 2025-04-23 | LA Siding Construction LLP [Hector]
70 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
70 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-18 | 2025-04-18
70 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-19 | 2025-02-19
70 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
61 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-22 | 2025-04-22
61 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
61 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
61 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
61 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-11 | 2025-04-11 | Toluca Construction
61 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-02-28 | 2025-02-28
61 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-21 | 2025-03-21
61 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-31 | 2025-01-31
61 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-05 | 2025-03-05
42 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
42 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-19 | 2025-06-19
42 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
42 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Santiago Professional Siding [Santiago]
42 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
42 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
42 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
42 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
42 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
41 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
41 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
41 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
41 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Santiago Professional Siding [Santiago]
41 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
41 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
41 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
41 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
41 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
40 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
40 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
40 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
40 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Santiago Professional Siding [Santiago]
40 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
40 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
40 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
40 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
40 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
39 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
39 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-26 | 2025-05-26
39 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
39 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20 | Santiago Professional Siding [Santiago]
39 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
39 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
39 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
39 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
39 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
38 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
38 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-26 | 2025-05-26
38 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
38 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20 | Santiago Professional Siding [Santiago]
38 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
38 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-19 | 2025-05-19
38 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Santiago Professional Siding [Santiago]
38 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-17 | 2025-03-17
38 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
53 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
53 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
53 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
53 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
53 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-15 | 2025-04-15 | Toluca Construction
53 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-03-06 | 2025-03-06
53 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27
53 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-04 | 2025-02-04
53 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-07 | 2025-03-07
67 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-31 | 2025-03-31
67 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
67 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25
67 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
67 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | J Ortiz Siding Inc [Jose]
67 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
67 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-03 | 2025-06-03
67 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
67 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-25 | 2025-03-25
66 Summer Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-04 | 2025-04-04
66 Summer Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
66 Summer Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
66 Summer Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
66 Summer Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-26 | 2025-03-26 | J Ortiz Siding Inc [Jose]
66 Summer Place | Measurements | TRUE | 100 | Measured | 1 | 2025-03-13 | 2025-03-13
66 Summer Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18
66 Summer Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-15 | 2025-01-15
66 Summer Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-18 | 2025-02-18
171 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-16 | 2025-04-16
171 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-15 | 2025-04-15
171 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
171 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
171 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-04 | 2025-04-04 | JO Brothers [Richard]
171 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-04-04 | 2025-04-04
171 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23
171 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-16 | 2025-01-16
171 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
152 Trails at Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20
152 Trails at Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02 | Torres Painting Professional
152 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
152 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
152 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
152 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
152 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | JO Brothers [Richard]
152 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
152 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21
152 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-04 | 2025-02-04
152 Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
3302 Hall Place | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-21 | 2025-04-21
3302 Hall Place | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
3302 Hall Place | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
3302 Hall Place | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11
3302 Hall Place | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-15 | 2025-04-15 | Santiago Professional Siding [Santiago]
3302 Hall Place | Measurements | TRUE | 100 | Measured | 1 | 2025-04-21 | 2025-04-21
3302 Hall Place | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08
3302 Hall Place | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-11 | 2025-02-11
3302 Hall Place | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
110 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19
110 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17 | Torres Painting Professional
4531 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
4531 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-08 | 2025-05-08
4531 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
4531 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
4531 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | JO Brothers [Richard]
4531 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-24 | 2025-04-24
4531 Chatham Park North Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-05 | 2025-06-05
4531 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
4531 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
43 Turnberry Rd | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-19 | 2025-03-19
43 Turnberry Rd | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
43 Turnberry Rd | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
43 Turnberry Rd | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
43 Turnberry Rd | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Prime Exterior [Service] LLC [Tomas]
43 Turnberry Rd | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
43 Turnberry Rd | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-23 | 2025-01-23
43 Turnberry Rd | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
43 Turnberry Rd | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-03 | 2025-01-03
84 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-14 | 2025-04-14
84 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
84 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
84 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04 | Jesus Construction
84 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Jesus Construction
84 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-03-25 | 2025-03-25
84 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-30 | 2025-06-30 | Jesus Construction
84 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
84 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-22 | 2025-04-22
48 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
48 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
48 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
48 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21 | Santiago Professional Siding [Santiago]
48 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
48 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-14 | 2025-04-14
48 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
48 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
48 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
47 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
47 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
47 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
47 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21 | Santiago Professional Siding [Santiago]
47 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
47 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-14 | 2025-04-14
47 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
47 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
47 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
46 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
46 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
46 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
46 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21 | Santiago Professional Siding [Santiago]
46 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
46 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-14 | 2025-04-14
46 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | Santiago Professional Siding [Santiago]
46 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
46 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-04 | 2025-04-04
151Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
151Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-21 | 2025-04-21
151Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
151Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
151Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | JO Brothers [Richard]
151Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
151Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-10 | 2025-04-10
151Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-21 | 2025-01-21
151Trails at Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-27 | 2025-02-27
5 Gardner Farms | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-09-09 | 2025-09-09
5 Gardner Farms | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-11 | 2025-08-11
5 Gardner Farms | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-12 | 2025-08-12
5 Gardner Farms | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-08 | 2025-08-08 | Siding Boxing Construction [ARTURO]
5 Gardner Farms | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-07 | 2025-08-07 | Siding Boxing Construction [ARTURO]
5 Gardner Farms | Measurements | TRUE | 100 | Measured | 1 | 2025-06-23 | 2025-06-23
5 Gardner Farms | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-07 | 2025-08-07 | Siding Boxing Construction [ARTURO]
5 Gardner Farms | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-05 | 2025-06-05
5 Gardner Farms | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-11 | 2025-07-11
39 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
39 Watkins Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
39 Watkins Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
39 Watkins Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
39 Watkins Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | NC SIDING & REMODELING PRO LLC
39 Watkins Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-04-25 | 2025-04-25
39 Watkins Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
39 Watkins Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
39 Watkins Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
90 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
90 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
90 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
90 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21 | Santiago Professional Siding [Santiago]
90 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-16 | 2025-04-16 | Santiago Professional Siding [Santiago]
90 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-16 | 2025-04-16
90 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16 | Santiago Professional Siding [Santiago]
90 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
90 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-10 | 2025-03-10
89 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-06 | 2025-05-06
89 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-02 | 2025-05-02
89 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30
89 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28 | Santiago Professional Siding [Santiago]
89 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | Santiago Professional Siding [Santiago]
89 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-24 | 2025-04-24
89 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24 | Santiago Professional Siding [Santiago]
89 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
89 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
88 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
88 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
88 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
88 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07 | Santiago Professional Siding [Santiago]
88 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | Santiago Professional Siding [Santiago]
88 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-05-02 | 2025-05-02
88 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02 | Santiago Professional Siding [Santiago]
88 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-28 | 2025-02-28
88 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-25 | 2025-03-25
93 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
93 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
93 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
93 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
93 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Santiago Professional Siding [Santiago]
93 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
93 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-02 | 2025-04-02 | Santiago Professional Siding [Santiago]
93 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-29 | 2025-01-29
93 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
94 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-08 | 2025-04-08
94 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-04 | 2025-04-04
94 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
94 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago] ,Daniel's Construction & Repair [Roger]
94 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-26 | 2025-03-26 | Santiago Professional Siding [Santiago] ,Daniel's Construction & Repair [Roger]
94 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
94 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago] ,Daniel's Construction & Repair [Roger]
94 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-22 | 2025-01-22
94 Stonewood | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-22 | 2025-01-22
76 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-08 | 2025-04-08
76 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-04 | 2025-04-04
76 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
76 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Daniel's Construction & Repair [Roger]
76 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-26 | 2025-03-26 | Daniel's Construction & Repair [Roger]
76 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
76 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-26 | 2025-03-26 | Daniel's Construction & Repair [Roger]
76 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-22 | 2025-01-22
76 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
92 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
92 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-28 | 2025-03-28
92 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
92 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
92 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Santiago Professional Siding [Santiago]
92 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
92 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Santiago Professional Siding [Santiago]
92 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-14 | 2025-01-14
92 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-14 | 2025-01-14
73 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-22 | 2025-04-22
73 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-18 | 2025-04-18
73 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
73 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Daniel's Construction & Repair [Roger]
73 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | Daniel's Construction & Repair [Roger]
73 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
73 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-10 | 2025-04-10 | Daniel's Construction & Repair [Roger]
73 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-13 | 2025-02-13
73 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
125 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
125 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
125 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
125 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Jesus Construction
125 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
125 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-02-28 | 2025-02-28
125 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
125 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
125 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
81 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
81 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
81 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
81 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Jesus Construction
81 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
81 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-04-18 | 2025-04-18
81 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
81 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
81 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
83 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-30 | 2025-04-30
83 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
83 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24
83 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22
83 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-16 | 2025-04-16 | Jesus Construction
83 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-04-25 | 2025-04-25
83 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16
83 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
83 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
72 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-31 | 2025-03-31
72 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-27 | 2025-03-27
72 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25
72 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21 | Daniel's Construction & Repair [Roger]
72 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Daniel's Construction & Repair [Roger]
72 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
72 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Daniel's Construction & Repair [Roger]
72 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-14 | 2025-01-14
72 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
110 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
110 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-15 | 2025-04-15
110 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
110 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
110 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Mendez Siding & Boxing LLC
110 Hickory Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-03-27 | 2025-03-27
110 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08 | Mendez Siding & Boxing LLC
110 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-17 | 2025-01-17
110 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-25 | 2025-02-25
121 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12
121 Hickory Grove | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17 | Torres Painting Professional
121 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
121 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-15 | 2025-04-15
121 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
121 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Mendez Siding & Boxing LLC
121 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Mendez Siding & Boxing LLC
121 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-04-14 | 2025-04-14
121 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-08 | 2025-04-08 | Mendez Siding & Boxing LLC
121 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
121 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
6 Rollins Acres | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
6 Rollins Acres | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-17 | 2025-06-17
6 Rollins Acres | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
6 Rollins Acres | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
6 Rollins Acres | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-21 | 2025-05-21 | Hector Oliverio [Hector]
6 Rollins Acres | Measurements | TRUE | 100 | Measured | 1 | 2025-05-05 | 2025-05-05
6 Rollins Acres | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-21 | 2025-05-21
6 Rollins Acres | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
6 Rollins Acres | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-29 | 2025-05-29
5 Rollins Acre | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
5 Rollins Acre | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
5 Rollins Acre | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
5 Rollins Acre | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
5 Rollins Acre | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Hector Oliverio [Hector]
5 Rollins Acre | Measurements | TRUE | 100 | Measured | 1 | 2025-05-05 | 2025-05-05
5 Rollins Acre | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
5 Rollins Acre | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-14 | 2025-03-14
5 Rollins Acre | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-26 | 2025-05-26
10 Ballard Rd | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-11 | 2025-03-11
10 Ballard Rd | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-03 | 2025-03-03
10 Ballard Rd | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
10 Ballard Rd | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03 | Hector Oliverio [Hector]
10 Ballard Rd | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-28 | 2025-02-28 | Hector Oliverio [Hector]
10 Ballard Rd | Measurements | TRUE | 100 | Measured | 1 | 2025-02-11 | 2025-02-11
10 Ballard Rd | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Hector Oliverio [Hector]
10 Ballard Rd | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-13 | 2024-12-13
10 Ballard Rd | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
9 Ballard Rd | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-11 | 2025-03-11
9 Ballard Rd | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-03 | 2025-03-03
9 Ballard Rd | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
9 Ballard Rd | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03 | Hector Oliverio [Hector]
9 Ballard Rd | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-28 | 2025-02-28 | Hector Oliverio [Hector]
9 Ballard Rd | Measurements | TRUE | 100 | Measured | 1 | 2025-02-04 | 2025-02-04
9 Ballard Rd | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Hector Oliverio [Hector]
9 Ballard Rd | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-13 | 2024-12-13
9 Ballard Rd | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
171 Keith Hills | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
171 Keith Hills | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
171 Keith Hills | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
171 Keith Hills | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Mendez Siding & Boxing LLC
171 Keith Hills | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-26 | 2025-02-26 | Mendez Siding & Boxing LLC
171 Keith Hills | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
171 Keith Hills | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Mendez Siding & Boxing LLC
171 Keith Hills | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
171 Keith Hills | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
152 Preserve @ Jones Dairy | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
152 Preserve @ Jones Dairy | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | MTR Painting LLC [Moises]
152 Preserve @ Jones Dairy | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
152 Preserve @ Jones Dairy | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
152 Preserve @ Jones Dairy | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
152 Preserve @ Jones Dairy | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
152 Preserve @ Jones Dairy | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | H-Rojas Construction LLC [David]
152 Preserve @ Jones Dairy | Measurements | TRUE | 100 | Measured | 1 | 2025-04-10 | 2025-04-10
152 Preserve @ Jones Dairy | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31
152 Preserve @ Jones Dairy | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
152 Preserve @ Jones Dairy | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-27 | 2025-03-27
64 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
64 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
64 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
64 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16 | Hector Oliverio [Hector]
64 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Hector Oliverio [Hector]
64 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-04-01 | 2025-04-01
64 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | Hector Oliverio [Hector]
64 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
64 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-10 | 2025-03-10
10 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
10 Southern Estates | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-11 | 2025-06-11
10 Southern Estates | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
10 Southern Estates | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
10 Southern Estates | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-24 | 2025-04-24
10 Southern Estates | Measurements | FALSE | 0 | Measured | 1 | 2025-04-23 | 2025-04-23
10 Southern Estates | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-27 | 2025-05-27
10 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
10 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
146 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
146 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
146 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
146 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25
146 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-24 | 2025-03-24 | JO Brothers [Richard]
146 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-03-12 | 2025-03-12
146 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-25 | 2025-03-25
146 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-06 | 2025-01-06
146 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-25 | 2025-03-25
6 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-22 | 2025-04-22
6 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-14 | 2025-04-14
6 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
6 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14 | Hector Oliverio [Hector]
6 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-11 | 2025-04-11 | Hector Oliverio [Hector]
6 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
6 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-11 | 2025-04-11 | Hector Oliverio [Hector]
6 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
6 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-07 | 2025-03-07
82 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
82 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
82 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
82 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Jesus Construction
82 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Jesus Construction
82 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-02-14 | 2025-02-14
82 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-28 | 2025-05-28 | Jesus Construction
82 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-16 | 2025-01-16
82 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
380 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
380 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
380 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
380 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
380 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | JO Brothers [Richard]
380 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
380 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
380 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-28 | 2025-02-28
380 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-18 | 2025-04-18
100 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
100 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
100 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
100 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-01 | 2025-05-01
100 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-28 | 2025-04-28 | Delia Construction
100 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-20 | 2025-05-20
100 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
100 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
100 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
21 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
21 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
21 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
21 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16 | Delia Construction
21 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Delia Construction
21 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-14 | 2025-05-14
21 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-27 | 2025-06-27 | Delia Construction
21 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
21 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
85 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
85 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
85 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
85 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Delia Construction
85 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Delia Construction
85 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-29 | 2025-05-29
85 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09 | Delia Construction
85 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
85 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
50 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
50 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
50 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
50 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Delia Construction
50 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Delia Construction
50 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-19 | 2025-05-19
50 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Delia Construction
50 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-17 | 2025-02-17
50 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
2 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
2 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-04 | 2025-03-04
2 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
2 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Delia Construction
2 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | Delia Construction
2 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-30 | 2025-01-30
2 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-25 | 2025-02-25 | Delia Construction
2 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-05 | 2024-12-05
2 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
70 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06
70 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13 | Torres Painting Professional
69 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06
69 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14 | Torres Painting Professional
68 Stonewood | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06
68 Stonewood | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13 | Torres Painting Professional
172 Trails at Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
172 Trails at Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
172 Trails at Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
172 Trails at Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
172 Trails at Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-24 | 2025-03-24 | JO Brothers [Richard]
172 Trails at Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-03-24 | 2025-03-24
172 Trails at Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-14 | 2025-02-14
172 Trails at Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-07 | 2025-01-07
172 Trails at Young Farm | Lien # | FALSE | 0 | Lien # | 1 | 2025-01-07 | 2025-01-07
275 Oak Manor | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-21 | 2025-05-21
275 Oak Manor | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
275 Oak Manor | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17
275 Oak Manor | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
275 Oak Manor | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-12 | 2025-03-12 | H&M Remodeling [Fernando]
275 Oak Manor | Measurements | TRUE | 100 | Measured | 1 | 2025-02-11 | 2025-02-11
275 Oak Manor | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-12 | 2025-03-12
275 Oak Manor | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-02 | 2025-01-02
275 Oak Manor | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-02 | 2025-01-02
129 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-10 | 2025-04-10
129 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
129 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
129 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02 | Jesus Construction
129 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Jesus Construction
129 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-03-25 | 2025-03-25
129 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-14 | 2025-05-14 | Jesus Construction
129 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
129 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
128 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
128 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
128 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
128 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Jesus Construction
128 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
128 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-02-27 | 2025-02-27
128 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Jesus Construction
128 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
128 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
17 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
17 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
16 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
16 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
15 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
15 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
14 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
14 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
13 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
13 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Torres Painting Professional
18 Chapel Oaks | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-19 | 2025-06-19
18 Chapel Oaks | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
18 Chapel Oaks | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
18 Chapel Oaks | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
18 Chapel Oaks | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-30 | 2025-04-30
18 Chapel Oaks | Measurements | FALSE | 0 | Measured | 1 | 2025-04-29 | 2025-04-29
18 Chapel Oaks | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
18 Chapel Oaks | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-14 | 2025-04-14
18 Chapel Oaks | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-14 | 2025-04-14
16 Chapel Oaks | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-23 | 2025-06-23
16 Chapel Oaks | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-19 | 2025-06-19
16 Chapel Oaks | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
16 Chapel Oaks | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
16 Chapel Oaks | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-02 | 2025-05-02
16 Chapel Oaks | Measurements | FALSE | 0 | Measured | 1 | 2025-05-01 | 2025-05-01
16 Chapel Oaks | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
16 Chapel Oaks | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-14 | 2025-04-14
16 Chapel Oaks | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-14 | 2025-04-14
20 Chapel Oaks | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-20 | 2025-06-20
20 Chapel Oaks | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
20 Chapel Oaks | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16
20 Chapel Oaks | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
20 Chapel Oaks | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-01 | 2025-05-01
20 Chapel Oaks | Measurements | FALSE | 0 | Measured | 1 | 2025-04-30 | 2025-04-30
20 Chapel Oaks | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
20 Chapel Oaks | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-14 | 2025-04-14
20 Chapel Oaks | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-14 | 2025-04-14
75 Harvest Meadows | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
75 Harvest Meadows | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
75 Harvest Meadows | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
75 Harvest Meadows | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21 | Rodriguez Contracting LLC [Hemeny]
75 Harvest Meadows | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-18 | 2025-04-18 | Rodriguez Contracting LLC [Hemeny]
75 Harvest Meadows | Measurements | TRUE | 100 | Measured | 1 | 2025-04-21 | 2025-04-21 | Rodriguez Contracting LLC [Hemeny]
75 Harvest Meadows | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21 | Rodriguez Contracting LLC [Hemeny]
75 Harvest Meadows | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
75 Harvest Meadows | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-11 | 2025-03-11
5 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-13 | 2025-06-13
5 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-05 | 2025-06-05
5 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-09 | 2025-06-09
5 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-05 | 2025-06-05
5 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-02 | 2025-06-02 | NC Stark Construction Inc. [Amando]
5 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-06-02 | 2025-06-02
5 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-28 | 2025-05-28
5 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-16 | 2025-05-16
5 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-26 | 2025-05-26
42 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-20 | 2025-06-20
42 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
42 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-16 | 2025-06-16
42 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
42 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-01 | 2025-05-01
42 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-04-30 | 2025-04-30
42 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
42 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
42 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
19 Chapel Oaks | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-19 | 2025-06-19
19 Chapel Oaks | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-17 | 2025-06-17
19 Chapel Oaks | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
19 Chapel Oaks | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-11 | 2025-06-11
19 Chapel Oaks | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-30 | 2025-04-30
19 Chapel Oaks | Measurements | FALSE | 0 | Measured | 1 | 2025-04-29 | 2025-04-29
19 Chapel Oaks | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
19 Chapel Oaks | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-14 | 2025-04-14
19 Chapel Oaks | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-14 | 2025-04-14
90 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-10 | 2025-04-10
90 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
90 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
90 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02 | Hector Oliverio [Hector]
90 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Hector Oliverio [Hector]
90 Falls of The Cape | Measurements | TRUE | 100 | Measured | 1 | 2025-03-17 | 2025-03-17
90 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Hector Oliverio [Hector]
90 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-16 | 2025-01-16
90 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-28 | 2025-02-28
89 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-26 | 2025-08-26
89 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-09-04 | 2025-09-04
89 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-20 | 2025-08-20
89 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-08-18 | 2025-08-18
89 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-08-14 | 2025-08-14
89 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
89 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-08-13 | 2025-08-13
89 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-09 | 2025-06-09
89 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-22 | 2025-07-22
88 Falls of The Cape | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-04-08 | 2025-04-08
88 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
88 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
88 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Hector Oliverio [Hector]
88 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-28 | 2025-03-28 | Hector Oliverio [Hector]
88 Falls of The Cape | Measurements | TRUE | 100 | Measured | 1 | 2025-03-11 | 2025-03-11
88 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28 | Hector Oliverio [Hector]
88 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-21 | 2025-01-21
88 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-05 | 2025-03-05
87 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-20 | 2025-05-20
87 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
87 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-14 | 2025-05-14
87 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
87 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-09 | 2025-05-09 | Hector Oliverio [Hector]
87 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-03 | 2025-04-03
87 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-09 | 2025-05-09
87 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-12 | 2025-03-12
87 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-24 | 2025-04-24
86 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
86 Falls of The Cape | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-05 | 2025-06-05
86 Falls of The Cape | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
86 Falls of The Cape | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
86 Falls of The Cape | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-18 | 2025-04-18
86 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
86 Falls of The Cape | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28
86 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-12 | 2025-02-12
86 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
85 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-09 | 2025-06-09
85 Falls of The Cape | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-05 | 2025-06-05
85 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-03 | 2025-06-03
85 Falls of The Cape | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
85 Falls of The Cape | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-18 | 2025-04-18
85 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
85 Falls of The Cape | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-24 | 2025-03-24
85 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-03 | 2025-02-03
85 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
97 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-17 | 2025-03-17
97 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
97 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
97 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
97 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-06 | 2025-03-06 | Hector Oliverio [Hector]
97 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
97 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-06 | 2025-03-06 | Hector Oliverio [Hector]
97 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
97 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
96 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-17 | 2025-03-17
96 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
96 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
96 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
96 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-06 | 2025-03-06 | Hector Oliverio [Hector]
96 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
96 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-06 | 2025-03-06 | Hector Oliverio [Hector]
96 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
96 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
93 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
93 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-14 | 2025-02-14
93 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12
93 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | Hector Oliverio [Hector]
93 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
93 Falls of The Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-04-10 | 2025-04-10
93 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
93 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-29 | 2024-11-29
93 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-05 | 2025-02-05
92 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
92 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-24 | 2025-02-24
92 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12
92 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | Hector Oliverio [Hector]
92 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
92 Falls of The Cape | Measurements | TRUE | 100 | Measured | 1 | 2025-01-17 | 2025-01-17
92 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
92 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-29 | 2024-11-29
92 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-05 | 2025-02-05
8 Ballard Road | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
8 Ballard Road | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
8 Ballard Road | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
8 Ballard Road | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Hector Oliverio [Hector]
8 Ballard Road | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-27 | 2025-02-27 | Hector Oliverio [Hector]
8 Ballard Road | Measurements | TRUE | 100 | Measured | 1 | 2025-02-04 | 2025-02-04
8 Ballard Road | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12 | Hector Oliverio [Hector]
8 Ballard Road | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-19 | 2024-12-19
8 Ballard Road | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
2 Eller Farms 2 | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-16 | 2025-04-16
2 Eller Farms 2 | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
2 Eller Farms 2 | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
2 Eller Farms 2 | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
2 Eller Farms 2 | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | On Top Contracting LLC
2 Eller Farms 2 | Measurements | TRUE | 100 | Measured | 1 | 2025-03-13 | 2025-03-13
2 Eller Farms 2 | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-14 | 2025-04-14 | On Top Contracting LLC
2 Eller Farms 2 | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
2 Eller Farms 2 | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
37 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
37 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
36 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
36 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
37 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
37 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
37 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
37 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
37 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
37 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
37 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
37 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
37 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
20 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
20 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Lopez Painting Group Inc
36 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
36 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
36 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
36 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
36 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
36 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
36 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
36 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
36 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
35 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
35 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
35 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
35 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
35 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
35 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
35 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
35 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
35 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
35 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
35 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
34 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
34 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
34 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
34 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
34 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
34 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
34 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
34 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-15 | 2025-04-15
34 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
34 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
34 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
33 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
33 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22 | Torres Painting Professional
33 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
33 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
33 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
33 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
33 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
33 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
33 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
33 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
33 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
32 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
32 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
32 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
32 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-01 | 2025-05-01
32 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
32 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Santiago Professional Siding [Santiago]
32 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
32 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-22 | 2025-04-22
32 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Santiago Professional Siding [Santiago]
32 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
32 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-31 | 2025-03-31
89 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
89 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
89 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
89 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
89 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-26 | 2025-03-26 | NC Stark Construction Inc. [Amando]
89 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-01-30 | 2025-01-30
89 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-18 | 2025-06-18
89 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-08 | 2024-11-08
89 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
49 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-05 | 2025-06-05
49 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-24 | 2025-06-24
49 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
49 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
49 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-16 | 2025-04-16
49 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-05-28 | 2025-05-28
49 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
49 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
49 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
60 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-05 | 2025-06-05
60 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-24 | 2025-06-24
60 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30
60 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-28 | 2025-05-28
60 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-16 | 2025-04-16
60 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-04-15 | 2025-04-15
60 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05
60 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
60 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
55 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
55 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
55 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
55 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
55 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-21 | 2025-04-21 | JO Brothers [Richard]
55 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
55 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21
55 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-10 | 2025-04-10
55 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-01 | 2025-05-01
7 Ballard Road | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
7 Ballard Road | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-03 | 2025-03-03
7 Ballard Road | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
7 Ballard Road | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Hector Oliverio [Hector]
7 Ballard Road | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-27 | 2025-02-27 | Hector Oliverio [Hector]
7 Ballard Road | Measurements | FALSE | 0 | Measured | 1 | 2025-04-11 | 2025-04-11
7 Ballard Road | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19 | Hector Oliverio [Hector]
7 Ballard Road | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
7 Ballard Road | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
346 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
346 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06 | Lopez Painting Group Inc
346 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
346 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
346 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
346 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
346 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | JO Brothers [Richard]
346 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
346 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
346 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-29 | 2025-01-29
346 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-27 | 2025-02-27
49 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
49 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
49 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
49 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
49 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | Delia Construction
49 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
49 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-26 | 2025-06-26 | Delia Construction
49 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
49 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
6 Ballard Road | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
6 Ballard Road | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-05 | 2025-03-05
6 Ballard Road | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
6 Ballard Road | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Hector Oliverio [Hector]
6 Ballard Road | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-26 | 2025-02-26 | Hector Oliverio [Hector]
6 Ballard Road | Measurements | TRUE | 100 | Measured | 1 | 2025-01-30 | 2025-01-30
6 Ballard Road | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-26 | 2025-02-26 | Hector Oliverio [Hector]
6 Ballard Road | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
6 Ballard Road | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
4551 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
4551 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-08 | 2025-05-08
4551 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
4551 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
4551 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | JO Brothers [Richard]
4551 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-04-08 | 2025-04-08
4551 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
4551 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
4551 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
109 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-28 | 2025-01-28
109 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Torres Painting Professional
109 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
109 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-21 | 2025-02-21
109 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
109 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
109 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-14 | 2025-03-14 | JO Brothers [Richard]
109 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
109 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-25 | 2025-03-25
109 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-02 | 2025-01-02
109 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
18 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
18 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
18 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-18 | 2025-03-18
18 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
18 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-13 | 2025-03-13 | J&A Construction
18 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
18 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-25 | 2025-02-25
18 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
18 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-09 | 2025-01-09
16 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
16 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
16 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
16 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-25 | 2025-02-25
16 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
16 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
16 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-22 | 2025-01-22
16 Williams Grove | Ordered | FALSE | 0 | Ordered | 1 | 2024-12-24 | 2024-12-24
16 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-24 | 2024-12-24
46 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
46 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-12 | 2025-03-12
46 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
46 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
46 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | J&A Construction
46 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
46 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13
46 Williams Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
46 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-03 | 2025-01-03
31 Williams Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
31 Williams Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-20 | 2025-05-20
31 Williams Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
31 Williams Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
31 Williams Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-08 | 2025-05-08 | J&A Construction
31 Williams Grove | Measurements | TRUE | 100 | Measured | 1 | 2025-05-07 | 2025-05-07
31 Williams Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-08 | 2025-05-08
31 Williams Grove | Ordered | TRUE | 100 | Ordered | 7 | 2025-03-06 | 2025-03-14
31 Williams Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-29 | 2025-04-29
4532 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
4532 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-17 | 2025-03-17
4532 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
4532 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
4532 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-05 | 2025-03-05 | JO Brothers [Richard]
4532 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-03-05 | 2025-03-05
4532 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-10 | 2025-02-10
4532 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-01 | 2025-01-01
4532 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-01 | 2025-01-01
12 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
12 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31 | Torres Painting Professional
11 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
11 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31 | Torres Painting Professional
10 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
9 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
9 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31 | Torres Painting Professional
8 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
8 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31 | Torres Painting Professional
7 Twinleaf Townes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
7 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31 | Torres Painting Professional
76 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
76 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
75 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03
75 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
74 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03
74 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
73 Twinleaf Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03
73 Twinleaf Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Torres Painting Professional
9 North Lakes at South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
9 North Lakes at South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21 | Lopez Painting Group Inc
8 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
8 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | Lopez Painting Group Inc
7 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
7 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Lopez Painting Group Inc
65 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
65 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Lopez Painting Group Inc
61 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
61 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Lopez Painting Group Inc
60 North Lakes at South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
60 North Lakes at South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Lopez Painting Group Inc
59 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
59 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Lopez Painting Group Inc
5 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
5 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | Lopez Painting Group Inc
376 Paddington Station 60' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
376 Paddington Station 60' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11 | MTR Painting LLC [Moises]
3 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
3 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Lopez Painting Group Inc
28 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
28 Hickory Grove | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-23 | 2025-01-23
2 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
2 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Lopez Painting Group Inc
19 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
19 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-23 | 2025-01-23
183 Trails @ Young Farm | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
183 Trails @ Young Farm | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
18 Forestville TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
18 Forestville TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-23 | 2025-01-23
150 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
150 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17 | Torres Painting Professional
147 Trails @ Young Farm | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
147 Trails @ Young Farm | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17 | Torres Painting Professional
13 North Lakes at South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
13 North Lakes at South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Lopez Painting Group Inc
45 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
45 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
44 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
44 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
12 North Lakes @ South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
12 North Lakes @ South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Lopez Painting Group Inc
43 Page Townes TH | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
43 Page Townes TH | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
114 Hickory Grove | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
114 Hickory Grove | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-23 | 2025-01-23
113 Hickory Grove | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
113 Hickory Grove | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-23 | 2025-01-23
11 North Lakes at South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-24 | 2025-01-24
11 North Lakes at South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21 | Lopez Painting Group Inc
383 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
383 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Lopez Painting Group Inc
304 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20
304 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06 | Lopez Painting Group Inc
383 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
383 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
383 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
383 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
383 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-25 | 2025-04-25 | JO Brothers [Richard]
383 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
383 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-25 | 2025-04-25
383 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-17 | 2025-02-17
383 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
23 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17
23 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Lopez Painting Group Inc
23 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
23 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
23 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
23 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Delia Construction
23 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-21 | 2025-04-21 | Delia Construction
23 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-08 | 2025-05-08
23 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21 | Delia Construction
23 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-10 | 2025-02-10
23 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-27 | 2025-03-27
19 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24 | Lopez Painting Group Inc
20 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
20 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-27 | 2025-03-27
20 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
20 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
20 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
20 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-04-24 | 2025-04-24
20 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
20 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
20 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
19 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
19 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
19 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
19 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
19 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16 | Delia Construction
19 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-15 | 2025-04-15 | Delia Construction
19 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-05-09 | 2025-05-09
19 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-23 | 2025-06-23 | Delia Construction
19 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-05 | 2025-02-05
19 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
18 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19
18 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21 | Lopez Painting Group Inc
18 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
18 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
18 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
18 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
18 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
18 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-12 | 2025-03-12
18 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
18 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
18 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-14 | 2025-03-14
71 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-25 | 2025-03-25
71 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-21 | 2025-03-21
71 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19
71 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17 | Daniel's Construction & Repair [Roger]
71 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-10 | 2025-03-10 | Daniel's Construction & Repair [Roger]
71 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
71 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-10 | 2025-03-10 | Daniel's Construction & Repair [Roger]
71 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-06 | 2025-01-06
71 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-06 | 2025-01-06
45 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
45 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
45 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
45 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
45 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
45 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-03 | 2025-04-03
45 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
45 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-31 | 2025-01-31
45 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
44 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
44 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
44 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
44 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
44 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
44 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-03 | 2025-04-03
44 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
44 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-31 | 2025-01-31
44 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
43 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
43 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
43 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
43 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
43 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
43 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-03 | 2025-04-03
43 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-03 | 2025-04-03 | Santiago Professional Siding [Santiago]
43 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
43 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-21 | 2025-03-21
11 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
11 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | Torres Painting Professional
36 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
36 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
36 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
36 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
36 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
36 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | J&A Construction
36 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
36 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-13 | 2025-03-13
36 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
36 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
36 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
11 Mulhollem | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
11 Mulhollem | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
11 Mulhollem | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
11 Mulhollem | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07
11 Mulhollem | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Siding Boxing Construction [ARTURO]
11 Mulhollem | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
11 Mulhollem | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31
11 Mulhollem | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-15 | 2025-01-15
11 Mulhollem | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-17 | 2025-03-17
35 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
35 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
35 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
35 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
35 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
35 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | J&A Construction
35 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
35 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
35 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
35 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
35 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
34 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
34 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
34 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
34 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
34 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
34 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | J&A Construction
34 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
34 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-17 | 2025-03-17
34 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05 | Antonio Bailey,J&A Construction
34 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
34 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
33 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
33 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
33 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
33 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
33 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
33 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | J&A Construction
33 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
33 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
33 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
33 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
33 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
32 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
32 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-30 | 2025-05-30 | Torres Painting Professional
32 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-13 | 2025-05-13
32 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
32 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
32 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
32 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
32 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
32 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-05 | 2025-05-05 | J&A Construction
32 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
32 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
31 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
31 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | Torres Painting Professional
31 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
31 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
31 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
31 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
31 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
31 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-04-11 | 2025-04-11 | J&A Construction
31 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
31 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-30 | 2025-04-30
31 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-11 | 2025-06-11
30 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
30 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | Torres Painting Professional
30 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
30 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
30 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
30 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
30 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
30 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20 | J&A Construction
30 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
30 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-30 | 2025-04-30
30 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-11 | 2025-06-11
29 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
29 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16 | Torres Painting Professional
29 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
29 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-26 | 2025-06-26
29 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
29 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
29 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
29 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
29 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-12 | 2025-06-12 | J&A Construction
29 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-30 | 2025-04-30
29 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-11 | 2025-06-11
28 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
28 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
28 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-27 | 2025-06-27
28 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-07-15 | 2025-07-15
28 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-23 | 2025-06-23
28 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
28 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
28 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
28 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-19 | 2025-06-19 | J&A Construction
28 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-07 | 2025-05-07
28 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-18 | 2025-06-18
11 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
11 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
11 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
11 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
11 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
11 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
11 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | J&A Construction
11 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
11 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
10 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
10 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
74 Archer's Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-10 | 2025-04-10
74 Archer's Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
74 Archer's Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
74 Archer's Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02 | Rodriguez Contracting LLC [Hemeny]
74 Archer's Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-28 | 2025-03-28 | Rodriguez Contracting LLC [Hemeny]
74 Archer's Park | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31 | Rodriguez Contracting LLC [Hemeny]
74 Archer's Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Rodriguez Contracting LLC [Hemeny]
74 Archer's Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-29 | 2025-01-29
74 Archer's Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-29 | 2025-01-29
73 Archer's Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-27 | 2025-05-27
73 Archer's Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
73 Archer's Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-21 | 2025-05-21
73 Archer's Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19 | Requena Siding [Jairo]
73 Archer's Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-15 | 2025-05-15 | Requena Siding [Jairo]
73 Archer's Park | Measurements | TRUE | 100 | Measured | 1 | 2025-05-15 | 2025-05-15 | Requena Siding [Jairo]
73 Archer's Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-15 | 2025-05-15 | Requena Siding [Jairo]
73 Archer's Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-18 | 2025-03-18
73 Archer's Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-18 | 2025-03-18
10 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
10 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
10 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
10 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
10 Raven Ridge Place TH | Siding Installation Start, | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
10 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
10 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | J&A Construction
10 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
10 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
9 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
9 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
9 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
9 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
9 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
9 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
9 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
9 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
9 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | J&A Construction
9 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
9 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
8 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
8 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
7 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
7 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
6 Raven Ridge Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
6 Raven Ridge Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09 | Torres Painting Professional
8 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
8 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
8 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
8 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
8 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
8 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
8 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | J&A Construction
8 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
8 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
7 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
7 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
7 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
7 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
7 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
7 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
7 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | J&A Construction
7 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
7 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
6 Raven Ridge Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
6 Raven Ridge Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-13 | 2025-03-13
6 Raven Ridge Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
6 Raven Ridge Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | J&A Construction
6 Raven Ridge Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | J&A Construction
6 Raven Ridge Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
6 Raven Ridge Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-04 | 2025-02-04
6 Raven Ridge Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-27 | 2024-12-27
6 Raven Ridge Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-27 | 2024-12-27
88 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
88 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Lopez Painting Group Inc
87 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
87 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25 | Lopez Painting Group Inc
16 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
16 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Lopez Painting Group Inc
75 Olive Grove SF | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15
75 Olive Grove SF | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15 | Torres Painting Professional
150 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-30 | 2025-04-30
150 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-24 | 2025-02-24
150 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20
150 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-18 | 2025-02-18
150 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-14 | 2025-02-14 | JO Brothers [Richard]
150 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-02-14 | 2025-02-14
150 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-14 | 2025-01-14
150 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
150 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-12 | 2024-12-12
86 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
86 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Lopez Painting Group Inc
22 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
22 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21 | Lopez Painting Group Inc
17 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19
17 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Lopez Painting Group Inc
15 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
15 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Lopez Painting Group Inc
14 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
14 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
13 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
13 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25 | Lopez Painting Group Inc
348 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
348 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
348 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
348 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
348 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-10 | 2025-04-10 | JO Brothers [Richard]
348 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
348 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-10 | 2025-04-10
348 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
348 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-24 | 2025-03-24
304 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
304 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-13 | 2025-05-13
304 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
304 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
304 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | JO Brothers [Richard]
304 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
304 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
304 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
304 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-02 | 2025-04-02
88 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
88 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
88 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
88 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
88 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
88 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
88 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
88 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-22 | 2025-01-22
88 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-22 | 2025-01-22
87 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-21 | 2025-03-21
87 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
87 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17
87 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13 | Delia Construction
87 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-12 | 2025-03-12 | Delia Construction
87 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
87 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-12 | 2025-03-12 | Delia Construction
87 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
87 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
86 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
86 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
86 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
86 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
86 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
86 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
86 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
86 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-21 | 2025-01-21
86 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-21 | 2025-01-21
22 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-25 | 2025-03-25
22 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-19 | 2025-03-19
22 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19
22 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
22 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-14 | 2025-03-14 | Delia Construction
22 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
22 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-14 | 2025-03-14 | Delia Construction
22 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-14 | 2025-01-14
22 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-14 | 2025-01-14
17 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-11 | 2025-04-11
17 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
17 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07
17 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Delia Construction
17 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
17 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
17 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
17 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
17 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-30 | 2025-01-30
16 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-11 | 2025-04-11
16 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
16 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07
16 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Delia Construction
16 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
16 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
16 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
16 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-28 | 2025-01-28
16 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-28 | 2025-01-28
15 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
15 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-09 | 2025-04-09
15 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
15 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10 | Delia Construction
15 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Delia Construction
15 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
15 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27 | Delia Construction
15 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
15 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-23 | 2025-01-23
14 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
14 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
14 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
14 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
14 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
14 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
14 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
14 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
14 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
13 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-21 | 2025-03-21
13 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
13 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17
13 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13 | Delia Construction
13 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-11 | 2025-03-11 | Delia Construction
13 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14
13 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-11 | 2025-03-11 | Delia Construction
13 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-07 | 2025-01-07
13 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-07 | 2025-01-07
4533 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
4533 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-17 | 2025-03-17
4533 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
4533 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
4533 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-05 | 2025-03-05 | JO Brothers [Richard]
4533 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-03-05 | 2025-03-05
4533 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-05 | 2025-03-05
4533 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
4533 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-03 | 2025-01-03
80 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-13 | 2025-03-13
80 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
80 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07
80 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05 | Jesus Construction
80 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Jesus Construction
80 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-03-26 | 2025-03-26
80 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Jesus Construction
80 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
80 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-24 | 2024-12-24
50 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-10 | 2025-06-10
50 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-23 | 2025-06-23
50 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04
50 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
50 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-23 | 2025-05-23 | Wohlstand Construction LLC
50 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-24 | 2025-04-24
50 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
50 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-04 | 2025-06-04
50 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-09 | 2025-06-09
79 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
79 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
79 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
79 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Jesus Construction
79 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-27 | 2025-02-27 | Jesus Construction
79 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-03-14 | 2025-03-14
79 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-27 | 2025-02-27 | Jesus Construction
79 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
79 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
84 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
84 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
84 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
84 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
84 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
84 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
84 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
84 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
84 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
83 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
83 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
83 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
83 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
83 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
83 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
83 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
83 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
83 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
82 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
82 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
82 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
82 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
82 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
82 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
82 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
82 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
82 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
81 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
81 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-28 | 2025-05-28
81 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
81 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
81 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
81 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
81 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
81 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
81 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
80 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
80 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
80 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
80 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
80 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
80 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
80 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
80 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
80 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
79 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
79 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
79 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
79 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Jimenez Services
79 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
79 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-05-20 | 2025-05-20
79 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-20 | 2025-05-20 | Jimenez Services
79 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-24 | 2025-04-24
79 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-23 | 2025-05-23
70 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-31 | 2025-03-31
70 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-21 | 2025-02-21
70 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19
70 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17 | Santiago Professional Siding [Santiago]
70 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-12 | 2025-02-12 | Santiago Professional Siding [Santiago]
70 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-02-12 | 2025-02-12
70 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-12 | 2025-02-12 | Santiago Professional Siding [Santiago]
70 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
70 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-11 | 2024-12-11
78 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
78 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
78 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
78 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Jesus Construction
78 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-26 | 2025-02-26 | Jesus Construction
78 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-04-11 | 2025-04-11
78 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-26 | 2025-02-26 | Jesus Construction
78 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-29 | 2024-11-29
78 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-29 | 2024-11-29
31 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
31 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
31 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
31 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
31 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
31 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
31 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
31 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
31 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
31 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
31 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
30 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
30 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
30 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
30 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
30 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
30 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
30 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
30 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
30 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
30 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
30 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
29 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
29 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
29 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
29 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
29 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
29 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
29 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
29 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
29 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
29 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
29 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
28 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
28 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
28 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
28 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
28 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
28 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
28 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
28 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
28 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
28 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
28 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
27 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
27 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
27 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
27 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
27 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
27 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
27 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
27 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
27 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Santiago Professional Siding [Santiago]
27 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
27 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
26 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
26 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Torres Painting Professional
26 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
26 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
26 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
26 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Santiago Professional Siding [Santiago]
26 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-19 | 2025-03-19 | Santiago Professional Siding [Santiago]
26 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-19 | 2025-03-19
26 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-19 | 2025-03-19 | Santiago Professional Siding [Santiago]
26 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-14 | 2025-01-14
26 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-14 | 2025-01-14
233 Oak Manors | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
233 Oak Manors | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
233 Oak Manors | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
233 Oak Manors | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
233 Oak Manors | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
233 Oak Manors | Measurements | TRUE | 100 | Measured | 1 | 2025-02-19 | 2025-02-19
233 Oak Manors | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-31 | 2025-07-31
233 Oak Manors | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-13 | 2025-06-13
233 Oak Manors | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-02 | 2025-05-02
76 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-17 | 2025-02-17
76 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-21 | 2025-02-21
76 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-11 | 2025-02-11
76 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07 | Jesus Construction
76 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-05 | 2025-02-05 | Jesus Construction
76 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-01-30 | 2025-01-30
76 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-05 | 2025-02-05 | Jesus Construction
76 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-06 | 2024-12-06
76 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-06 | 2024-12-06
75 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-20 | 2025-02-20
75 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
75 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14
75 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12 | Jesus Construction
75 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-10 | 2025-02-10 | Jesus Construction
75 River Glen | Measurements | TRUE | 100 | Measured | 1 | 2025-01-30 | 2025-01-30
75 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-10 | 2025-02-10 | Jesus Construction
75 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
75 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-11 | 2024-12-11
77 River Glen | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-06 | 2025-03-06
77 River Glen | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
77 River Glen | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
77 River Glen | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26 | Jesus Construction
77 River Glen | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | Jesus Construction
77 River Glen | Measurements | FALSE | 0 | Measured | 1 | 2025-03-14 | 2025-03-14
77 River Glen | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-25 | 2025-02-25 | Jesus Construction
77 River Glen | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
77 River Glen | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
49 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-04 | 2025-04-04
49 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
49 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
49 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27 | Hector Oliverio [Hector]
49 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-26 | 2025-03-26 | Hector Oliverio [Hector]
49 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
49 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-26 | 2025-03-26 | Hector Oliverio [Hector]
49 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
49 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-23 | 2025-01-23
48 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-19 | 2025-03-19
48 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
48 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13
48 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11 | Hector Oliverio [Hector]
48 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-10 | 2025-03-10 | Hector Oliverio [Hector]
48 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
48 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-10 | 2025-03-10 | Hector Oliverio [Hector]
48 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-06 | 2025-01-06
48 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-06 | 2025-01-06
1 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
1 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
1 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
1 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Hector Oliverio [Hector]
1 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
1 Southern Estates | Measurements | FALSE | 0 | Measured | 1 | 2025-03-07 | 2025-03-07
1 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
1 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
1 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-03 | 2025-01-03
19 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
19 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
19 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
19 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
19 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-06 | 2025-03-06
19 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-03-05 | 2025-03-05
19 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
19 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-27 | 2025-05-27
19 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-27 | 2025-05-27
18 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
18 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
18 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
18 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
18 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-06 | 2025-03-06
18 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-03-05 | 2025-03-05
18 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
18 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-27 | 2025-05-27
18 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-27 | 2025-05-27
17 Forestville TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
17 Forestville TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
17 Forestville TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
17 Forestville TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
17 Forestville TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-06 | 2025-03-06
17 Forestville TH | Measurements | FALSE | 0 | Measured | 1 | 2025-03-05 | 2025-03-05
17 Forestville TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
17 Forestville TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-27 | 2025-05-27
17 Forestville TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-05-27 | 2025-05-27
28 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
28 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
28 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
28 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Mendez Siding & Boxing LLC
28 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | Mendez Siding & Boxing LLC
28 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-04-02 | 2025-04-02
28 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06 | Mendez Siding & Boxing LLC
28 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-20 | 2024-12-20
28 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
60 North Lakes at South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
60 North Lakes at South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
60 North Lakes at South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
60 North Lakes at South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
60 North Lakes at South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
60 North Lakes at South Lakes | Measurements | FALSE | 0 | Measured | 1 | 2025-05-12 | 2025-05-12
60 North Lakes at South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
60 North Lakes at South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
60 North Lakes at South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
11 North Lakes at South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
11 North Lakes at South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
11 North Lakes at South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
11 North Lakes at South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
11 North Lakes at South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
11 North Lakes at South Lakes | Measurements | FALSE | 0 | Measured | 1 | 2025-05-14 | 2025-05-14
11 North Lakes at South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
11 North Lakes at South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-30 | 2024-12-30
11 North Lakes at South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-30 | 2024-12-30
9 North Lakes at South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
9 North Lakes at South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
9 North Lakes at South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
9 North Lakes at South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
9 North Lakes at South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
9 North Lakes at South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-24 | 2025-03-24
9 North Lakes at South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
9 North Lakes at South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-19 | 2025-02-19
9 North Lakes at South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-19 | 2025-02-19
13 North Lakes at South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
13 North Lakes at South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
13 North Lakes at South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
13 North Lakes at South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Delia Construction
13 North Lakes at South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-19 | 2025-03-19 | Delia Construction
13 North Lakes at South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-18 | 2025-03-18
13 North Lakes at South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-19 | 2025-03-19 | Delia Construction
13 North Lakes at South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-13 | 2025-02-13
13 North Lakes at South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-13 | 2025-02-13
4549 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
4549 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
4549 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
4549 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
4549 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | JO Brothers [Richard]
4549 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-02-11 | 2025-02-11
4549 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-25 | 2025-02-25
4549 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-13 | 2025-01-13
4549 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-13 | 2025-01-13
4550 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
4550 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-07 | 2025-03-07
4550 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
4550 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
4550 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | JO Brothers [Richard]
4550 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
4550 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-16 | 2025-01-16
4550 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-02 | 2024-12-02
4550 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-02 | 2024-12-02
4534 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
4534 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-19 | 2025-02-19
4534 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
4534 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
4534 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-28 | 2025-01-28 | JO Brothers [Richard]
4534 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-01-15 | 2025-01-15
4534 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2024-12-25 | 2024-12-25
4534 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-26 | 2024-11-26
4534 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-26 | 2024-11-26
2 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-24 | 2025-02-24
2 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
2 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-18 | 2025-02-18
2 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14
2 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
2 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-01-16 | 2025-01-16
2 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
2 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-28 | 2024-11-28
2 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-28 | 2024-11-28
11 Providence Oaks 30' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-10 | 2025-01-10
11 Providence Oaks 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
11 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-08 | 2025-04-08
11 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
11 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
11 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Delia Construction
11 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Delia Construction
11 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-02-26 | 2025-02-26
11 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27 | Delia Construction
11 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
11 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-23 | 2025-01-23
44 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-23 | 2025-06-23
44 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-08-05 | 2025-08-05
44 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-17 | 2025-06-17
44 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-06-13 | 2025-06-13
44 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-06-11 | 2025-06-11 | Hector Oliverio [Hector]
44 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
44 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-11 | 2025-06-11
44 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-12 | 2025-05-12
44 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-23 | 2025-06-23
104 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
104 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
104 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
104 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Daniel's Construction & Repair [Roger]
104 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Daniel's Construction & Repair [Roger]
104 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
104 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Daniel's Construction & Repair [Roger]
104 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
104 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-17 | 2024-12-17
103 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
103 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
103 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
103 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Daniel's Construction & Repair [Roger]
103 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-05 | 2025-03-05 | Daniel's Construction & Repair [Roger]
103 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-03-05 | 2025-03-05
103 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-05 | 2025-03-05 | Daniel's Construction & Repair [Roger]
103 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-01 | 2025-01-01
103 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-01 | 2025-01-01
102 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-11 | 2025-03-11
102 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-07 | 2025-03-07
102 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
102 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03 | Daniel's Construction & Repair [Roger]
102 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-27 | 2025-02-27 | Daniel's Construction & Repair [Roger]
102 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-02-28 | 2025-02-28
102 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-28 | 2025-02-28 | Daniel's Construction & Repair [Roger]
102 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
102 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
69 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
69 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
69 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 2 | 2025-02-10 | 2025-02-11
69 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07 | Santiago Professional Siding [Santiago]
69 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-05 | 2025-02-05 | Santiago Professional Siding [Santiago]
69 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-02-05 | 2025-02-05
69 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-05 | 2025-02-05 | Santiago Professional Siding [Santiago]
69 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-13 | 2024-12-13
69 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-13 | 2024-12-13
68 Stonewood | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
68 Stonewood | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
68 Stonewood | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
68 Stonewood | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | Santiago Professional Siding [Santiago]
68 Stonewood | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-07 | 2025-02-07 | Santiago Professional Siding [Santiago]
68 Stonewood | Measurements | TRUE | 100 | Measured | 1 | 2025-02-07 | 2025-02-07
68 Stonewood | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-07 | 2025-02-07
68 Stonewood | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-06 | 2024-12-06
68 Stonewood | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-06 | 2024-12-06
43 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-21 | 2025-02-21
43 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
43 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17
43 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
43 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-12 | 2025-02-12 | Hector Oliverio [Hector]
43 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-09 | 2025-01-09
43 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-12 | 2025-02-12 | Hector Oliverio [Hector]
43 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-27 | 2024-11-27
43 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-27 | 2024-11-27
41 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-21 | 2025-02-21
41 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
41 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17
41 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
41 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-12 | 2025-02-12 | Hector Oliverio [Hector]
41 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-09 | 2025-01-09
41 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-12 | 2025-02-12 | Hector Oliverio [Hector]
41 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-27 | 2024-11-27
41 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-27 | 2024-11-27
4548 Chatham Park North Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
4548 Chatham Park North Village | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-29 | 2025-01-29
4548 Chatham Park North Village | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-30 | 2025-01-30
4548 Chatham Park North Village | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-28 | 2025-01-28
4548 Chatham Park North Village | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | JO Brothers [Richard]
4548 Chatham Park North Village | Measurements | TRUE | 100 | Measured | 1 | 2025-01-24 | 2025-01-24
4548 Chatham Park North Village | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-30 | 2025-01-30
4548 Chatham Park North Village | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-03 | 2024-12-03
4548 Chatham Park North Village | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-03 | 2024-12-03
40 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
40 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
40 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
40 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Hector Oliverio [Hector]
40 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
40 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
40 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
40 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-20 | 2024-12-20
40 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-20 | 2024-12-20
24 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
24 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
24 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
24 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Hector Oliverio [Hector]
24 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Hector Oliverio [Hector]
24 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
24 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27 | Hector Oliverio [Hector]
24 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
24 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-09 | 2025-01-09
23 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
23 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
23 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
23 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Hector Oliverio [Hector]
23 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
23 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-03-04 | 2025-03-04
23 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
23 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-01 | 2025-01-01
23 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-01 | 2025-01-01
22 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
22 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
22 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
22 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
22 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Hector Oliverio [Hector]
22 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
22 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Hector Oliverio [Hector]
22 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
22 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
8 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-17 | 2025-02-17
8 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
8 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-11 | 2025-02-11
8 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
8 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
8 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-01-08 | 2025-01-08
8 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
8 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-21 | 2024-11-21
8 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-21 | 2024-11-21
Smith's Farmhouse Lodge | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-08-29 | 2025-08-29
Smith's Farmhouse Lodge | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
Smith's Farmhouse Lodge | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
Smith's Farmhouse Lodge | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
Smith's Farmhouse Lodge | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-10 | 2025-03-10 | Modern Exteriors Inc
Smith's Farmhouse Lodge | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
Smith's Farmhouse Lodge | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2024-12-18 | 2024-12-18
Smith's Farmhouse Lodge | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
Smith's Farmhouse Lodge | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
3 Heritage @ Neills Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-16 | 2025-01-16
3 Heritage @ Neills Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
3 Heritage @ Neills Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
3 Heritage @ Neills Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-08 | 2025-01-08 | Jesus Construction
3 Heritage @ Neills Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-07 | 2025-01-07 | Jesus Construction
3 Heritage @ Neills Creek | Measurements | TRUE | 100 | Measured | 1 | 2024-12-26 | 2024-12-26
3 Heritage @ Neills Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-07 | 2025-01-07 | Jesus Construction
3 Heritage @ Neills Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-22 | 2024-10-22
3 Heritage @ Neills Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-22 | 2024-10-22
12 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
12 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25 | Lopez Painting Group Inc
12 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
12 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
12 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
12 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Delia Construction
12 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
12 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-11 | 2025-03-11
12 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17 | Delia Construction
12 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-15 | 2025-01-15
12 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-15 | 2025-01-15
10 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
10 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06 | Lopez Painting Group Inc
10 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
10 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
10 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
10 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | Delia Construction
10 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-03 | 2025-03-03 | Delia Construction
10 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
10 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-03 | 2025-03-03 | Delia Construction
10 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-10 | 2024-12-10
10 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-10 | 2024-12-10
9 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
9 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Lopez Painting Group Inc
6 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13
6 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12 | Lopez Painting Group Inc
8 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
8 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17 | Lopez Painting Group Inc
9 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
9 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
9 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
9 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Delia Construction
9 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Delia Construction
9 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
9 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Delia Construction
9 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
9 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
8 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-13 | 2025-03-13
8 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-10 | 2025-03-10
8 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07
8 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05 | Delia Construction
8 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Delia Construction
8 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-02-25 | 2025-02-25
8 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Delia Construction
8 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
8 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-12 | 2024-12-12
2 Providence Oaks 30' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13
2 Providence Oaks 30' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
2 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
2 Providence Oaks 30' | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
2 Providence Oaks 30' | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
2 Providence Oaks 30' | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
2 Providence Oaks 30' | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-10 | 2025-03-10
2 Providence Oaks 30' | Measurements | FALSE | 0 | Measured | 1 | 2025-03-07 | 2025-03-07
2 Providence Oaks 30' | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-01-31 | 2025-01-31
2 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
2 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
90 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15
90 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Lopez Painting Group Inc
90 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
90 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
90 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06
90 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04 | Delia Construction
90 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-03 | 2025-03-03 | Delia Construction
90 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-03-07 | 2025-03-07
90 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-03 | 2025-03-03 | Delia Construction
90 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
90 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-12 | 2024-12-12
89 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15
89 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Lopez Painting Group Inc
89 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-11 | 2025-04-11
89 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
89 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07
89 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03 | Delia Construction
89 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
89 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-07 | 2025-03-07
89 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-01 | 2025-04-01 | Delia Construction
89 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
89 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-09 | 2025-01-09
93 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
93 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Lopez Painting Group Inc
375 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-07 | 2025-01-07
375 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27 | Lopez Painting Group Inc
375 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-04 | 2025-04-04
375 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
375 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
375 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
375 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-17 | 2025-03-17 | JO Brothers [Richard]
375 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
375 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17
375 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
375 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-13 | 2025-03-13
46 Little River | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
46 Little River | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-28 | 2025-02-28
46 Little River | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
46 Little River | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25 | Martinez NC Construction LLC [Luis]
46 Little River | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-24 | 2025-03-24 | Martinez NC Construction LLC [Luis]
46 Little River | Measurements | TRUE | 100 | Measured | 1 | 2025-03-25 | 2025-03-25 | Martinez NC Construction LLC [Luis]
46 Little River | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-25 | 2025-03-25 | Martinez NC Construction LLC [Luis]
46 Little River | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-20 | 2025-01-20
46 Little River | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-20 | 2025-01-20
6 North Lakes at South Lakes | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
6 North Lakes at South Lakes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | Lopez Painting Group Inc
347 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-26 | 2024-12-26
347 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | Lopez Painting Group Inc
345 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-02 | 2025-01-02
345 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15 | Lopez Painting Group Inc
340 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-09 | 2025-01-09
340 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27 | Lopez Painting Group Inc
13 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
13 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01 | Torres Painting Professional
12 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
12 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01 | Torres Painting Professional
11 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
11 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01 | Torres Painting Professional
13 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
13 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
13 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
13 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
13 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-17 | 2025-02-17 | On Top Contracting LLC
13 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-17 | 2025-02-17
13 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-17 | 2025-02-17
13 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-19 | 2024-12-19
13 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-19 | 2024-12-19
12 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
12 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
12 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
12 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
12 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-17 | 2025-02-17 | On Top Contracting LLC
12 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-17 | 2025-02-17
12 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-14 | 2025-02-14
12 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-19 | 2024-12-19
12 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-19 | 2024-12-19
11 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
11 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
11 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
11 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
11 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-17 | 2025-02-17 | On Top Contracting LLC
11 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-17 | 2025-02-17
11 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-14 | 2025-02-14
11 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-19 | 2024-12-19
11 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-19 | 2024-12-19
7 Providence Oaks 30' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-08 | 2025-01-08
7 Providence Oaks 30' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17 | Lopez Painting Group Inc
78 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
78 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
78 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
78 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
78 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
78 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
78 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
78 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
78 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
77 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
77 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
77 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
77 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
77 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
77 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
77 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
77 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
77 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
76 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
76 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
76 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
76 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
76 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
76 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
76 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
76 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
76 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
75 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
75 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
75 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
75 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
75 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
75 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
75 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
75 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
75 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
74 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-15 | 2025-04-15
74 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
74 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
74 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
74 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
74 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
74 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
74 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
74 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
5 Heritage at Neill's Creek | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17
5 Heritage at Neill's Creek | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14
73 Twinleaf Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
73 Twinleaf Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-11 | 2025-04-11
73 Twinleaf Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-09 | 2025-04-09
73 Twinleaf Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-07 | 2025-04-07 | Santiago Professional Siding [Santiago]
73 Twinleaf Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
73 Twinleaf Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-31 | 2025-03-31
73 Twinleaf Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-31 | 2025-03-31 | Santiago Professional Siding [Santiago]
73 Twinleaf Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-27 | 2025-01-27
73 Twinleaf Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
9 Watkins Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-23 | 2025-05-23
9 Watkins Grove | Invoiced | FALSE | 0 | Close Out | 1 | 2025-05-21 | 2025-05-21
9 Watkins Grove | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-19 | 2025-05-19
9 Watkins Grove | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
9 Watkins Grove | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-03 | 2025-04-03
9 Watkins Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-04-02 | 2025-04-02
9 Watkins Grove | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-24 | 2025-03-24
9 Watkins Grove | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
9 Watkins Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-20 | 2025-03-20
25 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
25 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
25 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
25 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
25 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
25 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
25 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
25 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
25 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
25 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
25 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
24 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
24 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
24 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
24 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
24 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
24 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
24 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
24 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
24 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
24 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
24 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
23 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
23 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
23 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
23 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
23 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
23 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
23 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
23 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
23 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
23 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
23 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
22 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
22 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
22 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
22 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
22 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
22 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
22 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
22 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
22 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
22 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
22 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
21 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
21 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
21 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
21 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
21 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
21 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
21 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
21 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
21 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
21 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-26 | 2024-12-26
21 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-26 | 2024-12-26
9 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-17 | 2025-02-17
9 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
9 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-11 | 2025-02-11
9 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
9 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
9 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-01-22 | 2025-01-22
9 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
9 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-21 | 2024-11-21
9 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-21 | 2024-11-21
91 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-13 | 2025-02-13
91 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-12 | 2025-02-12
91 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07
91 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
91 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | Delia Construction
91 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
91 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | Delia Construction
91 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-11 | 2024-11-11
91 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-11 | 2024-11-11
7 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
7 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
7 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
7 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Delia Construction
7 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-07 | 2025-03-07 | Delia Construction
7 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
7 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-07 | 2025-03-07 | Delia Construction
7 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-20 | 2024-12-20
7 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-20 | 2024-12-20
20 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
20 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31 | Torres Painting Professional
4 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-27 | 2025-02-27
4 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
4 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
4 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19 | Hector Oliverio [Hector]
4 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Hector Oliverio [Hector]
4 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-02-17 | 2025-02-17
4 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Hector Oliverio [Hector]
4 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-03 | 2024-12-03
4 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-05 | 2025-02-05
20 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
20 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
20 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
20 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
20 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
20 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
20 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
20 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-30 | 2025-01-30
20 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-30 | 2025-01-30
42 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-22 | 2025-01-22
42 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
42 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16
42 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14 | Hector Oliverio [Hector]
42 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-13 | 2025-01-13 | Hector Oliverio [Hector]
42 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02 | Hector Oliverio [Hector]
42 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-13 | 2025-01-13 | Hector Oliverio [Hector]
42 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-28 | 2024-10-28
42 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-28 | 2024-10-28
35 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-17 | 2025-01-17
35 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
35 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
35 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-09 | 2025-01-09 | Hector Oliverio [Hector]
35 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-08 | 2025-01-08 | Hector Oliverio [Hector]
35 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2024-12-18 | 2024-12-18
35 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-08 | 2025-01-08 | Hector Oliverio [Hector]
35 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-23 | 2024-10-23
35 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-23 | 2024-10-23
3 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-28 | 2025-01-28
3 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-28 | 2025-01-28
3 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22
3 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20 | Hector Oliverio [Hector]
3 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-17 | 2025-01-17 | Hector Oliverio [Hector]
3 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
3 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-17 | 2025-01-17 | Hector Oliverio [Hector]
3 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-01 | 2024-11-01
3 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-01 | 2024-11-01
2 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-04 | 2025-04-04
2 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
2 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-31 | 2025-03-31
2 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
2 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-25 | 2025-03-25 | J&A Construction
2 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-27 | 2025-03-27
2 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-26 | 2025-03-26
2 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-14 | 2025-02-14
2 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
1 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-03 | 2025-04-03
1 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
1 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
1 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
1 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | J&A Construction
1 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
1 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-28 | 2025-05-28
1 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-11 | 2025-03-11
1 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
36 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-09 | 2025-04-09
36 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
36 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03
36 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
36 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | NC Stark Construction Inc. [Amando]
36 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-27 | 2025-03-27
36 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-25 | 2025-04-25
36 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
36 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
8 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
8 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
8 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
8 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
8 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Wohlstand Construction LLC
8 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
8 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-15 | 2025-05-15
8 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-09 | 2025-04-09
8 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-09 | 2025-04-09
3 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
3 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
3 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
3 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25
3 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-20 | 2025-03-20 | NC Stark Construction Inc. [Amando]
3 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-21 | 2025-03-21
3 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
3 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-15 | 2025-01-15
3 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-25 | 2025-03-25
10 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
10 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-29 | 2025-04-29
10 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
10 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
10 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | Wohlstand Construction LLC
10 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
10 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
10 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-28 | 2025-04-28
10 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-28 | 2025-04-28
59 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-18 | 2025-06-18
59 Millstone | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-16 | 2025-06-16
59 Millstone | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-12 | 2025-06-12
59 Millstone | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-10 | 2025-06-10
59 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-29 | 2025-04-29
59 Millstone | Measurements | FALSE | 0 | Measured | 1 | 2025-04-28 | 2025-04-28
59 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
59 Millstone | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-07 | 2025-04-07
59 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-07 | 2025-04-07
147 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
147 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-21 | 2025-02-21
147 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19
147 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17
147 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | JO Brothers [Richard]
147 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-01-20 | 2025-01-20
147 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13
147 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
147 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-09 | 2025-01-09
183 Trails @ Young Farm | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
183 Trails @ Young Farm | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
183 Trails @ Young Farm | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
183 Trails @ Young Farm | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
183 Trails @ Young Farm | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-19 | 2025-02-19 | JO Brothers [Richard]
183 Trails @ Young Farm | Measurements | TRUE | 100 | Measured | 1 | 2025-01-23 | 2025-01-23
183 Trails @ Young Farm | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-19 | 2025-02-19
183 Trails @ Young Farm | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-10 | 2025-01-10
183 Trails @ Young Farm | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-10 | 2025-01-10
59 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
59 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
59 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
59 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Delia Construction
59 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
59 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-22 | 2025-01-22
59 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
59 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-07 | 2025-01-07
59 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-07 | 2025-01-07
5 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-27 | 2025-02-27
5 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
5 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
5 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
5 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-17 | 2025-02-17 | Delia Construction
5 North Lakes @ South Lakes | Measurements | FALSE | 0 | Measured | 1 | 2025-03-27 | 2025-03-27
5 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-17 | 2025-02-17 | Delia Construction
5 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
5 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
12 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
12 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-28 | 2025-02-28
12 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
12 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Delia Construction
12 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
12 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-14 | 2025-01-14 | Delia Construction
12 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
12 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-03 | 2025-01-03
12 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-03 | 2025-01-03
8 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-27 | 2025-02-27
8 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
8 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
8 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-19 | 2025-02-19 | Delia Construction
8 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-17 | 2025-02-17 | Delia Construction
8 North Lakes @ South Lakes | Measurements | FALSE | 0 | Measured | 1 | 2025-03-27 | 2025-03-27
8 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-17 | 2025-02-17 | Delia Construction
8 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
8 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-24 | 2024-12-24
376 Paddington Station 60' | 100% Job Complete | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11 | Gregorio Gutierrez
376 Paddington Station 60' | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
376 Paddington Station 60' | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
376 Paddington Station 60' | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
376 Paddington Station 60' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-06 | 2025-03-06
376 Paddington Station 60' | Measurements | TRUE | 100 | Measured | 1 | 2025-03-06 | 2025-03-06
376 Paddington Station 60' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-04 | 2025-02-04
376 Paddington Station 60' | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-21 | 2025-02-21
376 Paddington Station 60' | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-21 | 2025-02-21
10 Twinleaf Townes | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-27 | 2025-01-27
95 Providence Oaks 40' | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-12 | 2024-12-12
95 Providence Oaks 40' | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28
92 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-25 | 2024-12-25
92 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-13 | 2025-02-13 | Lopez Painting Group Inc
93 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-28 | 2025-02-28
93 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-21 | 2025-02-21
93 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24
93 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20 | Delia Construction
93 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Delia Construction
93 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-31 | 2025-01-31
93 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Delia Construction
93 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
93 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-12 | 2024-12-12
92 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-13 | 2025-02-13
92 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-12 | 2025-02-12
92 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07
92 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05 | Delia Construction
92 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | Delia Construction
92 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-31 | 2025-01-31
92 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | Delia Construction
92 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-26 | 2024-11-26
92 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-26 | 2024-11-26
59 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
59 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
59 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
59 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
59 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
59 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
59 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Santiago Professional Siding [Santiago]
59 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
59 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
62 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
62 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
62 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
62 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
62 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04
62 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
62 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04
62 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
62 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
60 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
60 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
60 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
60 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
60 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04
60 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
60 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04
60 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
60 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
63 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
63 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
63 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
63 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
63 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04
63 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
63 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04
63 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
63 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
61 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
61 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
61 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12
61 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10 | Santiago Professional Siding [Santiago]
61 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04
61 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
61 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04
61 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-31 | 2024-12-31
61 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-31 | 2024-12-31
7 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-28 | 2025-01-28
7 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
7 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22
7 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20 | Delia Construction
7 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-17 | 2025-01-17 | Delia Construction
7 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-03 | 2025-01-03
7 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-17 | 2025-01-17 | Delia Construction
7 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-20 | 2024-12-20
7 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-20 | 2024-12-20
2 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-06 | 2025-02-06
2 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-11 | 2025-02-11
2 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
2 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Delia Construction
2 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
2 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-15 | 2025-01-15
2 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
2 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-14 | 2024-11-14
2 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-14 | 2024-11-14
3 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
3 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
3 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22
3 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20 | Delia Construction
3 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-16 | 2025-01-16 | Delia Construction
3 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-03 | 2025-01-03
3 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-16 | 2025-01-16 | Delia Construction
3 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-26 | 2024-11-26
3 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-26 | 2024-11-26
19 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
19 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20
19 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
19 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
19 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
19 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | On Top Contracting LLC
19 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
19 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-20 | 2025-02-20
19 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-24 | 2025-02-24
19 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
19 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-25 | 2024-12-25
18 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
18 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
18 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
18 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
18 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
18 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | On Top Contracting LLC
18 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
18 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
18 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-24 | 2025-02-24
18 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
18 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-25 | 2024-12-25
17 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20
17 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
17 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
17 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
17 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
17 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | On Top Contracting LLC
17 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
17 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
17 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-24 | 2025-02-24
17 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
17 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-25 | 2024-12-25
16 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
16 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
16 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
16 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
16 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
16 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | On Top Contracting LLC
16 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
16 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
16 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-24 | 2025-02-24
16 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-24 | 2024-12-24
16 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-25 | 2024-12-25
15 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
15 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
15 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
15 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
15 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
15 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | On Top Contracting LLC
15 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
15 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
15 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-24 | 2025-02-24 | On Top Contracting LLC
15 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-23 | 2024-12-23
15 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-25 | 2024-12-25
94 Providence Oaks 40' | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-05 | 2024-12-05
94 Providence Oaks 40' | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
347 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
347 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-27 | 2025-02-27
347 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
347 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
347 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-30 | 2025-01-30 | JO Brothers [Richard]
347 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
347 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-30 | 2025-01-30
347 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-29 | 2024-11-29
347 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-29 | 2024-11-29
95 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
95 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-17 | 2025-02-17
95 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
95 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | Delia Construction
95 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-07 | 2025-02-07 | Delia Construction
95 Providence Oaks 40' | Measurements | FALSE | 0 | Measured | 1 | 2025-01-31 | 2025-01-31
95 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-07 | 2025-02-07 | Delia Construction
95 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
95 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
94 Providence Oaks 40' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
94 Providence Oaks 40' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-17 | 2025-02-17
94 Providence Oaks 40' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
94 Providence Oaks 40' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | Delia Construction
94 Providence Oaks 40' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-07 | 2025-02-07 | Delia Construction
94 Providence Oaks 40' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-07 | 2025-01-07
94 Providence Oaks 40' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-07 | 2025-02-07 | Delia Construction
94 Providence Oaks 40' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-06 | 2024-12-06
94 Providence Oaks 40' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-06 | 2024-12-06
6 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-14 | 2025-02-14
6 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-17 | 2025-02-17
6 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
6 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06 | Delia Construction
6 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-05 | 2025-02-05 | Delia Construction
6 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-31 | 2025-01-31
6 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-05 | 2025-02-05 | Delia Construction
6 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
6 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-11 | 2024-12-11
5 Providence Oaks 30' | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-13 | 2025-02-13
5 Providence Oaks 30' | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-17 | 2025-02-17
5 Providence Oaks 30' | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07
5 Providence Oaks 30' | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05 | Delia Construction
5 Providence Oaks 30' | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-04 | 2025-02-04 | Delia Construction
5 Providence Oaks 30' | Measurements | TRUE | 100 | Measured | 1 | 2025-01-07 | 2025-01-07
5 Providence Oaks 30' | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-04 | 2025-02-04 | Delia Construction
5 Providence Oaks 30' | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-03 | 2024-12-03
5 Providence Oaks 30' | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-03 | 2024-12-03
111 Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-19 | 2025-05-19
111 Chatham Park | Invoiced | FALSE | 0 | Close Out | 1 | 2025-05-15 | 2025-05-15
111 Chatham Park | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
111 Chatham Park | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-09 | 2025-05-09
111 Chatham Park | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-28 | 2025-03-28
111 Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
111 Chatham Park | Safety Walk/OSHA Log Signed | FALSE | 78 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
111 Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
111 Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-24 | 2025-01-24
58 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
58 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
58 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
58 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
58 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-09 | 2025-05-09 | Wohlstand Construction LLC
58 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-05-14 | 2025-05-14
58 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-09 | 2025-05-09
58 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-14 | 2025-04-14
58 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-21 | 2025-04-21
3 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-26 | 2025-05-26
3 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-19 | 2025-05-19
3 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
3 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-16 | 2025-05-16
3 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-12 | 2025-05-12 | Wohlstand Construction LLC
3 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-24 | 2025-04-24
3 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-26 | 2025-05-26
3 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-21 | 2025-04-21
3 Millstone | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-21 | 2025-04-21
11 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-09 | 2025-04-09
11 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
11 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-03 | 2025-04-03
11 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
11 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-24 | 2025-03-24 | J&A Construction
11 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
11 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
11 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-27 | 2025-02-27
11 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
46 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-13 | 2025-05-13
46 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
46 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
46 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
46 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-15 | 2025-04-15 | JO Brothers [Richard]
46 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
46 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
46 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-10 | 2025-03-10
46 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
9 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-08 | 2025-05-08
9 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
9 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
9 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-30 | 2025-04-30
9 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | J&A Construction
9 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
9 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24
9 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-14 | 2025-04-14
9 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
12 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-16 | 2025-04-16
12 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
12 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-10 | 2025-04-10
12 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
12 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | J&A Construction
12 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-10 | 2025-03-10
12 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
12 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-10 | 2025-02-10
12 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
56 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-21 | 2025-05-21
56 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
56 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
56 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
56 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | JO Brothers [Richard]
56 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
56 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-02 | 2025-05-02
56 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-09 | 2025-04-09
56 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-21 | 2025-04-21
57 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-10 | 2025-04-10
57 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
57 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
57 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02
57 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | JO Brothers [Richard]
57 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
57 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-28 | 2025-04-28
57 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-18 | 2025-03-18
57 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
112 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
112 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
112 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
112 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25
112 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-14 | 2025-03-14 | J&A Construction
112 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-14 | 2025-03-14 | J&A Construction
112 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16
112 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-27 | 2024-12-27
112 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-19 | 2025-03-19
2 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
2 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
2 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
2 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
2 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-16 | 2025-05-16 | Wohlstand Construction LLC
2 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-24 | 2025-04-24
2 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16
2 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-09 | 2025-05-09
2 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
54 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-21 | 2025-05-21
54 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-14 | 2025-05-14
54 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-15 | 2025-05-15
54 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-13 | 2025-05-13
54 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-02 | 2025-05-02 | Wohlstand Construction LLC
54 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09
54 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-12 | 2025-05-12
54 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-08 | 2025-04-08
54 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-21 | 2025-04-21
51 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
51 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
51 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-25 | 2025-02-25
51 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
51 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-14 | 2025-02-14 | JO Brothers [Richard]
51 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
51 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-14 | 2025-02-14
51 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-04 | 2024-11-04
51 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-04 | 2024-11-04
48 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
48 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-27 | 2025-05-27
48 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
48 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23
48 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-13 | 2025-05-13 | Wohlstand Construction LLC
48 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-05-13 | 2025-05-13
48 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-13 | 2025-05-13
48 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-04-28 | 2025-04-28
48 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-30 | 2025-04-30
45 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-29 | 2025-04-29
45 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-22 | 2025-04-22
45 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23
45 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-21 | 2025-04-21
45 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-14 | 2025-04-14 | Wohlstand Construction LLC
45 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
45 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-18 | 2025-04-18
45 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-06 | 2025-03-06
45 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-01 | 2025-04-01
13 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-23 | 2025-04-23
13 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
13 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-17 | 2025-04-17
13 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
13 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-07 | 2025-04-07 | JO Brothers [Richard]
13 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-20 | 2025-03-20
13 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-16 | 2025-04-16
13 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-11 | 2025-03-11
13 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-16 | 2025-04-16
6 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-14 | 2025-04-14
6 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-24 | 2025-04-24
6 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-08 | 2025-04-08
6 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
6 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-01 | 2025-04-01 | JO Brothers [Richard]
6 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-12 | 2025-03-12
6 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-06 | 2025-05-06
6 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
6 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
5 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
5 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
5 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
5 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
5 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-29 | 2025-04-29 | Wohlstand Construction LLC
5 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-03-26 | 2025-03-26
5 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
5 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-25 | 2025-03-25
5 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-15 | 2025-04-15
4 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-02 | 2025-06-02
4 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-29 | 2025-05-29
4 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27
4 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-23 | 2025-05-23 | Wohlstand Construction LLC
4 Millstone | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-05-02 | 2025-05-02
4 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-05-08 | 2025-05-08
4 Millstone | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-02 | 2025-06-02
4 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-08 | 2025-05-08
4 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-12 | 2025-05-12
65 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-21 | 2025-03-21
65 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-28 | 2025-01-28
65 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29
65 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
65 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | Delia Construction
65 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-15 | 2025-01-15
65 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24 | Delia Construction
65 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-13 | 2024-11-13
65 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-13 | 2024-11-13
61 North Lakes @ South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-04 | 2025-02-04
61 North Lakes @ South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-28 | 2025-01-28
61 North Lakes @ South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29
61 North Lakes @ South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
61 North Lakes @ South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-23 | 2025-01-23 | Delia Construction
61 North Lakes @ South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-15 | 2025-01-15
61 North Lakes @ South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-23 | 2025-01-23 | Delia Construction
61 North Lakes @ South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-11 | 2024-11-11
61 North Lakes @ South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-11 | 2024-11-11
14 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
14 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
14 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
14 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
14 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
14 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
14 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
14 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
14 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
14 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
14 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
13 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
13 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
13 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
13 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
13 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
13 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
13 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
13 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
13 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18
13 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
13 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
12 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
12 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
12 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
12 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
12 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
12 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
12 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
12 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
12 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
12 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
12 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
11 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05
11 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
11 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
11 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-25 | 2025-02-25
11 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
11 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
11 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
11 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
11 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
11 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
11 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
10 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
10 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12 | Torres Painting Professional
10 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
10 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
10 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
10 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
10 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
10 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-18 | 2025-02-18
10 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Santiago Professional Siding [Santiago]
10 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
10 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-18 | 2024-12-18
17 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03
17 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Torres Painting Professional
16 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03
16 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Torres Painting Professional
15 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
15 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Torres Painting Professional
14 Page Townes TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-21 | 2025-02-21
14 Page Townes TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Torres Painting Professional
17 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-20 | 2025-03-20
17 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
17 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
17 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | On Top Contracting LLC
17 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
17 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
17 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-17 | 2025-04-17 | On Top Contracting LLC
17 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
17 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
16 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-05 | 2025-03-05
16 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
16 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
16 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | On Top Contracting LLC
16 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
16 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
16 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-17 | 2025-04-17 | On Top Contracting LLC
16 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
16 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
15 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
15 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
15 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
15 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | On Top Contracting LLC
15 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
15 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
15 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-17 | 2025-04-17 | On Top Contracting LLC
15 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
15 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
14 Page Townes TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-17 | 2025-04-17
14 Page Townes TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
14 Page Townes TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
14 Page Townes TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10 | On Top Contracting LLC
14 Page Townes TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
14 Page Townes TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
14 Page Townes TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
14 Page Townes TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
14 Page Townes TH | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
6 North Lakes at South Lakes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-06 | 2025-02-06
6 North Lakes at South Lakes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-11 | 2025-02-11
6 North Lakes at South Lakes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
6 North Lakes at South Lakes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Delia Construction
6 North Lakes at South Lakes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
6 North Lakes at South Lakes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-21 | 2025-01-21
6 North Lakes at South Lakes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27 | Delia Construction
6 North Lakes at South Lakes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-25 | 2024-11-25
6 North Lakes at South Lakes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-25 | 2024-11-25
349 Vineyards @ Chatham Park | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-11-15 | 2024-11-15
349 Vineyards @ Chatham Park | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16 | Lopez Painting Group Inc
39 Carolina Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
39 Carolina Landing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
39 Carolina Landing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
39 Carolina Landing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02 | Requena Siding [Jairo]
39 Carolina Landing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Requena Siding [Jairo]
39 Carolina Landing | Measurements | TRUE | 100 | Measured | 1 | 2025-03-27 | 2025-03-27 | Requena Siding [Jairo]
39 Carolina Landing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-26 | 2025-03-26 | Requena Siding [Jairo]
39 Carolina Landing | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-23 | 2025-01-23
39 Carolina Landing | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-03 | 2025-02-03
17 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
17 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
17 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
17 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
17 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
17 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
17 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27
17 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-30 | 2024-10-30
17 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-30 | 2024-10-30
16 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-05 | 2025-03-05
16 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
16 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
16 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
16 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
16 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
16 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27
16 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-30 | 2024-10-30
16 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-30 | 2024-10-30
15 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
15 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
15 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
15 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
15 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
15 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
15 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
15 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-30 | 2024-10-30
15 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-30 | 2024-10-30
14 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-12 | 2025-03-12
14 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
14 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
14 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
14 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
14 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
14 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27
14 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-30 | 2024-10-30
14 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-30 | 2024-10-30
13 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-11 | 2025-02-11
13 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
13 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
13 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | On Top Contracting LLC
13 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-27 | 2025-01-27 | On Top Contracting LLC
13 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-27 | 2025-01-27
13 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-27 | 2025-01-27
13 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-30 | 2024-10-30
13 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-30 | 2024-10-30
101 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
101 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
101 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
101 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
101 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
101 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-07-31 | 2025-07-31
101 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-12-15 | 2025-12-15
101 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-07-28 | 2025-07-28
101 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-07-28 | 2025-07-28
100 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
100 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
100 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
100 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
100 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
100 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-18 | 2025-09-18
100 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-20 | 2025-08-20
100 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-18 | 2025-08-18
100 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-18 | 2025-08-18
60 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-07 | 2025-11-07
60 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-11-05 | 2025-11-05
60 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-11-03 | 2025-11-03
60 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-30 | 2025-10-30
60 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-18 | 2025-09-18
60 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-07-14 | 2025-07-14
60 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-10 | 2025-10-10
60 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-08 | 2025-10-08
60 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-08 | 2025-10-08
59 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-07 | 2025-11-07
59 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-11-05 | 2025-11-05
59 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-11-03 | 2025-11-03
59 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-30 | 2025-10-30
59 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-18 | 2025-09-18
59 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-11 | 2025-09-11
59 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-13 | 2025-10-13
59 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-09 | 2025-10-09
59 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-09 | 2025-10-09
58 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-07 | 2025-11-07
58 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-11-05 | 2025-11-05
58 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-11-03 | 2025-11-03
58 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-30 | 2025-10-30
58 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-18 | 2025-09-18
58 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-11 | 2025-09-11
58 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-12-17 | 2025-12-17
58 Fieldview Village | Ordered | TRUE | 100 | Ordered | 1 | 2025-09-12 | 2025-09-12
58 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-09-12 | 2025-09-12
57 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-31 | 2025-10-31
57 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-29 | 2025-10-29
57 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-27 | 2025-10-27
57 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-23 | 2025-10-23
57 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-11 | 2025-09-11
57 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-10 | 2025-09-10
57 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
57 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
57 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
56 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-31 | 2025-10-31
56 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-29 | 2025-10-29
56 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-27 | 2025-10-27
56 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-23 | 2025-10-23
56 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-11 | 2025-09-11
56 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-10 | 2025-09-10
56 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
56 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
56 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
55 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-31 | 2025-10-31
55 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-29 | 2025-10-29
55 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-27 | 2025-10-27
55 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-23 | 2025-10-23
55 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-11 | 2025-09-11
55 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-10 | 2025-09-10
55 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
55 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
55 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
54 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-30 | 2025-10-30
54 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-28 | 2025-10-28
54 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-24 | 2025-10-24
54 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-22 | 2025-10-22
54 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-10 | 2025-09-10
54 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-09 | 2025-09-09
54 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
54 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
54 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
53 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-30 | 2025-10-30
53 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-28 | 2025-10-28
53 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-24 | 2025-10-24
53 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-22 | 2025-10-22
53 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-10 | 2025-09-10
53 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-09 | 2025-09-09
53 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
53 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
53 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
52 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-29 | 2025-10-29
52 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-27 | 2025-10-27
52 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-23 | 2025-10-23
52 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-21 | 2025-10-21
52 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-09 | 2025-09-09
52 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-08 | 2025-09-08
52 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
52 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-03 | 2025-10-03
52 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-03 | 2025-10-03
10 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-28 | 2025-04-28
10 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-24 | 2025-04-24
10 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-22 | 2025-04-22
10 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-18 | 2025-04-18
10 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-07 | 2025-03-07
10 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-03-06 | 2025-03-06
10 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-29 | 2025-05-29
10 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-04-16 | 2025-04-16
10 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-04-16 | 2025-04-16
9 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
9 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
9 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
9 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
9 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
9 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
9 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-14 | 2025-08-14
9 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-12 | 2025-08-12
9 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-12 | 2025-08-12
8 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
8 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
8 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
8 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
8 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
8 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
8 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-14 | 2025-08-14
8 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-12 | 2025-08-12
8 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-12 | 2025-08-12
7 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-25 | 2025-09-25
7 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-23 | 2025-09-23
7 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-19 | 2025-09-19
7 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-17 | 2025-09-17
7 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-06 | 2025-08-06
7 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
7 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-14 | 2025-08-14
7 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-12 | 2025-08-12
7 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-12 | 2025-08-12
6 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
6 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
6 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
6 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
6 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-05 | 2025-08-05
6 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-04 | 2025-08-04
6 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-14 | 2025-08-14
6 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-12 | 2025-08-12
6 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-12 | 2025-08-12
5 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
5 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
5 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
5 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
5 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-05 | 2025-08-05
5 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-04 | 2025-08-04
5 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-14 | 2025-08-14
5 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-12 | 2025-08-12
5 Carson's Landing | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-12 | 2025-08-12
349 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
349 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-21 | 2025-01-21
349 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20
349 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16
349 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-13 | 2025-01-13 | JO Brothers [Richard]
349 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-01-09 | 2025-01-09
349 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-13 | 2025-01-13
349 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-14 | 2024-11-14
349 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-21 | 2024-11-21
345 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
345 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-15 | 2025-01-15
345 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
345 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-10 | 2025-01-10
345 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-08 | 2025-01-08 | JO Brothers [Richard]
345 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
345 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-08 | 2025-01-08
345 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-12 | 2024-11-12
345 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-12 | 2024-11-12
84 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-11 | 2025-03-11
84 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
84 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
84 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03
84 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-31 | 2025-01-31
84 Regency @ Olde Towne | Measurements | FALSE | 0 | Measured | 1 | 2025-04-17 | 2025-04-17
84 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-03-12 | 2025-03-12
84 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-28 | 2024-10-28
84 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-05 | 2025-02-05
7 Millstone | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
7 Millstone | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
7 Millstone | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-06 | 2025-05-06
7 Millstone | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-02 | 2025-05-02
7 Millstone | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-29 | 2025-04-29 | Wohlstand Construction LLC
7 Millstone | Measurements | TRUE | 100 | Measured | 1 | 2025-04-02 | 2025-04-02
7 Millstone | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-29 | 2025-04-29
7 Millstone | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-31 | 2025-03-31
7 Millstone | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-23 | 2025-04-23
90 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-24 | 2025-03-24
90 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
90 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-18 | 2025-03-18
90 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
90 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-12 | 2025-03-12 | NC Stark Construction Inc. [Amando]
90 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-03-12 | 2025-03-12
90 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-11 | 2025-03-11
90 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-07 | 2025-01-07
90 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-07 | 2025-01-07
157 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
157 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
157 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
157 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Hector Oliverio [Hector]
157 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-21 | 2025-03-21 | Hector Oliverio [Hector]
157 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-26 | 2025-02-26
157 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-21 | 2025-03-21 | Hector Oliverio [Hector]
157 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-06 | 2025-02-06
157 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-29 | 2024-10-29
156 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
156 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
156 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
156 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
156 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-17 | 2025-03-17 | Hector Oliverio [Hector]
156 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-26 | 2025-02-26
156 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-17 | 2025-03-17 | Hector Oliverio [Hector]
156 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-25 | 2024-12-25
156 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-22 | 2025-01-22
155 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-04 | 2025-02-04
155 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-27 | 2025-01-27
155 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29
155 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-27 | 2025-01-27 | Hector Oliverio [Hector]
155 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | Hector Oliverio [Hector]
155 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2024-12-30 | 2024-12-30
155 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24 | Hector Oliverio [Hector]
155 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-06 | 2024-11-06
155 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-04 | 2024-12-04
154 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-24 | 2025-01-24
154 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-20 | 2025-01-20
154 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20
154 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16 | Hector Oliverio [Hector]
154 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-15 | 2025-01-15 | Hector Oliverio [Hector]
154 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
154 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-15 | 2025-01-15 | Hector Oliverio [Hector]
154 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-28 | 2024-10-28
154 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-28 | 2024-10-28
153 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-24 | 2025-01-24
153 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-20 | 2025-01-20
153 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20
153 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16 | Hector Oliverio [Hector]
153 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-15 | 2025-01-15 | Hector Oliverio [Hector]
153 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
153 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-15 | 2025-01-15 | Hector Oliverio [Hector]
153 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-28 | 2024-10-28
153 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-25 | 2024-11-25
152 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-27 | 2025-01-27
152 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2024-12-10 | 2024-12-10
152 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
152 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | Jesus Construction
152 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-16 | 2025-01-16 | Jesus Construction
152 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
152 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-16 | 2025-01-16 | Jesus Construction
152 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-25 | 2024-10-25
152 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-26 | 2024-11-26
160 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-03 | 2025-04-03
160 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
160 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
160 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26 | Hector Oliverio [Hector]
160 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-25 | 2025-03-25 | Hector Oliverio [Hector]
160 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-24 | 2025-02-24
160 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-25 | 2025-03-25 | Hector Oliverio [Hector]
160 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-06 | 2025-01-06
160 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-03 | 2025-02-03
158 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-24 | 2025-02-24
158 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
158 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-18 | 2025-02-18
158 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14 | Hector Oliverio [Hector]
158 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
158 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-15 | 2025-01-15
158 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13 | Hector Oliverio [Hector]
158 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-02 | 2025-01-02
158 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-02 | 2025-01-02
151 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-17 | 2025-02-17
151 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
151 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-11 | 2025-02-11
151 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07 | Hector Oliverio [Hector]
151 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
151 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-02-21 | 2025-02-21
151 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-06 | 2025-02-06 | Hector Oliverio [Hector]
151 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-28 | 2024-11-28
151 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-19 | 2024-12-19
131 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-06 | 2025-02-06
131 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
131 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
131 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Hector Oliverio [Hector]
131 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-28 | 2025-01-28 | Hector Oliverio [Hector]
131 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-21 | 2025-02-21
131 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-28 | 2025-01-28 | Hector Oliverio [Hector]
131 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-13 | 2024-11-13
131 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-10 | 2024-12-10
124 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-01 | 2025-04-01
124 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-24 | 2025-03-24
124 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-26 | 2025-03-26
124 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24 | Hector Oliverio [Hector]
124 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-21 | 2025-03-21 | Hector Oliverio [Hector]
124 Duncans Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-02-21 | 2025-02-21
124 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-21 | 2025-03-21 | Hector Oliverio [Hector]
124 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
124 Duncans Creek | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-05 | 2025-03-05
123 Duncans Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-25 | 2025-03-25
123 Duncans Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
123 Duncans Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19
123 Duncans Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17 | Hector Oliverio [Hector]
123 Duncans Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-14 | 2025-03-14 | Hector Oliverio [Hector]
123 Duncans Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
123 Duncans Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-14 | 2025-03-14 | Hector Oliverio [Hector]
123 Duncans Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-24 | 2025-01-24
123 Duncans Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-24 | 2025-01-24
16 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-14 | 2025-03-14
16 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-14 | 2025-03-14
16 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10
16 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06 | Leones Construction LLC
16 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Leones Construction LLC
16 Sippihaw Springs | Measurements | TRUE | 100 | Measured | 1 | 2025-02-13 | 2025-02-13
16 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-04 | 2025-03-04 | Leones Construction LLC
16 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-28 | 2025-02-28
16 Sippihaw Springs | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-28 | 2025-02-28
15 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-21 | 2025-01-21
15 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
15 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
15 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | OCCZ Construction LLC
15 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-09 | 2025-01-09 | OCCZ Construction LLC
15 Sippihaw Springs | Measurements | TRUE | 100 | Measured | 1 | 2024-12-20 | 2024-12-20
15 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-09 | 2025-01-09 | OCCZ Construction LLC
15 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-06 | 2024-11-06
15 Sippihaw Springs | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-06 | 2024-11-06
8 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
8 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
8 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
8 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25 | Hector Oliverio [Hector]
8 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
8 Sippihaw Springs | Measurements | FALSE | 0 | Measured | 1 | 2025-02-13 | 2025-02-13
8 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
8 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-30 | 2025-05-30
8 Sippihaw Springs | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-25 | 2025-06-25
7 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-02 | 2025-05-02
7 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-30 | 2025-04-30
7 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-28 | 2025-04-28
7 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-24 | 2025-04-24 | Hector Oliverio [Hector]
7 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-23 | 2025-04-23 | Hector Oliverio [Hector]
7 Sippihaw Springs | Measurements | FALSE | 0 | Measured | 1 | 2025-02-13 | 2025-02-13
7 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-23 | 2025-04-23 | Hector Oliverio [Hector]
7 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-27 | 2025-05-27
7 Sippihaw Springs | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-24 | 2025-06-24
4 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-28 | 2025-05-28
4 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-21 | 2025-05-21
4 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-22 | 2025-05-22
4 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-20 | 2025-05-20
4 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-19 | 2025-05-19 | Hector Oliverio [Hector]
4 Sippihaw Springs | Measurements | FALSE | 0 | Measured | 1 | 2025-02-17 | 2025-02-17
4 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-19 | 2025-05-19
4 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2025-07-22 | 2025-07-22
4 Sippihaw Springs | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-25 | 2025-07-25
3 Sippihaw Springs | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
3 Sippihaw Springs | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-06 | 2025-05-06
3 Sippihaw Springs | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
3 Sippihaw Springs | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-23 | 2025-04-23 | Hector Oliverio [Hector]
3 Sippihaw Springs | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
3 Sippihaw Springs | Measurements | TRUE | 100 | Measured | 1 | 2025-02-12 | 2025-02-12
3 Sippihaw Springs | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-22 | 2025-04-22 | Hector Oliverio [Hector]
3 Sippihaw Springs | Ordered | TRUE | 100 | Ordered | 1 | 2025-05-22 | 2025-05-22
3 Sippihaw Springs | Lien # | TRUE | 100 | Lien # | 1 | 2025-06-23 | 2025-06-23
73 Regency @ Olde Towne | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-01-14 | 2026-01-14
73 Regency @ Olde Towne | Invoiced | TRUE | 100 | Close Out | 1 | 2025-11-25 | 2025-11-25
73 Regency @ Olde Towne | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-11-25 | 2025-11-25
73 Regency @ Olde Towne | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-11-21 | 2025-11-21
73 Regency @ Olde Towne | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-11-17 | 2025-11-17 | NC Stark Construction Inc. [Amando]
73 Regency @ Olde Towne | Measurements | TRUE | 100 | Measured | 1 | 2025-01-02 | 2025-01-02
73 Regency @ Olde Towne | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-11-17 | 2025-11-17
73 Regency @ Olde Towne | Ordered | TRUE | 100 | Ordered | 1 | 2025-09-19 | 2025-09-19
73 Regency @ Olde Towne | Lien # | TRUE | 100 | Lien # | 1 | 2025-09-19 | 2025-09-19
340 Vineyards @ Chatham Park | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-12 | 2025-05-12
340 Vineyards @ Chatham Park | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-28 | 2025-04-28
340 Vineyards @ Chatham Park | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
340 Vineyards @ Chatham Park | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27
340 Vineyards @ Chatham Park | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-09 | 2025-01-09 | JO Brothers [Richard]
340 Vineyards @ Chatham Park | Measurements | TRUE | 100 | Measured | 1 | 2025-01-09 | 2025-01-09
340 Vineyards @ Chatham Park | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-24 | 2025-03-24
340 Vineyards @ Chatham Park | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
340 Vineyards @ Chatham Park | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
98 Magnolia Square West | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-10 | 2025-06-10
98 Magnolia Square West | Invoiced | FALSE | 0 | Close Out | 1 | 2025-06-06 | 2025-06-06
98 Magnolia Square West | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-04 | 2025-06-04
98 Magnolia Square West | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-06-02 | 2025-06-02
98 Magnolia Square West | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-21 | 2025-04-21
98 Magnolia Square West | Measurements | FALSE | 0 | Measured | 1 | 2025-04-18 | 2025-04-18
98 Magnolia Square West | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-02-19 | 2025-02-19
98 Magnolia Square West | Ordered | FALSE | 0 | Ordered | 1 | 2025-02-17 | 2025-02-17
98 Magnolia Square West | Lien # | FALSE | 0 | Lien # | 1 | 2025-02-17 | 2025-02-17
12 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
12 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-27 | 2025-01-27
12 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
12 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
12 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
12 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
12 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
12 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-18 | 2024-10-18
12 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-18 | 2024-10-18
11 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
11 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
11 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
11 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
11 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
11 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
11 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
11 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-18 | 2024-10-18
11 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-18 | 2024-10-18
10 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-18 | 2025-03-18
10 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
10 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
10 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
10 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
10 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
10 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
10 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-18 | 2024-10-18
10 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-18 | 2024-10-18
9 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
9 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
9 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
9 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
9 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
9 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
9 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
9 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-08 | 2024-11-08
9 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-08 | 2024-11-08
8 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-03 | 2025-03-03
8 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
8 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
8 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
8 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
8 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
8 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
8 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-08 | 2024-11-08
8 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-08 | 2024-11-08
7 Twinleaf Townes | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
7 Twinleaf Townes | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
7 Twinleaf Townes | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-21 | 2025-01-21
7 Twinleaf Townes | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17 | On Top Contracting LLC
7 Twinleaf Townes | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
7 Twinleaf Townes | Measurements | TRUE | 100 | Measured | 1 | 2025-01-10 | 2025-01-10
7 Twinleaf Townes | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-10 | 2025-01-10 | On Top Contracting LLC
7 Twinleaf Townes | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-08 | 2024-11-08
7 Twinleaf Townes | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-08 | 2024-11-08
6069 Jones Circle | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
6069 Jones Circle | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
6069 Jones Circle | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-24 | 2025-03-24
6069 Jones Circle | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-20 | 2025-03-20 | Hector Oliverio [Hector]
6069 Jones Circle | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
6069 Jones Circle | Measurements | FALSE | 0 | Measured | 1 | 2025-03-13 | 2025-03-13
6069 Jones Circle | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
6069 Jones Circle | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-01 | 2025-01-01
6069 Jones Circle | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-17 | 2025-03-17
3258 Yorkshire Circle | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
3258 Yorkshire Circle | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
3258 Yorkshire Circle | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
3258 Yorkshire Circle | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Junior Omar Reconco
3258 Yorkshire Circle | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-26 | 2025-02-26 | Junior Omar Reconco
3258 Yorkshire Circle | Measurements | FALSE | 0 | Measured | 1 | 2025-04-15 | 2025-04-15
3258 Yorkshire Circle | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-16 | 2025-05-16 | Junior Omar Reconco
3258 Yorkshire Circle | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
3258 Yorkshire Circle | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
3260 Yorkshire Circle | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-14 | 2025-03-14
3260 Yorkshire Circle | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
3260 Yorkshire Circle | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-10 | 2025-03-10
3260 Yorkshire Circle | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06 | Leones Construction LLC
3260 Yorkshire Circle | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-04 | 2025-03-04 | Junior Omar Reconco
3260 Yorkshire Circle | Measurements | FALSE | 0 | Measured | 1 | 2025-03-11 | 2025-03-11
3260 Yorkshire Circle | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-03 | 2025-03-03 | Leones Construction LLC
3260 Yorkshire Circle | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-18 | 2024-12-18
3260 Yorkshire Circle | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
9 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-27 | 2024-12-27
9 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
9 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-30 | 2025-04-30
9 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
9 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24
9 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20 | Santiago Professional Siding [Santiago]
9 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
9 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-01-13 | 2025-01-13
9 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13
9 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
9 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
8 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-02 | 2025-01-02
8 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
8 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
8 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-19 | 2025-02-19
8 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-17 | 2025-02-17
8 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
8 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
8 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-13 | 2025-02-13
8 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13
8 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
8 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
7 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-26 | 2024-12-26
7 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
7 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-04 | 2025-03-04
7 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-14 | 2025-02-14
7 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-26 | 2025-02-26
7 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24 | Santiago Professional Siding [Santiago]
7 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
7 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-13 | 2025-02-13
7 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13
7 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
7 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
6 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-24 | 2024-12-24
6 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14 | Torres Painting Professional
6 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-28 | 2025-02-28
6 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-19 | 2025-02-19
6 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24
6 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20 | Santiago Professional Siding [Santiago]
6 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
6 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2024-03-13 | 2024-03-13
6 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
6 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
6 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
5 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-31 | 2024-12-31
5 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-06 | 2025-03-06 | Torres Painting Professional
5 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
5 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
5 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-24 | 2025-02-24
5 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20 | Santiago Professional Siding [Santiago]
5 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-13 | 2025-02-13 | Santiago Professional Siding [Santiago]
5 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-02-13 | 2025-02-13
5 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-11 | 2025-02-11 | Santiago Professional Siding [Santiago]
5 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-16 | 2024-12-16
5 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-16 | 2024-12-16
4 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04
4 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Torres Painting Professional
4 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-20 | 2025-03-20
4 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
4 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
4 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Santiago Professional Siding [Santiago]
4 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago]
4 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-01-24 | 2025-01-24
4 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago]
4 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-22 | 2024-11-22
4 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-22 | 2024-11-22
3 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
3 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Torres Painting Professional
3 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-26 | 2025-03-26
3 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
3 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
3 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Santiago Professional Siding [Santiago]
3 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago]
3 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-01-24 | 2025-01-24
3 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago]
3 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-22 | 2024-11-22
3 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-22 | 2024-11-22
1 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14
1 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Torres Painting Professional
2 Stanat Place TH | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
2 Stanat Place TH | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Torres Painting Professional
2 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-13 | 2025-03-13
2 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-24 | 2025-02-24
2 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
2 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Santiago Professional Siding [Santiago]
2 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-17 | 2025-01-17 | Santiago Professional Siding [Santiago]
2 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-01-24 | 2025-01-24
2 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24
2 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-15 | 2024-11-15
2 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-15 | 2024-11-15
1 Stanat Place TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-19 | 2025-03-19
1 Stanat Place TH | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
1 Stanat Place TH | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
1 Stanat Place TH | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29 | Santiago Professional Siding [Santiago]
1 Stanat Place TH | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-24 | 2025-01-24 | Santiago Professional Siding [Santiago]
1 Stanat Place TH | Measurements | TRUE | 100 | Measured | 1 | 2025-01-24 | 2025-01-24
1 Stanat Place TH | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-24 | 2025-01-24
1 Stanat Place TH | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-22 | 2024-11-22
1 Stanat Place TH | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-22 | 2024-11-22
28 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
28 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
28 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
28 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
28 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
28 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
28 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-01 | 2025-09-01
28 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
28 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
27 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
27 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
27 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
27 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
27 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
27 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
27 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-01 | 2025-09-01
27 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
27 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
26 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
26 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
26 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
26 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
26 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
26 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
26 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-01 | 2025-09-01
26 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
26 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
25 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
25 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
25 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
25 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
25 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
25 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
25 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-01 | 2025-09-01
25 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
25 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
16 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
16 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
16 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
16 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
16 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
16 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
16 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-05 | 2025-09-05
16 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 3 | 2025-08-05 | 2025-08-07
16 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-07 | 2025-08-07
15 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
15 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
15 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
15 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
15 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
15 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
15 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
15 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
15 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
14 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
14 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
14 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
14 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
14 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
14 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
14 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
14 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
14 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
13 Pearl Street TH | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-22 | 2025-09-22
13 Pearl Street TH | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-18 | 2025-09-18
13 Pearl Street TH | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-16 | 2025-09-16
13 Pearl Street TH | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-12 | 2025-09-12
13 Pearl Street TH | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-01 | 2025-08-01
13 Pearl Street TH | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
13 Pearl Street TH | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-10-07 | 2025-10-07
13 Pearl Street TH | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-05 | 2025-08-05
13 Pearl Street TH | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-05 | 2025-08-05
115 Test Job | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-10-08 | 2024-10-08
115 Test Job | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-10-07 | 2024-10-07
115 Test Job | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-06 | 2025-02-06
115 Test Job | Invoiced | FALSE | 0 | Close Out | 1 | 2025-02-04 | 2025-02-04
115 Test Job | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-31 | 2025-01-31
115 Test Job | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-29 | 2025-01-29
115 Test Job | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-12-18 | 2024-12-18
115 Test Job | Measurements | FALSE | 0 | Measured | 1 | 2024-12-17 | 2024-12-17
115 Test Job | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-10-18 | 2024-10-18
115 Test Job | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-16 | 2024-10-16
115 Test Job | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-16 | 2024-10-16
16 Ellington Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-16 | 2025-05-16
16 Ellington Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-05-12 | 2025-05-12
16 Ellington Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-12 | 2025-05-12
16 Ellington Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-08 | 2025-05-08 | NC SIDING & REMODELING PRO LLC
16 Ellington Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-05 | 2025-05-05 | NC SIDING & REMODELING PRO LLC
16 Ellington Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-05-08 | 2025-05-08 | NC SIDING & REMODELING PRO LLC
16 Ellington Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-08 | 2025-05-08 | NC SIDING & REMODELING PRO LLC
16 Ellington Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-06 | 2025-03-06
16 Ellington Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-05-27 | 2025-05-27
30 Magnolia Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
30 Magnolia Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
30 Magnolia Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-27 | 2025-03-27
30 Magnolia Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-25 | 2025-03-25 | Prime Exterior [Siding] LLC [Miguel]
30 Magnolia Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-24 | 2025-03-24 | Prime Exterior [Siding] LLC [Miguel]
30 Magnolia Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-25 | 2025-03-25 | Prime Exterior [Siding] LLC [Miguel]
30 Magnolia Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-24 | 2025-03-24 | Prime Exterior [Siding] LLC [Miguel]
30 Magnolia Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-20 | 2025-02-20
30 Magnolia Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-20 | 2025-02-20
28 Magnolia Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-06-04 | 2025-06-04
28 Magnolia Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-06-02 | 2025-06-02
28 Magnolia Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-29 | 2025-05-29
28 Magnolia Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-05-27 | 2025-05-27 | NC SIDING & REMODELING PRO LLC
28 Magnolia Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-05-22 | 2025-05-22 | NC SIDING & REMODELING PRO LLC
28 Magnolia Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-05-22 | 2025-05-22 | NC SIDING & REMODELING PRO LLC
28 Magnolia Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-05-22 | 2025-05-22 | NC SIDING & REMODELING PRO LLC
28 Magnolia Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-06-20 | 2025-06-20
28 Magnolia Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-07-17 | 2025-07-17
25 Magnolia Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-13 | 2025-03-13
25 Magnolia Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
25 Magnolia Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-17 | 2025-03-17
25 Magnolia Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-13 | 2025-03-13 | Martinez NC Construction LLC [Luis]
25 Magnolia Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-12 | 2025-03-12 | Martinez NC Construction LLC [Luis]
25 Magnolia Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-13 | 2025-03-13 | Martinez NC Construction LLC [Luis]
25 Magnolia Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-12 | 2025-03-12 | Martinez NC Construction LLC [Luis]
25 Magnolia Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-07 | 2025-02-07
25 Magnolia Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-07 | 2025-02-07
24 Magnolia Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-20 | 2025-03-20
24 Magnolia Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-18 | 2025-03-18
24 Magnolia Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
24 Magnolia Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12 | Martinez NC Construction LLC [Luis]
24 Magnolia Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-11 | 2025-03-11 | Martinez NC Construction LLC [Luis]
24 Magnolia Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-12 | 2025-03-12 | Martinez NC Construction LLC [Luis]
24 Magnolia Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-12 | 2025-03-12 | Martinez NC Construction LLC [Luis]
24 Magnolia Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-19 | 2025-03-19
24 Magnolia Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-12 | 2025-02-12
16 Magnolia Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-16 | 2025-04-16 | NC SIDING & REMODELING PRO LLC
16 Magnolia Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-21 | 2025-04-21
16 Magnolia Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
16 Magnolia Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | NC SIDING & REMODELING PRO LLC
16 Magnolia Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-08 | 2025-04-08 | NC SIDING & REMODELING PRO LLC
16 Magnolia Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-04-09 | 2025-04-09 | NC SIDING & REMODELING PRO LLC
16 Magnolia Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09 | NC SIDING & REMODELING PRO LLC
16 Magnolia Estates | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-05 | 2025-03-05
16 Magnolia Estates | Lien # | FALSE | 0 | Lien # | 1 | 2025-03-05 | 2025-03-05
39 Falls Of the Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-23 | 2025-01-23
39 Falls Of the Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-20 | 2025-01-20
39 Falls Of the Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-17 | 2025-01-17
39 Falls Of the Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-15 | 2025-01-15 | Hector Oliverio [Hector]
39 Falls Of the Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-14 | 2025-01-14 | Hector Oliverio [Hector]
39 Falls Of the Cape | Measurements | TRUE | 100 | Measured | 1 | 2025-01-01 | 2025-01-01
39 Falls Of the Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-14 | 2025-01-14 | Hector Oliverio [Hector]
39 Falls Of the Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-12 | 2024-11-12
39 Falls Of the Cape | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-12 | 2024-11-12
Thompson Residence | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-13 | 2025-05-13
Thompson Residence | Invoiced | FALSE | 0 | Close Out | 1 | 2025-05-09 | 2025-05-09
Thompson Residence | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-07 | 2025-05-07
Thompson Residence | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-05-05 | 2025-05-05
Thompson Residence | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-24 | 2025-03-24
Thompson Residence | Measurements | TRUE | 100 | Measured | 1 | 2025-01-13 | 2025-01-13
Thompson Residence | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-09 | 2025-06-09
Thompson Residence | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
Thompson Residence | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
Faircloth Residence | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-05-05 | 2025-05-05
Faircloth Residence | Invoiced | FALSE | 0 | Close Out | 1 | 2025-05-01 | 2025-05-01
Faircloth Residence | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-29 | 2025-04-29
Faircloth Residence | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-25 | 2025-04-25
Faircloth Residence | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-14 | 2025-03-14
Faircloth Residence | Measurements | TRUE | 100 | Measured | 1 | 2025-01-01 | 2025-01-01
Faircloth Residence | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-06-06 | 2025-06-06
Faircloth Residence | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
Faircloth Residence | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
Brogden Residence | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
Brogden Residence | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-03 | 2025-04-03
Brogden Residence | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
Brogden Residence | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28
Brogden Residence | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-03-27 | 2025-03-27
Brogden Residence | Measurements | TRUE | 100 | Measured | 1 | 2025-01-01 | 2025-01-01
Brogden Residence | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09
Brogden Residence | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-05 | 2025-06-05
Brogden Residence | Lien # | FALSE | 0 | Lien # | 1 | 2025-06-05 | 2025-06-05
15 Ellington Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-24 | 2025-02-24
15 Ellington Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
15 Ellington Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-18 | 2025-02-18
15 Ellington Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14 | NC SIDING & REMODELING PRO LLC
15 Ellington Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-10 | 2025-02-10 | NC SIDING & REMODELING PRO LLC
15 Ellington Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-02-11 | 2025-02-11 | NC SIDING & REMODELING PRO LLC
15 Ellington Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-11 | 2025-02-11 | NC SIDING & REMODELING PRO LLC
15 Ellington Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-09 | 2024-12-09
84 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-16 | 2025-01-16
84 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-23 | 2025-01-23
84 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
84 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-08 | 2025-01-08 | Hector Oliverio [Hector]
84 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-07 | 2025-01-07 | Hector Oliverio [Hector]
84 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
84 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-07 | 2025-01-07 | Hector Oliverio [Hector]
84 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-22 | 2024-10-22
84 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-13 | 2024-11-13
83 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-15 | 2025-01-15
83 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
83 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
83 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-07 | 2025-01-07 | Hector Oliverio [Hector]
83 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-06 | 2025-01-06 | Hector Oliverio [Hector]
83 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
83 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-06 | 2025-01-06 | Hector Oliverio [Hector]
83 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-21 | 2024-10-21
83 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-12 | 2024-11-12
63 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2024-12-30 | 2024-12-30
63 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2024-12-23 | 2024-12-23
63 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-24 | 2024-12-24
63 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-12-20 | 2024-12-20 | Hector Oliverio [Hector]
63 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2024-12-19 | 2024-12-19 | Hector Oliverio [Hector]
63 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2024-12-09 | 2024-12-09
63 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2024-12-19 | 2024-12-19 | Hector Oliverio [Hector]
63 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-04 | 2024-10-04
63 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-25 | 2024-10-25
46 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-20 | 2025-03-20
46 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-20 | 2025-03-20
46 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-14 | 2025-03-14
46 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-12 | 2025-03-12 | Hector Oliverio [Hector]
46 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-11 | 2025-03-11 | Hector Oliverio [Hector]
46 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2025-03-04 | 2025-03-04
46 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-11 | 2025-03-11 | Hector Oliverio [Hector]
46 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
46 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-08 | 2025-01-08
91 Falls of The Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-20 | 2025-02-20
91 Falls of The Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
91 Falls of The Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-14 | 2025-02-14
91 Falls of The Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-12 | 2025-02-12 | Hector Oliverio [Hector]
91 Falls of The Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-11 | 2025-02-11 | Hector Oliverio [Hector]
91 Falls of The Cape | Measurements | TRUE | 100 | Measured | 1 | 2025-01-17 | 2025-01-17
91 Falls of The Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-11 | 2025-02-11 | Hector Oliverio [Hector]
91 Falls of The Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-11 | 2024-12-11
91 Falls of The Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-01 | 2025-01-01
74 Olive Grove SF | Paid Painter | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-10-02 | 2024-10-02
74 Olive Grove SF | Paint Complete | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22 | Torres Painting Professional
52 Louisbury Preserve Test | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-10-02 | 2024-10-02
52 Louisbury Preserve Test | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-10-01 | 2024-10-01
52 Louisbury Preserve Test | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-22 | 2025-01-22
52 Louisbury Preserve Test | Invoiced | FALSE | 0 | Close Out | 1 | 2025-01-20 | 2025-01-20
52 Louisbury Preserve Test | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16
52 Louisbury Preserve Test | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14
52 Louisbury Preserve Test | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-12-03 | 2024-12-03
52 Louisbury Preserve Test | Measurements | FALSE | 0 | Measured | 1 | 2024-12-02 | 2024-12-02
52 Louisbury Preserve Test | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-10-21 | 2024-10-21
52 Louisbury Preserve Test | Ordered | TRUE | 100 | Ordered | 1 | 2024-09-17 | 2024-09-17
52 Louisbury Preserve Test | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-17 | 2024-10-17
75 Olive Grove SF | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-03 | 2025-03-03
75 Olive Grove SF | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-15 | 2025-01-15
75 Olive Grove SF | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-16 | 2025-01-16
75 Olive Grove SF | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-14 | 2025-01-14 | Santiago Professional Siding [Santiago]
75 Olive Grove SF | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-13 | 2025-01-13 | Santiago Professional Siding [Santiago]
75 Olive Grove SF | Measurements | TRUE | 100 | Measured | 1 | 2024-12-16 | 2024-12-16
75 Olive Grove SF | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-13 | 2025-01-13 | Santiago Professional Siding [Santiago]
75 Olive Grove SF | Ordered | TRUE | 100 | Ordered | 1 | 2024-10-15 | 2024-10-15
75 Olive Grove SF | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-13 | 2024-11-13
74 Olive Grove SF | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-03 | 2025-03-03
74 Olive Grove SF | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-21 | 2025-01-21
74 Olive Grove SF | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22
74 Olive Grove SF | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20 | Santiago Professional Siding [Santiago]
74 Olive Grove SF | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-17 | 2025-01-17 | Santiago Professional Siding [Santiago]
74 Olive Grove SF | Measurements | TRUE | 100 | Measured | 1 | 2024-11-18 | 2024-11-18
74 Olive Grove SF | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-17 | 2025-01-17 | Santiago Professional Siding [Santiago]
74 Olive Grove SF | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-15 | 2024-11-15
74 Olive Grove SF | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-17 | 2024-12-17
94 Falls of the Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-17 | 2025-03-17
94 Falls of the Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-11 | 2025-03-11
94 Falls of the Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-11 | 2025-03-11
94 Falls of the Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07 | Hector Oliverio [Hector]
94 Falls of the Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-05 | 2025-03-05 | Hector Oliverio [Hector]
94 Falls of the Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-11-17 | 2025-11-17
94 Falls of the Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-05 | 2025-03-05 | Hector Oliverio [Hector]
94 Falls of the Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-01 | 2025-01-01
94 Falls of the Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-02-03 | 2025-02-03
73 Falls of the Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-20 | 2025-01-20
73 Falls of the Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
73 Falls of the Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
73 Falls of the Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-10 | 2025-01-10 | Hector Oliverio [Hector]
73 Falls of the Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-09 | 2025-01-09 | Hector Oliverio [Hector]
73 Falls of the Cape | Measurements | TRUE | 100 | Measured | 1 | 2024-12-20 | 2024-12-20
73 Falls of the Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-09 | 2025-01-09 | Hector Oliverio [Hector]
73 Falls of the Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-07 | 2024-11-07
73 Falls of the Cape | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-10 | 2024-12-10
72 Falls of the Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-20 | 2025-01-20
72 Falls of the Cape | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-13 | 2025-01-13
72 Falls of the Cape | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-13 | 2025-01-13 | Brooke Slaugenhoup
72 Falls of the Cape | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-10 | 2025-01-10 | Hector Oliverio [Hector]
72 Falls of the Cape | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-09 | 2025-01-09 | Hector Oliverio [Hector]
72 Falls of the Cape | Measurements | TRUE | 100 | Measured | 1 | 2024-12-19 | 2024-12-19
72 Falls of the Cape | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-09 | 2025-01-09 | Hector Oliverio [Hector]
72 Falls of the Cape | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-07 | 2024-11-07
72 Falls of the Cape | Lien # | TRUE | 100 | Lien # | 1 | 2024-12-10 | 2024-12-10
71 Falls of the Cape | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-01-23 | 2026-01-23
71 Falls of the Cape | Invoiced | FALSE | 0 | Close Out | 1 | 2026-01-21 | 2026-01-21
71 Falls of the Cape | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-01-19 | 2026-01-19
71 Falls of the Cape | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-01-15 | 2026-01-15
71 Falls of the Cape | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-12-04 | 2025-12-04
71 Falls of the Cape | Measurements | FALSE | 0 | Measured | 1 | 2025-12-08 | 2025-12-08
71 Falls of the Cape | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-09-29 | 2026-09-29
71 Falls of the Cape | Ordered | TRUE | 100 | Ordered | 1 | 2025-09-11 | 2025-09-11
71 Falls of the Cape | Lien # | TRUE | 100 | Lien # | 1 | 2025-10-14 | 2025-10-14
54 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
54 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-07 | 2025-04-07
54 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
54 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | Hector Oliverio [Hector]
54 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-27 | 2025-03-27 | Hector Oliverio [Hector]
54 Kipling Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-03-11 | 2025-03-11
54 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-27 | 2025-03-27 | Hector Oliverio [Hector]
54 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-17 | 2025-01-17
54 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-17 | 2025-01-17
51 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-12 | 2025-02-12
51 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
51 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06
51 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-04 | 2025-02-04 | Hector Oliverio [Hector]
51 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-03 | 2025-02-03 | Hector Oliverio [Hector]
51 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-11-05 | 2025-11-05
51 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | Hector Oliverio [Hector]
51 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-25 | 2024-11-25
51 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-25 | 2024-11-25
74 Harvest Meadows | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-02 | 2025-04-02
74 Harvest Meadows | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-23 | 2025-04-23
74 Harvest Meadows | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-04 | 2025-04-04
74 Harvest Meadows | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-02 | 2025-04-02 | Requena Siding [Jairo]
74 Harvest Meadows | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-02 | 2025-04-02 | Requena Siding [Jairo]
74 Harvest Meadows | Measurements | TRUE | 100 | Measured | 1 | 2025-04-03 | 2025-04-03 | Requena Siding [Jairo]
74 Harvest Meadows | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-01 | 2025-01-01 | Requena Siding [Jairo]
74 Harvest Meadows | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-03 | 2025-03-03
74 Harvest Meadows | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-28 | 2024-11-28
55 Louisbury Test | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2024-12-31 | 2024-12-31
55 Louisbury Test | Invoiced | FALSE | 0 | Close Out | 1 | 2024-12-27 | 2024-12-27
55 Louisbury Test | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-25 | 2024-12-25
55 Louisbury Test | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-23 | 2024-12-23
55 Louisbury Test | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-11-11 | 2024-11-11
55 Louisbury Test | Measurements | FALSE | 0 | Measured | 1 | 2024-11-08 | 2024-11-08
55 Louisbury Test | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-09-09 | 2024-09-09
55 Louisbury Test | Ordered | TRUE | 100 | Ordered | 1 | 2024-09-05 | 2024-09-05
55 Louisbury Test | Lien # | TRUE | 100 | Lien # | 1 | 2024-09-05 | 2024-09-05
37 Glenmere Gardens test | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-09-06 | 2024-09-06
37 Glenmere Gardens test | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-09-05 | 2024-09-05
37 Glenmere Gardens test | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2024-12-27 | 2024-12-27
37 Glenmere Gardens test | Invoiced | FALSE | 0 | Close Out | 1 | 2024-12-25 | 2024-12-25
37 Glenmere Gardens test | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-23 | 2024-12-23
37 Glenmere Gardens test | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-19 | 2024-12-19
37 Glenmere Gardens test | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-11-07 | 2024-11-07
37 Glenmere Gardens test | Measurements | FALSE | 0 | Measured | 1 | 2024-11-06 | 2024-11-06
37 Glenmere Gardens test | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-09-06 | 2024-09-06
37 Glenmere Gardens test | Ordered | TRUE | 100 | Ordered | 1 | 2024-09-04 | 2024-09-04
37 Glenmere Gardens test | Lien # | TRUE | 100 | Lien # | 1 | 2024-09-04 | 2024-09-04
23 Holding Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-16 | 2025-01-16
23 Holding Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-01-14 | 2025-01-14
23 Holding Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-10 | 2025-01-10
23 Holding Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-08 | 2025-01-08
23 Holding Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-11-27 | 2024-11-27
23 Holding Village | Measurements | FALSE | 0 | Measured | 1 | 2024-11-26 | 2024-11-26
23 Holding Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-09-27 | 2024-09-27
23 Holding Village | Lien # | TRUE | 100 | Lien # | 1 | 2024-09-25 | 2024-09-25
15 Ellington Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-15 | 2024-10-15
20 Coolwater | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-11 | 2025-04-11
20 Coolwater | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-16 | 2025-04-16
20 Coolwater | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
20 Coolwater | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Prime Exterior [Siding] LLC [Miguel]
20 Coolwater | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-03 | 2025-04-03 | Prime Exterior [Siding] LLC [Miguel]
20 Coolwater | Measurements | TRUE | 100 | Measured | 1 | 2025-04-03 | 2025-04-03 | Prime Exterior [Siding] LLC [Miguel]
20 Coolwater | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-03 | 2025-04-03 | Prime Exterior [Siding] LLC [Miguel]
20 Coolwater | Ordered | TRUE | 100 | Ordered | 1 | 2025-01-09 | 2025-01-09
20 Coolwater | Lien # | TRUE | 100 | Lien # | 1 | 2025-04-17 | 2025-04-17
26 Coolwater | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-14 | 2025-04-14
26 Coolwater | Invoiced | FALSE | 0 | Close Out | 1 | 2025-04-18 | 2025-04-18
26 Coolwater | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-16 | 2025-04-16
26 Coolwater | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-04-14 | 2025-04-14
26 Coolwater | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-04-14 | 2025-04-14
26 Coolwater | Measurements | FALSE | 0 | Measured | 1 | 2025-04-14 | 2025-04-14
26 Coolwater | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-05-23 | 2025-05-23
26 Coolwater | Ordered | TRUE | 100 | Ordered | 1 | 2025-02-13 | 2025-02-13
26 Coolwater | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-26 | 2025-03-26
24 River Glen TEST | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-09-30 | 2024-09-30
24 River Glen TEST | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-09-27 | 2024-09-27
24 River Glen TEST | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-13 | 2025-01-13
24 River Glen TEST | Invoiced | FALSE | 0 | Close Out | 1 | 2025-01-09 | 2025-01-09
24 River Glen TEST | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-07 | 2025-01-07
24 River Glen TEST | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-01-03 | 2025-01-03
24 River Glen TEST | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-11-22 | 2024-11-22
24 River Glen TEST | Measurements | FALSE | 0 | Measured | 1 | 2024-11-21 | 2024-11-21
24 River Glen TEST | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-09-05 | 2024-09-05
24 River Glen TEST | Ordered | TRUE | 100 | Ordered | 1 | 2024-09-03 | 2024-09-03
24 River Glen TEST | Lien # | TRUE | 100 | Lien # | 1 | 2024-09-03 | 2024-09-03
26 Ellington Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-07 | 2025-04-07
26 Ellington Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-25 | 2025-04-25
26 Ellington Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-01 | 2025-04-01
26 Ellington Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-28 | 2025-03-28 | NC SIDING & REMODELING PRO LLC
26 Ellington Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-25 | 2025-03-25 | NC SIDING & REMODELING PRO LLC
26 Ellington Estates | Measurements | TRUE | 100 | Measured | 1 | 2024-11-13 | 2024-11-13 | NC SIDING & REMODELING PRO LLC
26 Ellington Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-28 | 2025-03-28 | NC SIDING & REMODELING PRO LLC
26 Ellington Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-09-12 | 2024-09-12
114 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-10 | 2025-03-10
114 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-06 | 2025-03-06
114 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-04 | 2025-03-04
114 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-28 | 2025-02-28 | Mendez Siding & Boxing LLC
114 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-26 | 2025-02-26 | Mendez Siding & Boxing LLC
114 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-11-11 | 2025-11-11
114 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-12-09 | 2025-12-09 | Mendez Siding & Boxing LLC
114 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2024-05-21 | 2024-05-21
114 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
113 Hickory Grove | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-07 | 2025-03-07
113 Hickory Grove | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-05 | 2025-03-05
113 Hickory Grove | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-03 | 2025-03-03
113 Hickory Grove | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-27 | 2025-02-27 | Mendez Siding & Boxing LLC
113 Hickory Grove | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-25 | 2025-02-25 | Mendez Siding & Boxing LLC
113 Hickory Grove | Measurements | FALSE | 0 | Measured | 1 | 2025-11-04 | 2025-11-04
113 Hickory Grove | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-11-21 | 2025-11-21 | Mendez Siding & Boxing LLC
113 Hickory Grove | Ordered | TRUE | 100 | Ordered | 1 | 2024-06-05 | 2024-06-05
113 Hickory Grove | Lien # | TRUE | 100 | Lien # | 1 | 2025-03-03 | 2025-03-03
11 Kipling Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-11 | 2025-02-11
11 Kipling Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-26 | 2025-02-26
11 Kipling Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05
11 Kipling Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-03 | 2025-02-03 | Hector Oliverio [Hector]
11 Kipling Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-31 | 2025-01-31 | Hector Oliverio [Hector]
11 Kipling Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-08-19 | 2025-08-19
11 Kipling Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-21 | 2025-04-21 | Hector Oliverio [Hector]
11 Kipling Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-18 | 2024-11-18
11 Kipling Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-18 | 2024-11-18
51 Southern Estates | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-28 | 2025-01-28
51 Southern Estates | Invoiced | TRUE | 100 | Close Out | 1 | 2025-01-28 | 2025-01-28
51 Southern Estates | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-22 | 2025-01-22
51 Southern Estates | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-01-20 | 2025-01-20 | Hector Oliverio [Hector]
51 Southern Estates | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-01-17 | 2025-01-17 | Hector Oliverio [Hector]
51 Southern Estates | Measurements | TRUE | 100 | Measured | 1 | 2024-11-05 | 2024-11-05
51 Southern Estates | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-01-17 | 2025-01-17 | Hector Oliverio [Hector]
51 Southern Estates | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-01 | 2024-11-01
51 Southern Estates | Lien # | TRUE | 100 | Lien # | 1 | 2024-11-05 | 2024-11-05
32 Harvest Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
32 Harvest Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
32 Harvest Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-20 | 2025-02-20
32 Harvest Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-18 | 2025-02-18 | Prime Exterior [Siding] LLC [Miguel]
32 Harvest Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-14 | 2025-02-14 | Prime Exterior [Siding] LLC [Miguel],Ashley Weaver
32 Harvest Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-17 | 2025-02-17 | Prime Exterior [Siding] LLC [Miguel]
32 Harvest Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-18 | 2025-02-18 | Prime Exterior [Siding] LLC [Miguel]
32 Harvest Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-08-23 | 2024-08-23
32 Harvest Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-10-18 | 2024-10-18
51 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-07 | 2025-11-07
51 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-11-05 | 2025-11-05
51 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-11-03 | 2025-11-03
51 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-30 | 2025-10-30
51 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-18 | 2025-09-18
51 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-26 | 2025-09-26
51 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-01-15 | 2026-01-15
51 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-10-13 | 2025-10-13
51 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-10-13 | 2025-10-13
50 Fieldview Village | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-19 | 2025-09-19
50 Fieldview Village | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-17 | 2025-09-17
50 Fieldview Village | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-15 | 2025-09-15
50 Fieldview Village | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-11 | 2025-09-11
50 Fieldview Village | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-07-31 | 2025-07-31
50 Fieldview Village | Measurements | FALSE | 0 | Measured | 1 | 2025-09-18 | 2025-09-18
50 Fieldview Village | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-21 | 2025-08-21
50 Fieldview Village | Ordered | FALSE | 0 | Ordered | 1 | 2025-08-19 | 2025-08-19
50 Fieldview Village | Lien # | FALSE | 0 | Lien # | 1 | 2025-08-19 | 2025-08-19
6 Emerson Fields | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2024-12-16 | 2024-12-16
6 Emerson Fields | Invoiced | FALSE | 0 | Close Out | 1 | 2024-12-12 | 2024-12-12
6 Emerson Fields | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-10 | 2024-12-10
6 Emerson Fields | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2024-12-06 | 2024-12-06
6 Emerson Fields | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2024-10-25 | 2024-10-25
6 Emerson Fields | Measurements | FALSE | 0 | Measured | 1 | 2024-10-24 | 2024-10-24
6 Emerson Fields | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2024-08-27 | 2024-08-27
6 Emerson Fields | Ordered | FALSE | 0 | Ordered | 1 | 2024-08-23 | 2024-08-23
6 Emerson Fields | Lien # | TRUE | 100 | Lien # | 1 | 2024-08-23 | 2024-08-23
Smith Farmhouse | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-01-29 | 2025-01-29
Smith Farmhouse | Invoiced | TRUE | 100 | Close Out | 1 | 2024-08-22 | 2024-08-22
Smith Farmhouse | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-08-16 | 2024-08-16
Smith Farmhouse | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2024-08-14 | 2024-08-14
Smith Farmhouse | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2024-07-15 | 2024-07-15 | Modern Exteriors Inc
Smith Farmhouse | Measurements | TRUE | 100 | Measured | 1 | 2024-09-10 | 2024-09-10
Smith Farmhouse | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2024-05-16 | 2024-05-16
Smith Farmhouse | Ordered | TRUE | 100 | Ordered | 1 | 2024-04-30 | 2024-04-30
Smith Farmhouse | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-14 | 2024-05-14
116 Ashcroft | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-11-05 | 2027-11-05
116 Ashcroft | Invoiced | FALSE | 0 | Close Out | 1 | 2027-11-03 | 2027-11-03
116 Ashcroft | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-11-01 | 2027-11-01
116 Ashcroft | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-10-28 | 2027-10-28
116 Ashcroft | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-09-16 | 2027-09-16
116 Ashcroft | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-10-13 | 2026-10-13
116 Ashcroft | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-26 | 2025-05-26
116 Ashcroft | Measurements | FALSE | 0 | Measured | 1 | 2026-06-19 | 2026-06-19
116 Ashcroft | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-18 | 2024-06-18
15 Duncan's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-02 | 2025-10-02
15 Duncan's Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-30 | 2025-09-30
15 Duncan's Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-26 | 2025-09-26
15 Duncan's Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-24 | 2025-09-24
15 Duncan's Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-13 | 2025-08-13
15 Duncan's Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-12 | 2025-08-12
15 Duncan's Creek | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-30 | 2025-05-30
15 Duncan's Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-06-04 | 2025-06-04
15 Duncan's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
36 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-06-11 | 2027-06-11
36 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-06-09 | 2027-06-09
36 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-06-07 | 2027-06-07
36 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-06-03 | 2027-06-03
36 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-04-22 | 2027-04-22
36 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-06-23 | 2026-06-23
36 High Gate Community | Ordered | FALSE | 0 | Ordered | 27 | 2025-05-01 | 2025-06-06
36 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-12 | 2026-06-12
36 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
34 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-09-14 | 2027-09-14
34 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-09-10 | 2027-09-10
34 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-08 | 2027-09-08
34 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-06 | 2027-09-06
34 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-07-26 | 2027-07-26
34 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-09-24 | 2026-09-24
34 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
34 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-08-11 | 2026-08-11
34 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
33 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-09-17 | 2027-09-17
33 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-09-15 | 2027-09-15
33 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-13 | 2027-09-13
33 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-09 | 2027-09-09
33 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-07-29 | 2027-07-29
33 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-09-29 | 2026-09-29
33 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
33 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-04 | 2026-06-04
33 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
32 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-10-19 | 2027-10-19
32 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-10-15 | 2027-10-15
32 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-10-13 | 2027-10-13
32 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-10-11 | 2027-10-11
32 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-08-30 | 2027-08-30
32 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-10-29 | 2026-10-29
32 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
32 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-11-04 | 2026-11-04
32 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
31 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-12-10 | 2027-12-10
31 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-12-08 | 2027-12-08
31 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-12-06 | 2027-12-06
31 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-12-02 | 2027-12-02
31 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-10-21 | 2027-10-21
31 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-12-29 | 2026-12-29
31 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
31 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-11-04 | 2026-11-04
31 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
30 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-11-10 | 2027-11-10
30 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-11-08 | 2027-11-08
30 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-11-04 | 2027-11-04
30 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-11-02 | 2027-11-02
30 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-09-21 | 2027-09-21
30 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-11-24 | 2026-11-24
30 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
30 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-07-13 | 2026-07-13
30 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
29 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-09-15 | 2027-09-15
29 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-09-13 | 2027-09-13
29 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-09 | 2027-09-09
29 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-07 | 2027-09-07
29 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-07-27 | 2027-07-27
29 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-10-02 | 2026-10-02
29 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
29 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-10-02 | 2026-10-02
29 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
27 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-10-04 | 2027-10-04
27 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-09-30 | 2027-09-30
27 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-28 | 2027-09-28
27 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-09-24 | 2027-09-24
27 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-08-13 | 2027-08-13
27 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-10-29 | 2026-10-29
27 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
27 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-08-12 | 2026-08-12
27 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
26 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-05-21 | 2027-05-21
26 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-05-19 | 2027-05-19
26 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-05-17 | 2027-05-17
26 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-05-13 | 2027-05-13
26 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-04-01 | 2027-04-01
26 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-06-16 | 2026-06-16
26 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
26 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-04 | 2026-06-04
26 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
19 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-07-28 | 2027-07-28
19 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-07-26 | 2027-07-26
19 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-07-22 | 2027-07-22
19 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-07-20 | 2027-07-20
19 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-06-08 | 2027-06-08
19 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-08-31 | 2026-08-31
19 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
19 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-04 | 2026-06-04
19 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
17 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-10-23 | 2026-10-23
17 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-10-21 | 2026-10-21
17 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-10-19 | 2026-10-19
17 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-10-15 | 2026-10-15
17 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-09-03 | 2026-09-03
17 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-11-27 | 2025-11-27
17 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
17 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-04 | 2026-06-04
17 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
16 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2027-08-25 | 2027-08-25
16 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2027-08-23 | 2027-08-23
16 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-08-19 | 2027-08-19
16 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2027-08-17 | 2027-08-17
16 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2027-07-06 | 2027-07-06
16 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2026-09-29 | 2026-09-29
16 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
16 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2026-06-04 | 2026-06-04
16 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
15 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-06-12 | 2026-06-12
15 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-06-10 | 2026-06-10
15 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-06-08 | 2026-06-08
15 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-06-04 | 2026-06-04
15 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-04-23 | 2026-04-23
15 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-07-22 | 2025-07-22
15 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
15 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2025-07-07 | 2025-07-07
15 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
14 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-07-23 | 2026-07-23
14 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-07-21 | 2026-07-21
14 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-17 | 2026-07-17
14 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-15 | 2026-07-15
14 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-06-03 | 2026-06-03
14 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-29 | 2025-08-29
14 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
14 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2025-06-04 | 2025-06-04
14 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
13 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-07-21 | 2026-07-21
13 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-07-17 | 2026-07-17
13 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-15 | 2026-07-15
13 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-13 | 2026-07-13
13 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-06-01 | 2026-06-01
13 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-29 | 2025-08-29
13 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
13 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2025-06-04 | 2025-06-04
13 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
12 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-07-21 | 2026-07-21
12 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-07-17 | 2026-07-17
12 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-15 | 2026-07-15
12 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-13 | 2026-07-13
12 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-06-01 | 2026-06-01
12 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-29 | 2025-08-29
12 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-12 | 2025-05-12
12 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2025-06-04 | 2025-06-04
12 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
10 High Gate Community | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-07-21 | 2026-07-21
10 High Gate Community | Invoiced | FALSE | 0 | Close Out | 1 | 2026-07-17 | 2026-07-17
10 High Gate Community | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-15 | 2026-07-15
10 High Gate Community | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-07-13 | 2026-07-13
10 High Gate Community | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-06-01 | 2026-06-01
10 High Gate Community | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-29 | 2025-08-29
10 High Gate Community | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-01 | 2025-05-01
10 High Gate Community | Measurements | FALSE | 0 | Measured | 1 | 2025-06-04 | 2025-06-04
10 High Gate Community | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-03 | 2024-06-03
157 Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-27 | 2025-03-27
157 Neill's Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-25 | 2025-03-25
157 Neill's Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-07 | 2025-03-07
157 Neill's Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-05 | 2025-03-05 | Junior Omar Reconco
157 Neill's Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-03 | 2025-03-03 | Junior Omar Reconco
157 Neill's Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-03 | 2025-03-03 | Junior Omar Reconco
157 Neill's Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-17 | 2024-12-17
157 Neill's Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-02-03 | 2025-02-03
157 Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-06 | 2025-01-06
4 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-03 | 2025-11-03
4 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-30 | 2025-10-30
4 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-28 | 2025-10-28
4 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-24 | 2025-10-24
4 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-12 | 2025-09-12
4 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-11 | 2025-09-11
4 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-03 | 2025-06-03
4 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-07-03 | 2025-07-03
4 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-11 | 2024-06-11
9 Mason Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-04-25 | 2025-04-25
9 Mason Landing | Invoiced | TRUE | 100 | Close Out | 1 | 2025-04-23 | 2025-04-23
9 Mason Landing | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-15 | 2025-04-15
9 Mason Landing | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-04-11 | 2025-04-11 | Leones Construction LLC
9 Mason Landing | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-04-09 | 2025-04-09 | Leones Construction LLC
9 Mason Landing | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-04-09 | 2025-04-09 | Leones Construction LLC
9 Mason Landing | Ordered | TRUE | 100 | Ordered | 1 | 2025-03-04 | 2025-03-04
9 Mason Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-06-09 | 2025-06-09
9 Mason Landing | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-16 | 2024-05-16
18 Heritage at Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
18 Heritage at Neill's Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-14 | 2025-02-14
18 Heritage at Neill's Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-13 | 2025-02-13
18 Heritage at Neill's Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-11 | 2025-02-11 | Hector Oliverio [Hector]
18 Heritage at Neill's Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-10 | 2025-02-10 | Hector Oliverio [Hector]
18 Heritage at Neill's Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-10 | 2025-02-10 | Hector Oliverio [Hector]
18 Heritage at Neill's Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-10 | 2024-12-10
18 Heritage at Neill's Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-06-17 | 2025-06-17
18 Heritage at Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-22 | 2024-05-22
10 Heritage at Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-03-28 | 2025-03-28
10 Heritage at Neill's Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-03-26 | 2025-03-26
10 Heritage at Neill's Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-21 | 2025-03-21
10 Heritage at Neill's Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-03-19 | 2025-03-19 | Hector Oliverio [Hector]
10 Heritage at Neill's Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-03-18 | 2025-03-18 | Hector Oliverio [Hector]
10 Heritage at Neill's Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-03-18 | 2025-03-18 | Hector Oliverio [Hector]
10 Heritage at Neill's Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-10 | 2024-12-10
10 Heritage at Neill's Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
10 Heritage at Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-22 | 2024-05-22
5 Heritage at Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-18 | 2025-02-18
5 Heritage at Neill's Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-14 | 2025-02-14
5 Heritage at Neill's Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-10 | 2025-02-10
5 Heritage at Neill's Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-06 | 2025-02-06 | Jesus Construction
5 Heritage at Neill's Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2025-02-05 | 2025-02-05 | Jesus Construction
5 Heritage at Neill's Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-05 | 2025-02-05 | Jesus Construction
5 Heritage at Neill's Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-09 | 2024-12-09
5 Heritage at Neill's Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-17 | 2025-01-17
5 Heritage at Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-22 | 2024-05-22
2 Heritage at Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-02-24 | 2025-02-24
2 Heritage at Neill's Creek | Invoiced | TRUE | 100 | Close Out | 1 | 2025-02-20 | 2025-02-20
2 Heritage at Neill's Creek | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-07 | 2025-02-07
2 Heritage at Neill's Creek | Job Complete/Inspected | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2025-02-05 | 2025-02-05 | Jesus Construction
2 Heritage at Neill's Creek | Siding Installation Start | TRUE | 100 | Siding Start | 1 | 2024-06-27 | 2024-06-27 | Jesus Construction
2 Heritage at Neill's Creek | Safety Walk/OSHA Log Signed | TRUE | 100 | Safety Checklist Signed | 1 | 2025-02-03 | 2025-02-03 | Jesus Construction
2 Heritage at Neill's Creek | Ordered | TRUE | 100 | Ordered | 1 | 2024-12-12 | 2024-12-12
2 Heritage at Neill's Creek | Measurements | TRUE | 100 | Measured | 1 | 2025-01-29 | 2025-01-29 | Jesus Construction
2 Heritage at Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-22 | 2024-05-22
206 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-11-03 | 2026-11-03
206 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2026-10-30 | 2026-10-30
206 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-10-28 | 2026-10-28
206 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-10-26 | 2026-10-26
206 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-09-14 | 2026-09-14
206 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-10 | 2025-09-10
206 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-06-03 | 2025-06-03
206 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-09-11 | 2025-09-11
206 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-10 | 2024-06-10
205 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-27 | 2025-10-27
205 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-23 | 2025-10-23
205 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-21 | 2025-10-21
205 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-17 | 2025-10-17
205 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-05 | 2025-09-05
205 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-04 | 2025-09-04
205 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-06 | 2025-05-06
205 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-05 | 2025-08-05
205 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-10 | 2024-06-10
204 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-30 | 2025-10-30
204 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-28 | 2025-10-28
204 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-24 | 2025-10-24
204 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-22 | 2025-10-22
204 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-10 | 2025-09-10
204 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-09 | 2025-09-09
204 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
204 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-06-10 | 2025-06-10
204 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-10 | 2024-06-10
195 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-31 | 2025-10-31
195 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-29 | 2025-10-29
195 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-27 | 2025-10-27
195 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-23 | 2025-10-23
195 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-11 | 2025-09-11
195 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-10 | 2025-09-10
195 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 2 | 2025-05-05 | 2025-05-06
195 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
195 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-17 | 2024-06-17
194 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-05 | 2025-11-05
194 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-11-03 | 2025-11-03
194 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-30 | 2025-10-30
194 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-28 | 2025-10-28
194 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-16 | 2025-09-16
194 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-15 | 2025-09-15
194 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
194 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-13 | 2025-08-13
194 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-20 | 2024-06-20
193 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-03 | 2025-10-03
193 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
193 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-29 | 2025-09-29
193 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
193 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-14 | 2025-08-14
193 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-13 | 2025-08-13
193 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
193 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-05-07 | 2025-05-07
193 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-30 | 2024-05-30
168 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-09-26 | 2025-09-26
168 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-09-24 | 2025-09-24
168 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-22 | 2025-09-22
168 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-18 | 2025-09-18
168 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-07 | 2025-08-07
168 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-06 | 2025-08-06
168 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
168 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-12 | 2025-08-12
168 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-30 | 2024-05-30
165 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-03 | 2025-10-03
165 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-01 | 2025-10-01
165 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-29 | 2025-09-29
165 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-09-25 | 2025-09-25
165 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-08-14 | 2025-08-14
165 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-13 | 2025-08-13
165 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
165 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-01 | 2025-08-01
165 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-30 | 2024-05-30
164 Neill's Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-30 | 2025-10-30
164 Neill's Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-28 | 2025-10-28
164 Neill's Pointe | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-24 | 2025-10-24
164 Neill's Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-22 | 2025-10-22
164 Neill's Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-10 | 2025-09-10
164 Neill's Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-09 | 2025-09-09
164 Neill's Pointe | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
164 Neill's Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
164 Neill's Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-10 | 2024-06-10
158 Neill's Creek | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-10-24 | 2025-10-24
158 Neill's Creek | Invoiced | FALSE | 0 | Close Out | 1 | 2025-10-22 | 2025-10-22
158 Neill's Creek | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-20 | 2025-10-20
158 Neill's Creek | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-16 | 2025-10-16
158 Neill's Creek | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-09-04 | 2025-09-04
158 Neill's Creek | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-03 | 2025-09-03
158 Neill's Creek | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
158 Neill's Creek | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
158 Neill's Creek | Lien # | TRUE | 100 | Lien # | 1 | 2024-06-06 | 2024-06-06
11 Carson's Landing | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-02-06 | 2026-02-06
11 Carson's Landing | Invoiced | FALSE | 0 | Close Out | 1 | 2026-02-04 | 2026-02-04
11 Carson's Landing | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-02-02 | 2026-02-02
11 Carson's Landing | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-01-29 | 2026-01-29
11 Carson's Landing | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-12-18 | 2025-12-18
11 Carson's Landing | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-09-17 | 2025-09-17
11 Carson's Landing | Ordered | FALSE | 0 | Ordered | 1 | 2025-05-05 | 2025-05-05
11 Carson's Landing | Measurements | FALSE | 0 | Measured | 1 | 2025-08-06 | 2025-08-06
11 Carson's Landing | Lien # | TRUE | 100 | Lien # | 1 | 2024-05-22 | 2024-05-22
20 Griffon Pointe | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2026-08-31 | 2026-08-31
20 Griffon Pointe | Invoiced | FALSE | 0 | Close Out | 1 | 2026-08-27 | 2026-08-27
20 Griffon Pointe | Paid Siding Sub | TRUE | 100 | Pay Crew/Ready to Invoice | 1 | 2026-08-25 | 2026-08-25
20 Griffon Pointe | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-08-21 | 2026-08-21 | Mendez Siding & Boxing LLC
20 Griffon Pointe | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-07-10 | 2026-07-10
20 Griffon Pointe | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-01 | 2025-08-01
20 Griffon Pointe | Ordered | TRUE | 100 | Ordered | 1 | 2024-11-18 | 2024-11-18
20 Griffon Pointe | Measurements | FALSE | 0 | Measured | 1 | 2025-06-05 | 2025-06-05
20 Griffon Pointe | Lien # | TRUE | 100 | Lien # | 1 | 2025-01-06 | 2025-01-06
Step Down/Site Condition | Paid Site Condition | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-30 | 2022-08-30
Step Down/Site Condition | Site Condition Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-29 | 2022-08-29
115 Ashcroft | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-12-12 | 2025-12-12
115 Ashcroft | Invoiced | TRUE | 100 | Close Out | 1 | 2024-12-10 | 2024-12-10
115 Ashcroft | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-08-11 | 2026-08-11
115 Ashcroft | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2026-08-07 | 2026-08-07
115 Ashcroft | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2026-06-26 | 2026-06-26
115 Ashcroft | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-04-25 | 2025-04-25
115 Ashcroft | Ordered | TRUE | 100 | Ordered | 1 | 2024-03-28 | 2024-03-28
115 Ashcroft | Measurements | FALSE | 0 | Measured | 1 | 2025-04-29 | 2025-04-29
115 Ashcroft | Lien # | TRUE | 100 | Lien # | 1 | 2024-04-02 | 2024-04-02
18 Mill Stream | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2025-11-20 | 2025-11-20
18 Mill Stream | Invoiced | FALSE | 0 | Close Out | 1 | 2023-08-14 | 2023-08-14
18 Mill Stream | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-21 | 2025-10-21
18 Mill Stream | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2025-10-17 | 2025-10-17
18 Mill Stream | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2025-08-13 | 2025-08-13
18 Mill Stream | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2025-10-13 | 2025-10-13
18 Mill Stream | Ordered | TRUE | 100 | Ordered | 1 | 2023-06-26 | 2023-06-26
18 Mill Stream | Measurements | FALSE | 0 | Measured | 1 | 2025-08-13 | 2025-08-13
18 Mill Stream | Lien # | TRUE | 100 | Lien # | 1 | 2023-07-10 | 2023-07-10
Gutter Template | Paid Gutter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-09-01 | 2022-09-01
Gutter Template | Gutter Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-31 | 2022-08-31
Louvered Wall Template | Paid Louvered Wall | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-18 | 2022-08-18
Louvered Wall Template | Louvered Wall Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-17 | 2022-08-17
Decking Template | Paid Decking | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-22 | 2022-08-22
Decking Template | Decking Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-19 | 2022-08-19
Column Template | Paid Column | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-10 | 2022-08-10
Column Template | Column Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-09 | 2022-08-09
Paint Template | Paid Painter | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-16 | 2022-08-16
Paint Template | Paint Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-15 | 2022-08-15
Waterproof Deck Template | Paid Waterproof Deck | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-26 | 2022-08-26
Waterproof Deck Template | Waterproof Deck Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-25 | 2022-08-25
Screen Porch Template | Paid Screen Porch | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-24 | 2022-08-24
Screen Porch Template | Screen Porch Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-23 | 2022-08-23
Trellis Template | Paid Trellis | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-12 | 2022-08-12
Trellis Template | Trellis Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-11 | 2022-08-11
Rail Template | Paid Rails | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-30 | 2022-08-30
Rail Template | Rails Complete | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-08-29 | 2022-08-29
Siding Template | Safety Walk/OSHA Log Signed | FALSE | 0 | Safety Checklist Signed | 1 | 2022-06-03 | 2022-06-03
Siding Template | 100% Job Complete | FALSE | 0 | Close Out | 1 | 2022-09-22 | 2022-09-22
Siding Template | Invoiced | FALSE | 0 | Close Out | 1 | 2022-09-20 | 2022-09-20
Siding Template | Paid Siding Sub | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-09-16 | 2022-09-16
Siding Template | Job Complete/Inspected | FALSE | 0 | Pay Crew/Ready to Invoice | 1 | 2022-09-14 | 2022-09-14
Siding Template | Siding Installation Start | FALSE | 0 | Siding Start | 1 | 2022-08-03 | 2022-08-03
Siding Template | Ordered | FALSE | 0 | Ordered | 1 | 2022-06-01 | 2022-06-01
Siding Template | Measurements | FALSE | 0 | Measured | 1 | 2022-08-02 | 2022-08-02
Siding Template | Lien # | FALSE | 0 | Lien # | 1 | 2022-06-01 | 2022-06-01
**Addition w/Bath - Slab** | Final Clean | FALSE | 0 |  | 1 | 2014-12-31 | 2014-12-31
**Addition w/Bath - Slab** | Completion items | FALSE | 0 |  | 5 | 2014-12-24 | 2014-12-30
**Addition w/Bath - Slab** | Final inspection | FALSE | 0 |  | 1 | 2014-12-23 | 2014-12-23
**Addition w/Bath - Slab** | Paint baseboards, downspouts, touch up | FALSE | 0 |  | 1 | 2014-12-22 | 2014-12-22
**Addition w/Bath - Slab** | Cabinet touch up | FALSE | 0 |  | 1 | 2014-12-22 | 2014-12-22
**Addition w/Bath - Slab** | Texture touch up | FALSE | 0 |  | 1 | 2014-12-19 | 2014-12-19
**Addition w/Bath - Slab** | Install bath accessories, door hardware | FALSE | 0 |  | 1 | 2014-12-19 | 2014-12-19
**Addition w/Bath - Slab** | Baseover | FALSE | 0 |  | 1 | 2014-12-19 | 2014-12-19
**Addition w/Bath - Slab** | Flooring install | FALSE | 0 |  | 3 | 2014-12-16 | 2014-12-18
**Addition w/Bath - Slab** | Finish electrical | FALSE | 0 |  | 2 | 2014-12-12 | 2014-12-15
**Addition w/Bath - Slab** | Finish plumbing | FALSE | 0 |  | 1 | 2014-12-11 | 2014-12-11
**Addition w/Bath - Slab** | Downspout install | FALSE | 0 |  | 1 | 2014-12-10 | 2014-12-10
**Addition w/Bath - Slab** | Tile floor | FALSE | 0 |  | 3 | 2014-12-09 | 2014-12-11
**Addition w/Bath - Slab** | Tile backsplash | FALSE | 0 |  | 2 | 2014-12-09 | 2014-12-10
**Addition w/Bath - Slab** | Shower glass install | FALSE | 0 |  | 1 | 2014-12-05 | 2014-12-05
**Addition w/Bath - Slab** | Exterior paint | FALSE | 0 |  | 3 | 2014-12-05 | 2014-12-09
**Addition w/Bath - Slab** | Measure shower glass | FALSE | 0 |  | 1 | 2014-12-04 | 2014-12-04
**Addition w/Bath - Slab** | Tile shower | FALSE | 0 |  | 3 | 2014-12-04 | 2014-12-08
**Addition w/Bath - Slab** | Counter top/ tubdeck install | FALSE | 0 |  | 1 | 2014-12-03 | 2014-12-03
**Addition w/Bath - Slab** | Stucco install- finish coat | FALSE | 0 |  | 3 | 2014-12-02 | 2014-12-04
**Addition w/Bath - Slab** | Counter top/ tubdeck template | FALSE | 0 |  | 1 | 2014-12-02 | 2014-12-02
**Addition w/Bath - Slab** | Cabinet delivery/ install | FALSE | 0 |  | 2 | 2014-12-02 | 2014-12-03
**Addition w/Bath - Slab** | Stucco install- brown coat | FALSE | 0 |  | 3 | 2014-11-27 | 2014-12-01
**Addition w/Bath - Slab** | Interior paint | FALSE | 0 |  | 3 | 2014-11-27 | 2014-12-01
**Addition w/Bath - Slab** | Doors, casing, shelving install | FALSE | 0 |  | 2 | 2014-11-27 | 2014-11-28
**Addition w/Bath - Slab** | Stucco scratch coat inspection | FALSE | 0 |  | 1 | 2014-11-26 | 2014-11-26
**Addition w/Bath - Slab** | Tape, Top, Texture | FALSE | 0 |  | 4 | 2014-11-21 | 2014-11-26
**Addition w/Bath - Slab** | Stucco install- scratch coat | FALSE | 0 |  | 3 | 2014-11-21 | 2014-11-25
**Addition w/Bath - Slab** | Drywall inspection | FALSE | 0 |  | 1 | 2014-11-20 | 2014-11-20
**Addition w/Bath - Slab** | Drywall install | FALSE | 0 |  | 3 | 2014-11-17 | 2014-11-19
**Addition w/Bath - Slab** | Insulation inspection | FALSE | 0 |  | 1 | 2014-11-14 | 2014-11-14
**Addition w/Bath - Slab** | Insulation install | FALSE | 0 |  | 1 | 2014-11-13 | 2014-11-13
**Addition w/Bath - Slab** | Plumber to have plumbing on test | FALSE | 0 |  | 1 | 2014-11-12 | 2014-11-12
**Addition w/Bath - Slab** | Frame inspection | FALSE | 0 |  | 1 | 2014-11-12 | 2014-11-12
**Addition w/Bath - Slab** | Alarm Pre-Wire Install | FALSE | 0 |  | 1 | 2014-11-11 | 2014-11-11
**Addition w/Bath - Slab** | Rough electrical | FALSE | 0 |  | 2 | 2014-11-07 | 2014-11-10
**Addition w/Bath - Slab** | Lath install | FALSE | 0 |  | 3 | 2014-11-04 | 2014-11-06
**Addition w/Bath - Slab** | Roof install | FALSE | 0 |  | 3 | 2014-10-30 | 2014-11-03
**Addition w/Bath - Slab** | Rough Plumbing | FALSE | 0 |  | 2 | 2014-10-28 | 2014-10-29
**Addition w/Bath - Slab** | Hot mop shower | FALSE | 0 |  | 1 | 2014-10-27 | 2014-10-27
**Addition w/Bath - Slab** | Gutter install | FALSE | 0 |  | 1 | 2014-10-27 | 2014-10-27
**Addition w/Bath - Slab** | Prime wood windows | FALSE | 0 |  | 1 | 2014-10-24 | 2014-10-24
**Addition w/Bath - Slab** | Hvac install- interior | FALSE | 0 |  | 2 | 2014-10-24 | 2014-10-27
**Addition w/Bath - Slab** | Window install | FALSE | 0 |  | 1 | 2014-10-23 | 2014-10-23
**Addition w/Bath - Slab** | Shear inspection | FALSE | 0 |  | 1 | 2014-10-22 | 2014-10-22
**Addition w/Bath - Slab** | Frame- roof | FALSE | 0 |  | 4 | 2014-10-16 | 2014-10-21
**Addition w/Bath - Slab** | Cabinet measure | FALSE | 0 |  | 1 | 2014-10-10 | 2014-10-10
**Addition w/Bath - Slab** | Frame-walls | FALSE | 0 |  | 4 | 2014-10-10 | 2014-10-15
**Addition w/Bath - Slab** | Slab Cure For Bolts | FALSE | 0 |  | 1 | 2014-10-09 | 2014-10-09
**Addition w/Bath - Slab** | Pour footings/ slab | FALSE | 0 |  | 1 | 2014-10-08 | 2014-10-08
**Addition w/Bath - Slab** | Footing Inspection | FALSE | 0 |  | 1 | 2014-10-07 | 2014-10-07
**Addition w/Bath - Slab** | Install slab steel | FALSE | 0 |  | 1 | 2014-10-06 | 2014-10-06
**Addition w/Bath - Slab** | Rough Plumbing-slab | FALSE | 0 |  | 2 | 2014-10-02 | 2014-10-03
**Addition w/Bath - Slab** | Excavation/ footings | FALSE | 0 |  | 3 | 2014-09-29 | 2014-10-01
**Addition w/Bath - Raised Foundation** | Final Clean | FALSE | 0 |  | 1 | 2014-12-08 | 2014-12-08
**Addition w/Bath - Raised Foundation** | Completion items | FALSE | 0 |  | 5 | 2014-12-01 | 2014-12-05
**Addition w/Bath - Raised Foundation** | Final inspection | FALSE | 0 |  | 1 | 2014-11-28 | 2014-11-28
**Addition w/Bath - Raised Foundation** | Paint baseboards, downspouts, touch up | FALSE | 0 |  | 1 | 2014-11-27 | 2014-11-27
**Addition w/Bath - Raised Foundation** | Cabinet touch up | FALSE | 0 |  | 1 | 2014-11-27 | 2014-11-27
**Addition w/Bath - Raised Foundation** | Texture touch up | FALSE | 0 |  | 1 | 2014-11-26 | 2014-11-26
**Addition w/Bath - Raised Foundation** | Install bath accessories, door hardware | FALSE | 0 |  | 1 | 2014-11-26 | 2014-11-26
**Addition w/Bath - Raised Foundation** | Baseover | FALSE | 0 |  | 1 | 2014-11-26 | 2014-11-26
**Addition w/Bath - Raised Foundation** | Flooring install | FALSE | 0 |  | 3 | 2014-11-21 | 2014-11-25
**Addition w/Bath - Raised Foundation** | Tile floor | FALSE | 0 |  | 3 | 2014-11-21 | 2014-11-25
**Addition w/Bath - Raised Foundation** | Hvac install- exterior unit | FALSE | 0 |  | 1 | 2014-11-20 | 2014-11-20
**Addition w/Bath - Raised Foundation** | Downspout install | FALSE | 0 |  | 1 | 2014-11-20 | 2014-11-20
**Addition w/Bath - Raised Foundation** | Finish electrical | FALSE | 0 |  | 2 | 2014-11-19 | 2014-11-20
**Addition w/Bath - Raised Foundation** | Shower glass install | FALSE | 0 |  | 1 | 2014-11-19 | 2014-11-19
**Addition w/Bath - Raised Foundation** | Finish plumbing | FALSE | 0 |  | 1 | 2014-11-18 | 2014-11-18
**Addition w/Bath - Raised Foundation** | Measure shower glass | FALSE | 0 |  | 1 | 2014-11-18 | 2014-11-18
**Addition w/Bath - Raised Foundation** | Tile shower | FALSE | 0 |  | 3 | 2014-11-18 | 2014-11-20
**Addition w/Bath - Raised Foundation** | Exterior paint | FALSE | 0 |  | 3 | 2014-11-17 | 2014-11-19
**Addition w/Bath - Raised Foundation** | Tile backsplash | FALSE | 0 |  | 2 | 2014-11-14 | 2014-11-17
**Addition w/Bath - Raised Foundation** | Cabinet delivery/ install | FALSE | 0 |  | 2 | 2014-11-14 | 2014-11-17
**Addition w/Bath - Raised Foundation** | Counter top/ tubdeck install | FALSE | 0 |  | 1 | 2014-11-13 | 2014-11-13
**Addition w/Bath - Raised Foundation** | Stucco install- finish coat | FALSE | 0 |  | 3 | 2014-11-12 | 2014-11-14
**Addition w/Bath - Raised Foundation** | Counter top/ tubdeck template | FALSE | 0 |  | 1 | 2014-11-12 | 2014-11-12
**Addition w/Bath - Raised Foundation** | Interior paint | FALSE | 0 |  | 3 | 2014-11-11 | 2014-11-13
**Addition w/Bath - Raised Foundation** | Stucco install- brown coat | FALSE | 0 |  | 3 | 2014-11-07 | 2014-11-11
**Addition w/Bath - Raised Foundation** | Doors, casing, shelving install | FALSE | 0 |  | 2 | 2014-11-07 | 2014-11-10
**Addition w/Bath - Raised Foundation** | Stucco scratch coat inspection | FALSE | 0 |  | 1 | 2014-11-06 | 2014-11-06
**Addition w/Bath - Raised Foundation** | Tape, Top, Texture | FALSE | 0 |  | 4 | 2014-11-03 | 2014-11-06
**Addition w/Bath - Raised Foundation** | Stucco install- scratch coat | FALSE | 0 |  | 3 | 2014-11-03 | 2014-11-05
**Addition w/Bath - Raised Foundation** | Drywall inspection | FALSE | 0 |  | 1 | 2014-10-31 | 2014-10-31
**Addition w/Bath - Raised Foundation** | Drywall install | FALSE | 0 |  | 3 | 2014-10-28 | 2014-10-30
**Addition w/Bath - Raised Foundation** | Insulation inspection | FALSE | 0 |  | 1 | 2014-10-27 | 2014-10-27
**Addition w/Bath - Raised Foundation** | Insulation install | FALSE | 0 |  | 1 | 2014-10-24 | 2014-10-24
**Addition w/Bath - Raised Foundation** | Plumber to have plumbing on test | FALSE | 0 |  | 1 | 2014-10-23 | 2014-10-23
**Addition w/Bath - Raised Foundation** | Frame inspection | FALSE | 0 |  | 1 | 2014-10-23 | 2014-10-23
**Addition w/Bath - Raised Foundation** | Alarm Pre-Wire Install | FALSE | 0 |  | 1 | 2014-10-22 | 2014-10-22
**Addition w/Bath - Raised Foundation** | Rough electrical | FALSE | 0 |  | 2 | 2014-10-20 | 2014-10-21
**Addition w/Bath - Raised Foundation** | Lath install | FALSE | 0 |  | 3 | 2014-10-15 | 2014-10-17
**Addition w/Bath - Raised Foundation** | Roof install | FALSE | 0 |  | 3 | 2014-10-10 | 2014-10-14
**Addition w/Bath - Raised Foundation** | Rough Plumbing- top out | FALSE | 0 |  | 2 | 2014-10-08 | 2014-10-09
**Addition w/Bath - Raised Foundation** | Hot mop shower | FALSE | 0 |  | 1 | 2014-10-07 | 2014-10-07
**Addition w/Bath - Raised Foundation** | Prime (paint) wood windows | FALSE | 0 |  | 1 | 2014-10-06 | 2014-10-06
**Addition w/Bath - Raised Foundation** | Hvac install- interior | FALSE | 0 |  | 2 | 2014-10-06 | 2014-10-07
**Addition w/Bath - Raised Foundation** | Gutter install | FALSE | 0 |  | 1 | 2014-10-06 | 2014-10-06
**Addition w/Bath - Raised Foundation** | Window install | FALSE | 0 |  | 1 | 2014-10-03 | 2014-10-03
**Addition w/Bath - Raised Foundation** | Shear inspection | FALSE | 0 |  | 1 | 2014-10-02 | 2014-10-02
**Addition w/Bath - Raised Foundation** | Frame- roof | FALSE | 0 |  | 4 | 2014-09-26 | 2014-10-01
**Addition w/Bath - Raised Foundation** | Cabinet measure | FALSE | 0 |  | 1 | 2014-09-22 | 2014-09-22
**Addition w/Bath - Raised Foundation** | Frame-walls | FALSE | 0 |  | 4 | 2014-09-22 | 2014-09-25
**Addition w/Bath - Raised Foundation** | Sub floor insulation inspection | FALSE | 0 |  | 1 | 2014-09-19 | 2014-09-19
**Addition w/Bath - Raised Foundation** | Sheet floor | FALSE | 0 |  | 1 | 2014-09-19 | 2014-09-19
**Addition w/Bath - Raised Foundation** | Sub floor insulation | FALSE | 0 |  | 1 | 2014-09-18 | 2014-09-18
**Addition w/Bath - Raised Foundation** | Plumbing inspection | FALSE | 0 |  | 1 | 2014-09-17 | 2014-09-17
**Addition w/Bath - Raised Foundation** | Sub floor plumbing | FALSE | 0 |  | 2 | 2014-09-15 | 2014-09-16
**Addition w/Bath - Raised Foundation** | Frame floor | FALSE | 0 |  | 2 | 2014-09-11 | 2014-09-12
**Addition w/Bath - Raised Foundation** | Footing Cure For Bolts | FALSE | 0 |  | 1 | 2014-09-10 | 2014-09-10
**Addition w/Bath - Raised Foundation** | Pour footings | FALSE | 0 |  | 1 | 2014-09-09 | 2014-09-09
**Addition w/Bath - Raised Foundation** | Footing Inspection | FALSE | 0 |  | 1 | 2014-09-08 | 2014-09-08
**Addition w/Bath - Raised Foundation** | Excavation/ footings | FALSE | 0 |  | 5 | 2014-09-01 | 2014-09-05
**Remodel - Basement** | Job Breakdown | FALSE | 0 |  | 2 | 2015-03-09 | 2015-03-10
**Remodel - Basement** | Painting - Final Coat | FALSE | 0 |  | 4 | 2015-03-03 | 2015-03-06
**Remodel - Basement** | Plumbing - Finishing | FALSE | 0 |  | 1 | 2015-03-02 | 2015-03-02
**Remodel - Basement** | Electrical - Finishing | FALSE | 0 |  | 1 | 2015-03-02 | 2015-03-02
**Remodel - Basement** | Finish Carpentry - Counter Tops | FALSE | 0 |  | 1 | 2015-02-27 | 2015-02-27
**Remodel - Basement** | Finish Carpentry - Misc. | FALSE | 0 |  | 5 | 2015-02-24 | 2015-03-02
**Remodel - Basement** | Finish Carpentry - Cabinetry | FALSE | 0 |  | 3 | 2015-02-24 | 2015-02-26
**Remodel - Basement** | Flooring Install | FALSE | 0 |  | 2 | 2015-02-20 | 2015-02-23
**Remodel - Basement** | Tile Installation | FALSE | 0 |  | 3 | 2015-02-17 | 2015-02-19
**Remodel - Basement** | Painting - Second Coat | FALSE | 0 |  | 3 | 2015-02-12 | 2015-02-16
**Remodel - Basement** | Trim and Door Installation | FALSE | 0 |  | 2 | 2015-02-10 | 2015-02-11
**Remodel - Basement** | Stair and Railings | FALSE | 0 |  | 1 | 2015-02-10 | 2015-02-10
**Remodel - Basement** | Electrical - Lighting Rough-In | FALSE | 0 |  | 1 | 2015-02-10 | 2015-02-10
**Remodel - Basement** | Painting - Prime Coat | FALSE | 0 |  | 1 | 2015-02-09 | 2015-02-09
**Remodel - Basement** | Drywall | FALSE | 0 |  | 6 | 2015-01-30 | 2015-02-06
**Remodel - Basement** | A/V Pre-Wiring | FALSE | 0 |  | 1 | 2015-01-29 | 2015-01-29
**Remodel - Basement** | Ceiling Insulation | FALSE | 0 |  | 1 | 2015-01-28 | 2015-01-28
**Remodel - Basement** | Electrical Rough-In | FALSE | 0 |  | 2 | 2015-01-26 | 2015-01-27
**Remodel - Basement** | Lighting Layout | FALSE | 0 |  | 1 | 2015-01-26 | 2015-01-26
**Remodel - Basement** | Ceiling Framing | FALSE | 0 |  | 4 | 2015-01-26 | 2015-01-29
**Remodel - Basement** | Fireplace Install | FALSE | 0 |  | 1 | 2015-01-26 | 2015-01-26
**Remodel - Basement** | Bulkhead Framing | FALSE | 0 |  | 2 | 2015-01-22 | 2015-01-23
**Remodel - Basement** | Wall Insulation | FALSE | 0 |  | 1 | 2015-01-20 | 2015-01-20
**Remodel - Basement** | Ductwork Alterations | FALSE | 0 |  | 2 | 2015-01-20 | 2015-01-21
**Remodel - Basement** | Plumbing Rough-In | FALSE | 0 |  | 1 | 2015-01-20 | 2015-01-20
**Remodel - Basement** | Wall Framing | FALSE | 0 |  | 9 | 2015-01-07 | 2015-01-19
**Remodel - Basement** | Subfloor Install | FALSE | 0 |  | 2 | 2015-01-05 | 2015-01-06
**Remodel - Basement** | Concrete Patching | FALSE | 0 |  | 1 | 2015-01-02 | 2015-01-02
**Remodel - Basement** | Underground Plumbing Rough-in | FALSE | 0 |  | 1 | 2015-01-01 | 2015-01-01
**Remodel - Basement** | Initial Material Delivery | FALSE | 0 |  | 1 | 2015-01-01 | 2015-01-01
**Remodel - Basement** | Plumbing Breakout | FALSE | 0 |  | 1 | 2014-12-31 | 2014-12-31
**Remodel - Basement** | Plumbing Layout | FALSE | 0 |  | 1 | 2014-12-30 | 2014-12-30
**Remodel - Basement** | Demolition | FALSE | 0 |  | 5 | 2014-12-30 | 2015-01-05
**Remodel - Basement** | Job Start | FALSE | 0 |  | 1 | 2014-12-29 | 2014-12-29
**Remodel - Bathroom** | Pick Up Portable Toilet | FALSE | 0 |  | 1 | 2015-03-20 | 2015-03-20
**Remodel - Bathroom** | Final Clean | FALSE | 0 |  | 1 | 2015-03-20 | 2015-03-20
**Remodel - Bathroom** | Completion items | FALSE | 0 |  | 5 | 2015-03-13 | 2015-03-19
**Remodel - Bathroom** | Install baseboard | FALSE | 0 |  | 1 | 2015-03-13 | 2015-03-13
**Remodel - Bathroom** | Final inspection | FALSE | 0 |  | 1 | 2015-03-12 | 2015-03-12
**Remodel - Bathroom** | Paint baseboards, touch up | FALSE | 0 |  | 1 | 2015-03-11 | 2015-03-11
**Remodel - Bathroom** | Cabinet touch up | FALSE | 0 |  | 1 | 2015-03-11 | 2015-03-11
**Remodel - Bathroom** | Texture touch up | FALSE | 0 |  | 1 | 2015-03-10 | 2015-03-10
**Remodel - Bathroom** | Install bath accessories | FALSE | 0 |  | 1 | 2015-03-10 | 2015-03-10
**Remodel - Bathroom** | Finish plumbing | FALSE | 0 |  | 1 | 2015-03-10 | 2015-03-10
**Remodel - Bathroom** | Install tile-floor | FALSE | 0 |  | 3 | 2015-03-10 | 2015-03-12
**Remodel - Bathroom** | Finish electrical | FALSE | 0 |  | 1 | 2015-03-09 | 2015-03-09
**Remodel - Bathroom** | Shower glass install | FALSE | 0 |  | 1 | 2015-03-06 | 2015-03-06
**Remodel - Bathroom** | Install backsplsh | FALSE | 0 |  | 2 | 2015-03-05 | 2015-03-06
**Remodel - Bathroom** | Shower glass measure | FALSE | 0 |  | 1 | 2015-03-05 | 2015-03-05
**Remodel - Bathroom** | Install tile-hower | FALSE | 0 |  | 3 | 2015-03-05 | 2015-03-09
**Remodel - Bathroom** | Install counter top/ tub deck | FALSE | 0 |  | 1 | 2015-03-04 | 2015-03-04
**Remodel - Bathroom** | Counter top/ tub deck template | FALSE | 0 |  | 1 | 2015-03-03 | 2015-03-03
**Remodel - Bathroom** | Install cabinets | FALSE | 0 |  | 2 | 2015-03-03 | 2015-03-04
**Remodel - Bathroom** | Interior paint | FALSE | 0 |  | 3 | 2015-02-26 | 2015-03-02
**Remodel - Bathroom** | Install doors,casing | FALSE | 0 |  | 1 | 2015-02-25 | 2015-02-25
**Remodel - Bathroom** | Tape, Top, Texture | FALSE | 0 |  | 4 | 2015-02-19 | 2015-02-24
**Remodel - Bathroom** | Sheetrock Inspection | FALSE | 0 |  | 1 | 2015-02-18 | 2015-02-18
**Remodel - Bathroom** | Installheetrock | FALSE | 0 |  | 2 | 2015-02-16 | 2015-02-17
**Remodel - Bathroom** | Plumber to have plumbing on test | FALSE | 0 |  | 1 | 2015-02-13 | 2015-02-13
**Remodel - Bathroom** | Install Insulation | FALSE | 0 |  | 1 | 2015-02-13 | 2015-02-13
**Remodel - Bathroom** | Frame inspection | FALSE | 0 |  | 1 | 2015-02-13 | 2015-02-13
**Remodel - Bathroom** | Hot mophower | FALSE | 0 |  | 1 | 2015-02-12 | 2015-02-12
**Remodel - Bathroom** | Rough electrical | FALSE | 0 |  | 2 | 2015-02-10 | 2015-02-11
**Remodel - Bathroom** | Rough Plumbing | FALSE | 0 |  | 2 | 2015-02-06 | 2015-02-09
**Remodel - Bathroom** | Cabinet measure | FALSE | 0 |  | 1 | 2015-02-06 | 2015-02-06
**Remodel - Bathroom** | Framewalk | FALSE | 0 |  | 1 | 2015-02-04 | 2015-02-04
**Remodel - Bathroom** | Install ducting | FALSE | 0 |  | 1 | 2015-02-04 | 2015-02-04
**Remodel - Bathroom** | Frame | FALSE | 0 |  | 2 | 2015-02-04 | 2015-02-05
**Remodel - Bathroom** | Install dust protection | FALSE | 0 |  | 1 | 2015-02-02 | 2015-02-02
**Remodel - Bathroom** | Demo | FALSE | 0 |  | 2 | 2015-02-02 | 2015-02-03
**Remodel - Bathroom** | Deliver Portable Toilet | FALSE | 0 |  | 1 | 2015-02-02 | 2015-02-02
**Remodel - Kitchen** | Remove Portable Toilet | FALSE | 0 |  | 1 | 2015-04-23 | 2015-04-23
**Remodel - Kitchen** | Final Clean | FALSE | 0 |  | 1 | 2015-04-23 | 2015-04-23
**Remodel - Kitchen** | Completion items | FALSE | 0 |  | 5 | 2015-04-16 | 2015-04-22
**Remodel - Kitchen** | Final inspection | FALSE | 0 |  | 1 | 2015-04-15 | 2015-04-15
**Remodel - Kitchen** | Paint baseboards, touch up | FALSE | 0 |  | 1 | 2015-04-14 | 2015-04-14
**Remodel - Kitchen** | Cabinet touch up | FALSE | 0 |  | 1 | 2015-04-14 | 2015-04-14
**Remodel - Kitchen** | Install door hardware | FALSE | 0 |  | 1 | 2015-04-13 | 2015-04-13
**Remodel - Kitchen** | Appliance Install | FALSE | 0 |  | 1 | 2015-04-13 | 2015-04-13
**Remodel - Kitchen** | Texture touch up | FALSE | 0 |  | 1 | 2015-04-10 | 2015-04-10
**Remodel - Kitchen** | Finish plumbing | FALSE | 0 |  | 1 | 2015-04-10 | 2015-04-10
**Remodel - Kitchen** | Finish electrical | FALSE | 0 |  | 2 | 2015-04-08 | 2015-04-09
**Remodel - Kitchen** | Install baseboard | FALSE | 0 |  | 1 | 2015-04-07 | 2015-04-07
**Remodel - Kitchen** | Install backsplsh | FALSE | 0 |  | 2 | 2015-04-06 | 2015-04-07
**Remodel - Kitchen** | Install counter tops | FALSE | 0 |  | 1 | 2015-04-03 | 2015-04-03
**Remodel - Kitchen** | Install flooring | FALSE | 0 |  | 3 | 2015-04-02 | 2015-04-06
**Remodel - Kitchen** | Counter top template | FALSE | 0 |  | 1 | 2015-04-02 | 2015-04-02
**Remodel - Kitchen** | Install cabinets | FALSE | 0 |  | 3 | 2015-03-30 | 2015-04-01
**Remodel - Kitchen** | Interior paint | FALSE | 0 |  | 3 | 2015-03-25 | 2015-03-27
**Remodel - Kitchen** | Install doors,casing | FALSE | 0 |  | 1 | 2015-03-24 | 2015-03-24
**Remodel - Kitchen** | Tape, Top, Texture | FALSE | 0 |  | 4 | 2015-03-18 | 2015-03-23
**Remodel - Kitchen** | Sheetrock Inspection | FALSE | 0 |  | 1 | 2015-03-17 | 2015-03-17
**Remodel - Kitchen** | Install Sheetrock | FALSE | 0 |  | 2 | 2015-03-13 | 2015-03-16
**Remodel - Kitchen** | Install Insulation | FALSE | 0 |  | 1 | 2015-03-12 | 2015-03-12
**Remodel - Kitchen** | Frame inspection | FALSE | 0 |  | 1 | 2015-03-12 | 2015-03-12
**Remodel - Kitchen** | Rough electrical | FALSE | 0 |  | 2 | 2015-03-10 | 2015-03-11
**Remodel - Kitchen** | Rough Plumbing | FALSE | 0 |  | 2 | 2015-03-06 | 2015-03-09
**Remodel - Kitchen** | Cabinet measure | FALSE | 0 |  | 1 | 2015-03-06 | 2015-03-06
**Remodel - Kitchen** | Framewalk | FALSE | 0 |  | 1 | 2015-03-04 | 2015-03-04
**Remodel - Kitchen** | Frame | FALSE | 0 |  | 2 | 2015-03-04 | 2015-03-05
**Remodel - Kitchen** | Install dust protection | FALSE | 0 |  | 1 | 2015-03-02 | 2015-03-02
**Remodel - Kitchen** | Demo | FALSE | 0 |  | 2 | 2015-03-02 | 2015-03-03
**Remodel - Kitchen** | Deliver Portable Toilet | FALSE | 0 |  | 1 | 2015-03-02 | 2015-03-02
**Remodel - Kitchen** | Check ducting for hood | FALSE | 0 |  | 1 | 2015-03-02 | 2015-03-02
**New Home - Detailed** | Final Walkthrough | FALSE | 0 |  | 1 | 2015-09-10 | 2015-09-10
**New Home - Detailed** | Punchlist Interior | FALSE | 0 |  | 1 | 2015-09-09 | 2015-09-09
**New Home - Detailed** | Paint Touch-upv | FALSE | 0 |  | 1 | 2015-09-08 | 2015-09-08
**New Home - Detailed** | Final Inspection | FALSE | 0 |  | 1 | 2015-09-07 | 2015-09-07
**New Home - Detailed** | Adjust Cabinets | FALSE | 0 |  | 1 | 2015-09-04 | 2015-09-04
**New Home - Detailed** | Mechanical Start Ups | FALSE | 0 |  | 1 | 2015-09-03 | 2015-09-03
**New Home - Detailed** | Install Meters | FALSE | 0 |  | 1 | 2015-09-02 | 2015-09-02
**New Home - Detailed** | Gas Meter Set | FALSE | 0 |  | 1 | 2015-09-02 | 2015-09-02
**New Home - Detailed** | Final Clean | FALSE | 0 |  | 3 | 2015-09-02 | 2015-09-04
**New Home - Detailed** | Install house numbers | FALSE | 0 |  | 1 | 2015-09-01 | 2015-09-01
**New Home - Detailed** | Install Garage Door Operators | FALSE | 0 |  | 1 | 2015-09-01 | 2015-09-01
**New Home - Detailed** | Final Inspections | FALSE | 0 |  | 1 | 2015-09-01 | 2015-09-01
**New Home - Detailed** | Install Ref. Dishwashers & Trash Compt | FALSE | 0 |  | 1 | 2015-08-31 | 2015-08-31
**New Home - Detailed** | Install Appliance Pans | FALSE | 0 |  | 1 | 2015-08-31 | 2015-08-31
**New Home - Detailed** | Carpet Install | FALSE | 0 |  | 2 | 2015-08-31 | 2015-09-01
**New Home - Detailed** | Hardwood Floors Sand & Seal or Prefinished | FALSE | 0 |  | 4 | 2015-08-25 | 2015-08-28
**New Home - Detailed** | Blow Attic Insulation | FALSE | 0 |  | 1 | 2015-08-25 | 2015-08-25
**New Home - Detailed** | Other Low Voltage Trim | FALSE | 0 |  | 1 | 2015-08-24 | 2015-08-24
**New Home - Detailed** | Insulate Attic/Crawl Space | FALSE | 0 |  | 1 | 2015-08-24 | 2015-08-24
**New Home - Detailed** | Install First Phase of Appliances | FALSE | 0 |  | 1 | 2015-08-24 | 2015-08-24
**New Home - Detailed** | Shower Enclosures | FALSE | 0 |  | 1 | 2015-08-20 | 2015-08-20
**New Home - Detailed** | Electrical Trim | FALSE | 0 |  | 2 | 2015-08-20 | 2015-08-21
**New Home - Detailed** | Wrought Iron Railing | FALSE | 0 |  | 1 | 2015-08-17 | 2015-08-17
**New Home - Detailed** | Mailbox Install | FALSE | 0 |  | 1 | 2015-08-17 | 2015-08-17
**New Home - Detailed** | Plumbing Set Out | FALSE | 0 |  | 4 | 2015-08-14 | 2015-08-19
**New Home - Detailed** | Mirrors Install | FALSE | 0 |  | 1 | 2015-08-14 | 2015-08-14
**New Home - Detailed** | Wallpaper | FALSE | 0 |  | 2 | 2015-08-12 | 2015-08-13
**New Home - Detailed** | HVAC Finish | FALSE | 0 |  | 2 | 2015-08-12 | 2015-08-13
**New Home - Detailed** | Tile counter Tops & Backsplash | FALSE | 0 |  | 2 | 2015-08-10 | 2015-08-11
**New Home - Detailed** | Landscaping/Finish Grade | FALSE | 0 |  | 5 | 2015-08-10 | 2015-08-14
**New Home - Detailed** | Interior Hardware/Locksets | FALSE | 0 |  | 4 | 2015-08-10 | 2015-08-13
**New Home - Detailed** | Install Lamnite Countertops | FALSE | 0 |  | 1 | 2015-08-07 | 2015-08-07
**New Home - Detailed** | Install Cultured Marble Countertops | FALSE | 0 |  | 1 | 2015-08-06 | 2015-08-06
**New Home - Detailed** | Gutters Install | FALSE | 0 |  | 2 | 2015-08-06 | 2015-08-07
**New Home - Detailed** | Install Granite/Marble Counter Tops | FALSE | 0 |  | 3 | 2015-08-03 | 2015-08-05
**New Home - Detailed** | Driveway | FALSE | 0 |  | 3 | 2015-08-03 | 2015-08-05
**New Home - Detailed** | Trim Clean | FALSE | 0 |  | 1 | 2015-07-20 | 2015-07-20
**New Home - Detailed** | Paint | FALSE | 0 |  | 10 | 2015-07-20 | 2015-07-31
**New Home - Detailed** | Interior Trim | FALSE | 0 |  | 7 | 2015-07-09 | 2015-07-17
**New Home - Detailed** | Set Cabinets & Vanities | FALSE | 0 |  | 1 | 2015-07-08 | 2015-07-08
**New Home - Detailed** | Install Interior Doors | FALSE | 0 |  | 2 | 2015-07-07 | 2015-07-08
**New Home - Detailed** | Hardwood Flooring Install | FALSE | 0 |  | 2 | 2015-07-06 | 2015-07-07
**New Home - Detailed** | Deliver Interior Doors & Trim | FALSE | 0 |  | 1 | 2015-07-06 | 2015-07-06
**New Home - Detailed** | Ceramic Tile - Tubs Surrounds & Showers | FALSE | 0 |  | 5 | 2015-06-29 | 2015-07-03
**New Home - Detailed** | Second Stage Polycel | FALSE | 0 |  | 1 | 2015-06-26 | 2015-06-26
**New Home - Detailed** | Paint Ceiling & First Coat Walls | FALSE | 0 |  | 2 | 2015-06-26 | 2015-06-29
**New Home - Detailed** | Finishing Trades | FALSE | 0 |  | 15 | 2015-06-26 | 2015-07-16
**New Home - Detailed** | Sheetrock Clean | FALSE | 0 |  | 1 | 2015-06-25 | 2015-06-25
**New Home - Detailed** | Texture | FALSE | 0 |  | 1 | 2015-06-24 | 2015-06-24
**New Home - Detailed** | Tape & Float | FALSE | 0 |  | 10 | 2015-06-10 | 2015-06-23
**New Home - Detailed** | Sheetrock Inspection | FALSE | 0 |  | 1 | 2015-06-10 | 2015-06-10
**New Home - Detailed** | Hang Sheetrock | FALSE | 0 |  | 2 | 2015-06-08 | 2015-06-09
**New Home - Detailed** | Insulation Inspection | FALSE | 0 |  | 1 | 2015-06-05 | 2015-06-05
**New Home - Detailed** | Schedule Hardwood Floor Installation | FALSE | 0 |  | 1 | 2015-06-04 | 2015-06-04
**New Home - Detailed** | Install Batts or Blown in Wall Insulation | FALSE | 0 |  | 1 | 2015-06-03 | 2015-06-03
**New Home - Detailed** | Poly Cel & Bafler Installation | FALSE | 0 |  | 1 | 2015-06-02 | 2015-06-02
**New Home - Detailed** | Install Septic Field | FALSE | 0 |  | 3 | 2015-05-28 | 2015-06-01
**New Home - Detailed** | Dig Hole for Propane Tank | FALSE | 0 |  | 1 | 2015-05-27 | 2015-05-27
**New Home - Detailed** | Underground Gas Line | FALSE | 0 |  | 1 | 2015-05-25 | 2015-05-25
**New Home - Detailed** | Underground Electric | FALSE | 0 |  | 1 | 2015-05-25 | 2015-05-25
**New Home - Detailed** | Install Roofing & Shingles | FALSE | 0 |  | 6 | 2015-05-25 | 2015-06-01
**New Home - Detailed** | Dig Septic Tank | FALSE | 0 |  | 2 | 2015-05-25 | 2015-05-26
**New Home - Detailed** | Clean up after Masonry Work | FALSE | 0 |  | 1 | 2015-05-25 | 2015-05-25
**New Home - Detailed** | Stone/Brick Installation | FALSE | 0 |  | 10 | 2015-05-11 | 2015-05-22
**New Home - Detailed** | Stucoo - Final Coat of Paint | FALSE | 0 |  | 2 | 2015-05-07 | 2015-05-08
**New Home - Detailed** | Stucco - First Coat Paint | FALSE | 0 |  | 1 | 2015-05-06 | 2015-05-06
**New Home - Detailed** | Stucco - Prime | FALSE | 0 |  | 1 | 2015-05-05 | 2015-05-05
**New Home - Detailed** | Stucco - Finish Coat | FALSE | 0 |  | 5 | 2015-04-28 | 2015-05-04
**New Home - Detailed** | Stucco - Scratch Coat | FALSE | 0 |  | 5 | 2015-04-21 | 2015-04-27
**New Home - Detailed** | Clean & Cover Windows | FALSE | 0 |  | 2 | 2015-04-21 | 2015-04-22
**New Home - Detailed** | Rough Interior & Exterior Structure | FALSE | 0 |  | 15 | 2015-04-20 | 2015-05-08
**New Home - Detailed** | Spray Walls with Insect Treatment | FALSE | 0 |  | 1 | 2015-04-20 | 2015-04-20
**New Home - Detailed** | Sound insulate master bedroom | FALSE | 0 |  | 1 | 2015-04-20 | 2015-04-20
**New Home - Detailed** | Run the studs | FALSE | 0 |  | 1 | 2015-04-20 | 2015-04-20
**New Home - Detailed** | Other Low Voltage Rough-ins | FALSE | 0 |  | 1 | 2015-04-20 | 2015-04-20
**New Home - Detailed** | Vac. Out Interior Walls | FALSE | 0 |  | 1 | 2015-04-17 | 2015-04-17
**New Home - Detailed** | Reinspections | FALSE | 0 |  | 1 | 2015-04-16 | 2015-04-16
**New Home - Detailed** | Pull all test balls (rough in) | FALSE | 0 |  | 1 | 2015-04-14 | 2015-04-14
**New Home - Detailed** | Inspects on Underground lines | FALSE | 0 |  | 1 | 2015-04-14 | 2015-04-14
**New Home - Detailed** | Inspection Corrections | FALSE | 0 |  | 2 | 2015-04-14 | 2015-04-15
**New Home - Detailed** | Masonry/Stucco | FALSE | 0 |  | 15 | 2015-04-14 | 2015-05-04
**New Home - Detailed** | Stucco - Install Felt Paper & Lath | FALSE | 0 |  | 6 | 2015-04-13 | 2015-04-20
**New Home - Detailed** | Security Rough-in | FALSE | 0 |  | 5 | 2015-04-13 | 2015-04-17
**New Home - Detailed** | Framing & Rough Inspections | FALSE | 0 |  | 1 | 2015-04-13 | 2015-04-13
**New Home - Detailed** | Painting Exterior | FALSE | 0 |  | 2 | 2015-04-08 | 2015-04-09
**New Home - Detailed** | Frame in Fireplace & Vent Hood | FALSE | 0 |  | 1 | 2015-04-08 | 2015-04-08
**New Home - Detailed** | Electrical Rough-in | FALSE | 0 |  | 3 | 2015-04-08 | 2015-04-10
**New Home - Detailed** | Run Water & Sewer Lines | FALSE | 0 |  | 1 | 2015-04-02 | 2015-04-02
**New Home - Detailed** | Rough HVAC | FALSE | 0 |  | 4 | 2015-04-02 | 2015-04-07
**New Home - Detailed** | Install Shower Pans | FALSE | 0 |  | 3 | 2015-04-02 | 2015-04-06
**New Home - Detailed** | Block for grab bars, hand rails, t/p holders, towe | FALSE | 0 |  | 1 | 2015-04-02 | 2015-04-02
**New Home - Detailed** | Wrap Shower Walls with Felt Paper | FALSE | 0 |  | 1 | 2015-04-01 | 2015-04-01
**New Home - Detailed** | Insulate sewer lines from second floor to first | FALSE | 0 |  | 1 | 2015-04-01 | 2015-04-01
**New Home - Detailed** | Cornice & Siding Installation | FALSE | 0 |  | 5 | 2015-04-01 | 2015-04-07
**New Home - Detailed** | Build Shower Curbs | FALSE | 0 |  | 1 | 2015-04-01 | 2015-04-01
**New Home - Detailed** | Block out for tub access - master | FALSE | 0 |  | 1 | 2015-04-01 | 2015-04-01
**New Home - Detailed** | Seal walls under tub(s) on exterior walls | FALSE | 0 |  | 1 | 2015-03-30 | 2015-03-30
**New Home - Detailed** | Install Foil Wrap if applicable | FALSE | 0 |  | 2 | 2015-03-30 | 2015-03-31
**New Home - Detailed** | Mechanical Rough Ins | FALSE | 0 |  | 10 | 2015-03-30 | 2015-04-10
**New Home - Detailed** | Plumbing Rough-in | FALSE | 0 |  | 6 | 2015-03-24 | 2015-03-31
**New Home - Detailed** | Install House Wrap or Felt Paper | FALSE | 0 |  | 4 | 2015-03-24 | 2015-03-27
**New Home - Detailed** | Build Masonry Fireplaces | FALSE | 0 |  | 5 | 2015-03-24 | 2015-03-30
**New Home - Detailed** | Install Windows & Doors | FALSE | 0 |  | 5 | 2015-03-23 | 2015-03-27
**New Home - Detailed** | Dry In Roof & Install Flashings | FALSE | 0 |  | 1 | 2015-03-23 | 2015-03-23
**New Home - Detailed** | Sheathing Inspection | FALSE | 0 |  | 1 | 2015-03-20 | 2015-03-20
**New Home - Detailed** | Deck Roof | FALSE | 0 |  | 1 | 2015-03-20 | 2015-03-20
**New Home - Detailed** | Install Exterior Sheathing | FALSE | 0 |  | 2 | 2015-03-18 | 2015-03-19
**New Home - Detailed** | Run ceiling Joists & Frame Roof | FALSE | 0 |  | 9 | 2015-03-05 | 2015-03-17
**New Home - Detailed** | Prime Fascia Material | FALSE | 0 |  | 1 | 2015-03-05 | 2015-03-05
**New Home - Detailed** | Frame Second Floor | FALSE | 0 |  | 5 | 2015-02-26 | 2015-03-04
**New Home - Detailed** | Install subfloor | FALSE | 0 |  | 1 | 2015-02-25 | 2015-02-25
**New Home - Detailed** | Set Floor Trusses/Joists | FALSE | 0 |  | 2 | 2015-02-23 | 2015-02-24
**New Home - Detailed** | Pour Polysteel Second Floor Forms | FALSE | 0 |  | 1 | 2015-02-23 | 2015-02-23
**New Home - Detailed** | Inspect Polysteel Second Floors Forms | FALSE | 0 |  | 1 | 2015-02-20 | 2015-02-20
**New Home - Detailed** | Frame First Floor | FALSE | 0 |  | 6 | 2015-02-19 | 2015-02-26
**New Home - Detailed** | Set Polysteel Second Floor | FALSE | 0 |  | 2 | 2015-02-18 | 2015-02-19
**New Home - Detailed** | Score Concrete if Applicable | FALSE | 0 |  | 1 | 2015-02-18 | 2015-02-18
**New Home - Detailed** | Pour Polysteel First Floor Forms | FALSE | 0 |  | 1 | 2015-02-17 | 2015-02-17
**New Home - Detailed** | Install Area Drains | FALSE | 0 |  | 2 | 2015-02-17 | 2015-02-18
**New Home - Detailed** | Framing | FALSE | 0 |  | 20 | 2015-02-17 | 2015-03-16
**New Home - Detailed** | Polysteel | FALSE | 0 |  | 12 | 2015-02-17 | 2015-03-04
**New Home - Detailed** | Set polysteel forms | FALSE | 0 |  | 1 | 2015-02-16 | 2015-02-16
**New Home - Detailed** | Inspect Polysteel First Level Forms | FALSE | 0 |  | 1 | 2015-02-16 | 2015-02-16
**New Home - Detailed** | Slab Survey - Take Elevations | FALSE | 0 |  | 1 | 2015-02-13 | 2015-02-13
**New Home - Detailed** | Rough Grade Lot | FALSE | 0 |  | 2 | 2015-02-13 | 2015-02-16
**New Home - Detailed** | Pop Out Slab | FALSE | 0 |  | 1 | 2015-02-13 | 2015-02-13
**New Home - Detailed** | Wreck Forms | FALSE | 0 |  | 2 | 2015-02-11 | 2015-02-12
**New Home - Detailed** | Wet Slab and Cover For Curing | FALSE | 0 |  | 3 | 2015-02-11 | 2015-02-13
**New Home - Detailed** | Pour Foundation | FALSE | 0 |  | 1 | 2015-02-10 | 2015-02-10
**New Home - Detailed** | Holt testing & observation | FALSE | 0 |  | 1 | 2015-02-10 | 2015-02-10
**New Home - Detailed** | Foundation Inspections | FALSE | 0 |  | 1 | 2015-02-09 | 2015-02-09
**New Home - Detailed** | Termite Treatment | FALSE | 0 |  | 1 | 2015-02-05 | 2015-02-05
**New Home - Detailed** | Install floor plugs and electrical grounds | FALSE | 0 |  | 1 | 2015-02-05 | 2015-02-05
**New Home - Detailed** | Close in forms | FALSE | 0 |  | 2 | 2015-02-05 | 2015-02-06
**New Home - Detailed** | Install steel | FALSE | 0 |  | 2 | 2015-02-03 | 2015-02-04
**New Home - Detailed** | Plumbing Copper Inspection | FALSE | 0 |  | 1 | 2015-02-02 | 2015-02-02
**New Home - Detailed** | Install french and area drains in slab | FALSE | 0 |  | 1 | 2015-01-30 | 2015-01-30
**New Home - Detailed** | Run plumbing copper | FALSE | 0 |  | 2 | 2015-01-29 | 2015-01-30
**New Home - Detailed** | Pull test ball (plumbing grounds) | FALSE | 0 |  | 1 | 2015-01-28 | 2015-01-28
**New Home - Detailed** | Grade pad, dig interior grade beams | FALSE | 0 |  | 2 | 2015-01-28 | 2015-01-29
**New Home - Detailed** | Plumbing Grounds Inspections | FALSE | 0 |  | 1 | 2015-01-27 | 2015-01-27
**New Home - Detailed** | Inspect int. piers, install steel and pour | FALSE | 0 |  | 1 | 2015-01-26 | 2015-01-26
**New Home - Detailed** | Plumbing grounds | FALSE | 0 |  | 2 | 2015-01-23 | 2015-01-26
**New Home - Detailed** | Drill Interior Piers | FALSE | 0 |  | 1 | 2015-01-23 | 2015-01-23
**New Home - Detailed** | Fill & Compact Base | FALSE | 0 |  | 5 | 2015-01-16 | 2015-01-22
**New Home - Detailed** | Dig Exterior Grade Beams | FALSE | 0 |  | 3 | 2015-01-16 | 2015-01-20
**New Home - Detailed** | Forms survey | FALSE | 0 |  | 1 | 2015-01-15 | 2015-01-15
**New Home - Detailed** | Set Forms | FALSE | 0 |  | 2 | 2015-01-13 | 2015-01-14
**New Home - Detailed** | Install steel, inspect and pour concrete | FALSE | 0 |  | 2 | 2015-01-09 | 2015-01-12
**New Home - Detailed** | Inspect Piers prior to steel | FALSE | 0 |  | 1 | 2015-01-08 | 2015-01-08
**New Home - Detailed** | Drill Exterior Piers | FALSE | 0 |  | 3 | 2015-01-05 | 2015-01-07
**New Home - Detailed** | Set Batter Boards & Grade Lines | FALSE | 0 |  | 2 | 2015-01-01 | 2015-01-02
**New Home - Detailed** | Check List Items before Set Forms | FALSE | 0 |  | 3 | 2014-12-29 | 2014-12-31
**New Home - Detailed** | Pre-Construction | FALSE | 0 |  | 20 | 2014-12-01 | 2014-12-26
**New Home - Basic** | Completion | FALSE | 0 |  | 1 | 2015-04-29 | 2015-04-29
**New Home - Basic** | Final touch up, punchout, clean. | FALSE | 0 |  | 5 | 2015-04-22 | 2015-04-28
**New Home - Basic** | Rough Punchout | FALSE | 0 |  | 4 | 2015-04-16 | 2015-04-21
**New Home - Basic** | Appliance Installation | FALSE | 0 |  | 1 | 2015-04-15 | 2015-04-15
**New Home - Basic** | Fences and Gates | FALSE | 0 |  | 2 | 2015-04-14 | 2015-04-15
**New Home - Basic** | Landscaping/Finish Grade | FALSE | 0 |  | 5 | 2015-04-14 | 2015-04-20
**New Home - Basic** | Structured Wiring Trim | FALSE | 0 |  | 4 | 2015-04-10 | 2015-04-15
**New Home - Basic** | Mirrors and Glasswork | FALSE | 0 |  | 1 | 2015-04-09 | 2015-04-09
**New Home - Basic** | Hardwood Floors Finish | FALSE | 0 |  | 4 | 2015-04-09 | 2015-04-14
**New Home - Basic** | Light Fixture Install | FALSE | 0 |  | 2 | 2015-04-07 | 2015-04-08
**New Home - Basic** | HVAC Finish | FALSE | 0 |  | 1 | 2015-04-07 | 2015-04-07
**New Home - Basic** | Interior Hardware Install | FALSE | 0 |  | 3 | 2015-04-07 | 2015-04-09
**New Home - Basic** | Flatwork | FALSE | 0 |  | 5 | 2015-04-07 | 2015-04-13
**New Home - Basic** | Pool Shell | FALSE | 0 |  | 5 | 2015-03-31 | 2015-04-06
**New Home - Basic** | Plumbing Fixtures Install | FALSE | 0 |  | 5 | 2015-03-31 | 2015-04-06
**New Home - Basic** | Hardwood Flooring Install | FALSE | 0 |  | 5 | 2015-03-31 | 2015-04-06
**New Home - Basic** | Countertop Install | FALSE | 0 |  | 5 | 2015-03-24 | 2015-03-30
**New Home - Basic** | Paint | FALSE | 0 |  | 10 | 2015-03-24 | 2015-04-06
**New Home - Basic** | Install Tile & Stone | FALSE | 0 |  | 20 | 2015-03-24 | 2015-04-20
**New Home - Basic** | Interior Millwork | FALSE | 0 |  | 15 | 2015-03-03 | 2015-03-23
**New Home - Basic** | Drywall | FALSE | 0 |  | 5 | 2015-02-24 | 2015-03-02
**New Home - Basic** | Exterior Masonry | FALSE | 0 |  | 30 | 2015-02-24 | 2015-04-06
**New Home - Basic** | Insulation Install | FALSE | 0 |  | 2 | 2015-02-20 | 2015-02-23
**New Home - Basic** | Structured Wiring Rough | FALSE | 0 |  | 5 | 2015-02-13 | 2015-02-19
**New Home - Basic** | Electrical Rough-In | FALSE | 0 |  | 5 | 2015-02-06 | 2015-02-12
**New Home - Basic** | Install Roof | FALSE | 0 |  | 15 | 2015-02-06 | 2015-02-26
**New Home - Basic** | Plumbing Top Out | FALSE | 0 |  | 5 | 2015-01-30 | 2015-02-05
**New Home - Basic** | HVAC Rough | FALSE | 0 |  | 5 | 2015-01-30 | 2015-02-05
**New Home - Basic** | Frame-Deck-Cornice | FALSE | 0 |  | 7 | 2015-01-21 | 2015-01-29
**New Home - Basic** | Foundation | FALSE | 0 |  | 7 | 2015-01-12 | 2015-01-20
**New Home - Basic** | Permits | FALSE | 0 |  | 10 | 2014-12-29 | 2015-01-09
**New Home - Basic** | Engineering Design | FALSE | 0 |  | 10 | 2014-12-15 | 2014-12-26
**New Home - Basic** | Architectural | FALSE | 0 |  | 30 | 2014-11-03 | 2014-12-12
Sample Job | Final Walkthrough | FALSE | 0 |  | 1 | 2012-11-12 | 2012-11-12
Sample Job | Final Punch-Out | FALSE | 0 |  | 10 | 2012-10-22 | 2012-11-02
Sample Job | Cleaning | FALSE | 0 |  | 15 | 2012-10-22 | 2012-11-09
Sample Job | Hardware Install | FALSE | 0 |  | 12 | 2012-10-04 | 2012-10-19
Sample Job | Interior Trim | FALSE | 0 |  | 22 | 2012-09-05 | 2012-10-04
Sample Job | Install Roof Shingles | FALSE | 0 |  | 7 | 2012-09-05 | 2012-09-13
Sample Job | Ceramic Tile | FALSE | 0 |  | 10 | 2012-09-05 | 2012-09-18
Sample Job | Drywall | FALSE | 0 |  | 18 | 2012-09-05 | 2012-09-28
Sample Job | Prep Paint | FALSE | 0 |  | 4 | 2012-08-30 | 2012-09-04
Sample Job | Exterior Landscape | FALSE | 0 |  | 31 | 2012-08-28 | 2012-10-09
Sample Job | Insulation | FALSE | 0 |  | 5 | 2012-08-23 | 2012-08-29
Sample Job | Brick Veneer | FALSE | 0 |  | 21 | 2012-07-25 | 2012-08-22
Sample Job | Brick Arch Forms | FALSE | 0 |  | 1 | 2012-07-24 | 2012-07-24
Sample Job | HVAC Rough-In | FALSE | 0 |  | 6 | 2012-07-20 | 2012-07-27
Sample Job | Specialty Rough-In | FALSE | 0 |  | 3 | 2012-07-19 | 2012-07-23
Sample Job | Garage Concrete Slab | FALSE | 0 |  | 3 | 2012-07-17 | 2012-07-19
Sample Job | Exterior Trim | FALSE | 0 |  | 6 | 2012-07-16 | 2012-07-23
Sample Job | Siding | FALSE | 0 |  | 3 | 2012-07-11 | 2012-07-13
Sample Job | Electrical Rough-In | FALSE | 0 |  | 6 | 2012-07-11 | 2012-07-18
Sample Job | Basement Concrete Slab | FALSE | 0 |  | 4 | 2012-07-11 | 2012-07-16
Sample Job | Roofing Paper Installed | FALSE | 0 |  | 3 | 2012-07-06 | 2012-07-10
Sample Job | Install Windows & Doors | FALSE | 0 |  | 3 | 2012-07-06 | 2012-07-10
Sample Job | Plumbing Rough-In | FALSE | 0 |  | 9 | 2012-06-29 | 2012-07-11
Sample Job | Frame Roof | FALSE | 0 |  | 7 | 2012-06-27 | 2012-07-05
Sample Job | 2nd Floor Framing | FALSE | 0 |  | 3 | 2012-06-22 | 2012-06-26
Sample Job | 1st Floor Framing | FALSE | 0 |  | 10 | 2012-06-08 | 2012-06-21
Sample Job | Foundation & Footings | FALSE | 0 |  | 10 | 2012-05-25 | 2012-06-07
Sample Job | Excavate for Foundation | FALSE | 0 |  | 2 | 2012-05-23 | 2012-05-24
Sample Job | Rough Grade Lot | FALSE | 0 |  | 1 | 2012-05-22 | 2012-05-22
Sample Job | Strip Topsoil & Stockpile | FALSE | 0 |  | 1 | 2012-05-21 | 2012-05-21
Sample Job | Stake Lot for Excavation | FALSE | 0 |  | 1 | 2012-05-21 | 2012-05-21
Sample Job | Clear Lot | FALSE | 0 |  | 3 | 2012-05-16 | 2012-05-18
Sample Job | Stake Lot | FALSE | 0 |  | 1 | 2012-05-15 | 2012-05-15
Sample Job | Bids & Contracts | FALSE | 0 |  | 15 | 2012-04-24 | 2012-05-14
Sample Job | Document & Plans Review | FALSE | 0 |  | 15 | 2012-04-03 | 2012-04-23
Sample Job | Contract Review | FALSE | 0 |  | 1 | 2012-04-02 | 2012-04-02

## Subs To Pay
Siding To Pay | Painters To Pay | Columns To Pay | Trellis To Pay | Rails To Pay | Screen Porch To Pay | Decking To Pay | Waterproof To Pay | Louvered Wall To Pay | Gutters To Pay | Jobs To Invoice | Jobs To Close
163 Edge of Auburn - Summit | #N/A |  | #N/A | #N/A | [5 empty] | Pinehurst Ct- Pinehurst | 244 Turkey Ridge
376 Paddington Station 60' | [10 empty] | 120 Annandale
251 Turkey Ridge
245 Turkey Ridge
50 Little River
37 Gardner Farms
137 Marin Woods
30 Elk Creek
25 Elk Creek
155 Preserve @ Jones Dairy
246 Turkey Ridge
264 Turkey Ridge
86 Carolina Landing
48 Little River
197 Falls Village
83 Summer Place
82 Summer Place
41 Gardner Farms
140 Annandale
5 Gardner Farms
88 Falls of The Cape